## Feuil1
WP | 1
T | 1.1 | Works on Sector 1 and horizontal studies
MS | 1 | T1.1 - Launch of works on the weirs of the Oise River (Sector 1) | 2027-03-01
MS | 2 | T1.1 - Launch of monitoring for compliance with the dam regulation | 2026-01-01
D | 1.1 | T1.1 - Completion of works on the weirs of the Oise River (Sector 1) | 2027-12-01
D | 1.2 | T1.1 - Launch of monitoring for compliance with the dam regulation | 2027-12-01
T | 1.2 | First works on Sector 2
MS | 3 | T1.2: Launch of tree and bush clearing on sector 2 | 2025-01-01
MS | 4 | T1.2 - Launch of works on the Catigny platform | 2025-06-01
MS | 5 | T1.2 - Launch of works on road deviations (Roads RD932 and RD934) | 2025-09-01
MS | 6 | T1.2 - Launch of excavation works for the lock of Noyon | 2025-07-01
MS | 7 | T1.2 – Launch of works on 3 bridges and 2 underpasses on Sector 2 | 2026-06-01
MS | 8 | T1.2 – Launch on works to build the A29 Highway Canal-Bridge | 2026-03-01
MS | 9 | T1.2 - Launch of works on the Creil-Jeumont railway line | 2026-06-01
MS | 10 | T1.2 - Launch of works on the Amiens-Laon railway line | 2026-08-01
MS | 11 | T1.2 – Launch of environmental and landscape design works on sector 2 (Stage 1) | 2025-09-01
D | 1.3 | T1.2 - Completion of tree and bush clearing on sector 2 | 2027-03-01
D | 1.4 | T1.2 - Completion of works on all construction quays | 2026-06-01
D | 1.5 | T1.2 - Completion of works on road deviations (Roads RD932 and RD934) | 2026-03-01
D | 1.6 | T1.2 - Completion of excavation works for the lock of Noyon | 2026-12-01
D | 1.7 | T1.2 – Completion of 3 bridges and 2 underpasses on Sector 2 | 2027-12-01
D | 1.8 | T1.2 – Completion of civil engineering works of the A29 Highway Canal-Bridge | 2027-12-01
D | 1.9 | T1.2 - Completion of works on the Creil-Jeumont railway line | 2027-12-01
D | 1.10 | T1.2 - Completion of works on the Amiens-Laon railway line | 2027-12-01
D | 1.11 | T1.2 – Completion of environmental and landscape design works on sector 2 (Stage 1) | 2027-04-01
T | 1.3 | First works on Sector 3
MS | 12 | T1.3: Launch of tree and bush clearing on sector 3 | 2025-09-01
MS | 13 | T1.3 – Launch of works on the deviation of road RD1017 | 2026-06-01
MS | 14 | T1.3 - Launch of works on banks of the Allaines platform | 2026-01-01
MS | 15 | T1.3 – Launch of environmental and landscape design works on sector 3 (Stage 1) | 2025-09-01
D | 1.12 | T1.3 - Completion of tree and bush clearing on sector 3 | 2026-05-01
D | 1.13 | T1.3 – Completion of works on the deviation of road RD1017 | 2026-12-01
D | 1.14 | T1.3 - Completion of works on banks of the Allaines platform | 2026-06-01
D | 1.15 | T1.3 – Completion of environmental and landscape design works on sector 3 (Stage 1) | 2027-04-01
T | 1.4 | First works on Sector 4
MS | 16 | T1.4: Launch of tree and bush clearing on sector 4 | 2025-09-01
MS | 17 | T1.4 – Launch of works on the Graincourt platform | 2025-10-01
MS | 18 | T1.4 – Launch of works on the RD7E | 2026-11-01
MS | 19 | T1.4 - Launch of excavation works for the lock of Oisy | 2025-04-01
MS | 20 | T1.4 - Launch of works on the highway A2's bridge | 2025-05-01
MS | 21 | T1.4 – Launch of environmental and landscape design works on sector 4 (Stage 1) | 2025-04-01
D | 1.16 | T1.4 - Completion of tree and bush clearing on sector 4 with the exclusion of the Canal du Nord sector | 2026-03-01
D | 1.17 | T1.4 – Completion of works on the Graincourt platform | 2026-02-01
D | 1.18 | T1.4 – Completion of works on the RD7E | 2027-12-01
D | 1.19 | T1.4 - Completion of excavation works for the lock of Oisy | 2026-03-01
D | 1.20 | T1.4 - Completion of works on the highway A2's bridge | 2027-12-01
D | 1.21 | T1.4 – Completion of environmental and landscape design works on sector 4 (Stage 1) | 2027-12-01
T | 1.5 | First works on Sector 5
MS | 22 | T1.5 - Launch of tree and bush clearing on sector 6 | 2026-01-01
MS | 23 | T1.5 - Launch of works to build a platform for works on Sector 6 | 2026-01-01
MS | 24 | T1.5 - Launch of works on road deviation on sector 6 | 2026-06-01
D | 1.22 | T1.5 - Completion of tree and bush clearing on sector 6 | 2027-03-01
D | 1.23 | T1.5 - Completion of works to build a platform for works on Sector 6 | 2027-06-01
D | 1.24 | T1.5 - Completion of works on road deviation on sector 6 | 2027-12-01
WP | 2 | Works on Sector 5 (locks)
T | 2.1 | Construction of 2 construction quays dedicated to construction works in Noyon and in Aubencheul-au-Bac, near the Oisy Lock
MS | 25 | T2.1 - Launch of works to build the platforms of Noyon and Oisy-le-Verger | 2025-01-01
D | 2.1 | T2.1 - Completion of works to build the platforms of Noyon and Oisy-le-Verger | 2025-09-01
T | 2.2 | Temporary road deviation
MS | 26 | T2.2 – Launch of works for the Allaine-Bouchavesne deviation | 2025-09-01
D | 2.2 | T2.2 – Completion of works for the Allaine-Bouchavesne deviation | 2025-12-01
T | 2.3 | Supply of specific equipment for the locks of Noyon and Oisy
MS | 27 | T2.3 – Notification of the contracts for the supply of equipment | 2026-01-01
D | 2.3 | T2.3 – All specific equipment under the horizontal contracts delivered for the locks of Noyon and Oisy | 2027-12-01
T | 2.4 | Connection to utility networks
MS | 28 | T2.4 – Signature of the first convention for the connection to utility networks | 2025-01-01
D | 2.4 | T2.4 – Completion of all network deviation works necessary for the lock construction phase | 2027-07-01
T | 2.5 | Works on the lock of Noyon
MS | 29 | T2.5 - Launch of works on the lock of Noyon (Stage 1) | 2026-02-01
MS | 30 | T2.5 – Launch of Stage 2 on the lock of Noyon | 2026-10-01
D | 2.5 | T2.5 – Completion of Stage 2 on the lock of Noyon | 2027-12-01
T | 2.6 | Works on the lock of Catigny
MS | 31 | T2.6 – Launch of works on the lock of Catigny | 2026-04-01
MS | 32 | T2.6 – Launch of Stage 2 on the lock of Catigny | 2026-12-01
D | 2.6 | T2.6 – Completion of Stage 2 on the lock of Catigny | 2027-09-01
T | 2.7 | Works on the lock of Allaines
MS | 33 | T2.7 – Launch of works on the lock of Allaines | 2026-08-01
MS | 34 | T2.7 – Launch of Stage 2 on the lock of Allaines | 2027-08-01
D | 2.7 | T2.7 – Completion of Stage 2 on the lock of Allaines | 2027-12-01
T | 2.8 | Works on the lock of Marquion
MS | 35 | T2.8 – Launch of works on the lock of Marquion | 2026-07-01
MS | 36 | T2.8 – Launch of Stage 2 on the lock of Marquion | 2027-05-01
D | 2.8 | T2.8 – Completion of Stage 2 on the lock of Marquion | 2027-08-01
T | 2.9 | Works on the lock of Oisy
MS | 37 | T2.9 – Launch of works on the lock of Oisy | 2025-08-01
MS | 38 | T2.9 – Launch of Stage 2 on the lock of Oisy | 2026-06-01
D | 2.9 | T2.9 – Completion of Stage 2 on the lock of Oisy | 2027-10-01
T | 2.10 | Works on the junction lock with Canal du Nord (Junction Lock)
MS | 39 | T2.10 – Launch of works on the Junction lock | 2026-08-01
MS | 40 | T2.10 – Launch of Stage 2 on the Junction lock | 2027-10-01
D | 2.10 | T2.10 – Completion of Stage 2 on the Junction lock | 2027-12-01

## Gantt (2)
|  | GANTT CHART | [9 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
|  | 23-EU-TG-SEINE-ESCAUT 2.3 |  | START | END | time axis 2024-07-31 to 2027-12-31
Project Month n° | time axis 2024-07-31 to 2027-12-31
WP | 1 |  |  | 2024-09-01 | 2027-12-31
T | 1.1 | Works on Sector 1 and horizontal studies |  | 2026-01-01 | 2027-12-31
MS | 1 | T1.1.1 - Launch of works on the weirs of the Oise River (Sector 1) | M31 | 2027-03-01 | 2027-03-31 | 2027-04-30: MS1
D | 1.1 | T1.1.1 - Completion of works on the weirs of the Oise River (Sector 1) | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D1.1
MS | 2 | T1.1.2 - Launch of monitoring for compliance with the dam regulation | M17 | 2026-01-01 | 2026-01-31 | 2026-02-28: MS2
D | 1.2 | T1.1.2 - Reports of monitoring for compliance with the dam regulation for years 2026 and 2027 | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D1.2
T | 1.2 | First works on Sector 2 |  | 2025-01-01 | 2027-12-31
MS | 3 | T1.2.1 - Launch of tree and bush clearing on sector 2 | M5 | 2025-01-01 | 2025-01-31 | 2025-02-28: MS3
D | 1.3 | T1.2.1 - Completion of tree and bush clearing on sector 2 | M31 | 2027-03-01 | 2027-03-31 | 2027-04-30: D1.3
MS | 4 | T1.2.2 - Launch of works on the Catigny platform | M10 | 2025-06-01 | 2025-06-30 | 2025-07-31: MS4
D | 1.4 | T1.2.2 - Completion of works on all construction quays | M22 | 2026-06-01 | 2026-06-30 | 2026-07-31: D1.4
MS | 5 | T1.2.3 - Launch of works on road deviations and the roundabout (Roads RD932 and RD934) | M11 | 2025-07-01 | 2025-07-31 | 2025-08-31: MS5
D | 1.5 | T1.2.3 - Completion of works on road deviations and the roundabout (Roads RD932 and RD934) | M19 | 2026-03-01 | 2026-03-31 | 2026-04-30: D1.5
MS | 6 | T1.2.4 - Launch of excavation works for the lock of Noyon | M11 | 2025-07-01 | 2025-07-31 | 2025-08-31: MS6
D | 1.6 | T1.2.4 - Completion of excavation works for the lock of Noyon | M28 | 2026-12-01 | 2026-12-31 | 2027-01-31: D1.6
MS | 7 | T1.2.5 – Launch of works on 3 bridges and 2 underpasses on Sector 2 | M22 | 2026-06-01 | 2026-06-30 | 2026-07-31: MS7
D | 1.7 | T1.2.5 – Completion of 3 bridges and 2 underpasses on Sector 2 | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D1.7
MS | 8 | T1.2.6 – Launch on works to build the A29 Highway Canal-Bridge | M19 | 2026-03-01 | 2026-03-31 | 2026-04-30: MS8
D | 1.8 | T1.2.6 – Completion of civil engineering works of the A29 Highway Canal-Bridge | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D1.8
MS | 9 | T1.2.7 - Launch of preparatory works on the Creil-Jeumont railway line | M14 | 2025-10-01 | 2025-10-31 | 2025-11-30: MS9
MS | 10 | T1.2.7 - Launch of main works on the Creil-Jeumont railway line | M22 | 2026-06-01 | 2026-06-30 | 2026-07-31: MS10
D | 1.9 | T1.2.7 – Completed preparatory works on the Creil-Jeumont line | M32 | 2027-04-01 | 2027-04-30 | 2027-05-31: D1.9
D | 1.10 | T1.2.7 – Completed removal of the top layer of soil for the Creil-Jeumont railway line | M33 | 2027-05-01 | 2027-05-31 | 2027-06-30: D1.10
D | 1.11 | T1.2.7 – Final crafting of metal for the construction of the necessary structures of the Creil-Jeumont railway line | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D1.11
D | 1.12 | T1.2.7 - Completed structure restoring the Divette watercourse on the Creil-Jeumont railway line | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D1.12
D | 1.13 | T1.2.7 – Completed abutments (2) on the Canal Seine-Nord Europe crossing structure of the Creil-Jeumont railway line | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D1.13
MS | 11 | T1.2.8 - Launch of preparatory works on the Amiens-Laon railway line | M14 | 2025-10-01 | 2025-10-31 | 2025-11-30: MS11
MS | 12 | T1.2.8 - Launch of main works on the Amiens-Laon railway line | M24 | 2026-08-01 | 2026-08-31 | 2026-09-30: MS12
D | 1.14 | T1.2.8 - Completed preparatory works on the Amiens-Laon line | M36 | 2027-08-01 | 2027-08-31 | 2027-09-30: D1.14
D | 1.15 | T1.2.8 – Completed removal of the top layer of soil for the Amiens-Laon railway line | M37 | 2027-09-01 | 2027-09-30 | 2027-10-31: D1.15
D | 1.16 | T1.2.8 – Final crafting of metal for the construction of the necessary structures of the Amiens-Laon railway line | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D1.16
D | 1.17 | T1.2.8 – Completed piles (4 out of 14) of the bridge of the Amiens-Laon railway line | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D1.17
D | 1.18 | T1.2.8 – Completed abutments (2) on the Canal Seine-Nord Europe crossing structure of the Amiens-Laon railway line | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D1.18
MS | 13 | T1.2.10 – Launch of environmental and landscape design works on sector 2 (Stage 1) | M13 | 2025-09-01 | 2025-09-30 | 2025-10-31: MS13
D | 1.19 | T1.2.10 – Completion of environmental and landscape design works on sector 2 (Stage 1) | M32 | 2027-04-01 | 2027-04-30 | 2027-05-31: D1.19
T | 1.3 | First works on Sector 3 |  | 2025-09-01 | 2027-04-30
MS | 14 | T1.3.1: Launch of tree and bush clearing on sector 3 | M13 | 2025-09-01 | 2025-09-30 | 2025-10-31: MS14
D | 1.20 | T1.3.1 - Completion of tree and bush clearing on sector 3 | M21 | 2026-05-01 | 2026-05-31 | 2026-06-30: D1.20
MS | 15 | T1.3 .2– Launch of works on the deviation of road RD1017 | M22 | 2026-06-01 | 2026-06-30 | 2026-07-31: MS15
D | 1.21 | T1.3 .2– Completion of works on the deviation of road RD1017 | M28 | 2026-12-01 | 2026-12-31 | 2027-01-31: D1.21
MS | 16 | T1.3 .3- Launch of works on banks of the Allaines platform | M17 | 2026-01-01 | 2026-01-31 | 2026-02-28: MS16
D | 1.22 | T1.3 .3- Completion of works on banks of the Allaines platform | M22 | 2026-06-01 | 2026-06-30 | 2026-07-31: D1.22
MS | 17 | T1.3 .4– Launch of environmental and landscape design works on sector 3 (Stage 1) | M13 | 2025-09-01 | 2025-09-30 | 2025-10-31: MS17
D | 1.23 | T1.3 .4– Completion of environmental and landscape design works on sector 3 (Stage 1) | M32 | 2027-04-01 | 2027-04-30 | 2027-05-31: D1.23
T | 1.4 | First works on Sector 4 |  | 2024-09-01 | 2027-12-31
MS | 18 | T1.4.1: Launch of tree and bush clearing on sector 4 | M13 | 2025-09-01 | 2025-09-30 | 2025-10-31: MS18
D | 1.24 | T1.4.1 - Completion of tree and bush clearing on sector 4 with the exclusion of the Canal du Nord sector | M19 | 2026-03-01 | 2026-03-31 | 2026-04-30: D1.24
MS | 19 | T1.4.2 – Launch of works on the Graincourt platform | M14 | 2025-10-01 | 2025-10-31 | 2025-11-30: MS19
D | 1.25 | T1.4.2 – Completion of works on the Graincourt platform | M18 | 2026-02-01 | 2026-02-28 | 2026-03-31: D1.25
MS | 20 | T1.4.3 – Launch of works on the RD7E | M27 | 2026-11-01 | 2026-11-30 | 2026-12-31: MS20
D | 1.26 | T1.4.3 – Completion of works on the RD7E | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D1.26
MS | 21 | T1.4.4 - Launch of excavation works for the lock of Oisy | M8 | 2025-04-01 | 2025-04-30 | 2025-05-31: MS21
D | 1.27 | T1.4.4 - Completion of excavation works for the lock of Oisy | M19 | 2026-03-01 | 2026-03-31 | 2026-04-30: D1.27
MS | 22 | T1.4.5 - Launch of works on the highway A2's bridge | M1 | 2024-09-01 | 2024-09-30 | 2024-10-31: MS22
D | 1.28 | T1.4.5 - Completion of works on the highway A2's bridge | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D1.28
MS | 23 | T1.4.6 – Launch of works on 4 bridges and 3 underpasses on Sector 4 | M26 | 2026-10-01 | 2026-10-31 | 2026-11-30: MS23
D | 1.29 | T1.4.6 – Completion of 4 bridges and 3 underpasses on Sector 4 | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D1.29
MS | 24 | T1.4.7 – Launch of environmental and landscape design works on sector 4 (Stage 1) | M8 | 2025-04-01 | 2025-04-30 | 2025-05-31: MS24
D | 1.30 | T1.4.7 – Completion of environmental and landscape design works on sector 4 (Stage 1) | M32 | 2027-04-01 | 2027-04-30 | 2027-05-31: D1.30
T | 1.5 | First works on Sector 6 |  | 2026-01-01 | 2027-12-31
MS | 25 | T1.5.1 - Launch of tree and bush clearing on sector 6 | M17 | 2026-01-01 | 2026-01-31 | 2026-02-28: MS25
D | 1.31 | T1.5.1 - Completion of tree and bush clearing on sector 6 | M31 | 2027-03-01 | 2027-03-31 | 2027-04-30: D1.31
MS | 26 | T1.5.2 - Launch of works to build a platform for works on Sector 6 | M17 | 2026-01-01 | 2026-01-31 | 2026-02-28: MS26
D | 1.32 | T1.5.2 - Completion of works to build a platform for works on Sector 6 | M34 | 2027-06-01 | 2027-06-30 | 2027-07-31: D1.32
MS | 27 | T1.5.3 - Launch of works on road deviation on sector 6 | M22 | 2026-06-01 | 2026-06-30 | 2026-07-31: MS27
D | 1.33 | T1.5.3 - Completion of works on road deviation on sector 6 | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D1.33
WP | 2 | Works on Sector 5 (locks) |  | 2025-01-01 | 2027-12-31
T | 2.1 | Construction of 2 construction quays dedicated to construction works in Noyon and in Aubencheul-au-Bac, near the Oisy Lock |  | 2025-01-01 | 2025-09-30
MS | 28 | T2.1 - Launch of works to build the platforms of Noyon and Oisy-le-Verger | M5 | 2025-01-01 | 2025-01-31 | 2025-02-28: MS28
D | 2.1 | T2.1 - Completion of works to build the platforms of Noyon and Oisy-le-Verger | M13 | 2025-09-01 | 2025-09-30 | 2025-10-31: D2.1
T | 2.2 | Temporary road deviation |  | 2025-09-01 | 2025-12-31
MS | 29 | T2.2 – Launch of works for the Allaine-Bouchavesne deviation | M13 | 2025-09-01 | 2025-09-30 | 2025-10-31: MS29
D | 2.2 | T2.2 – Completion of works for the Allaine-Bouchavesne deviation | M16 | 2025-12-01 | 2025-12-31 | 2026-01-31: D2.2
T | 2.3 | Supply of specific equipment for the locks of Noyon and Oisy |  | 2026-01-01 | 2027-12-31
MS | 30 | T2.3 – Notification of the contracts for the supply of equipment | M17 | 2026-01-01 | 2026-01-31 | 2026-02-28: MS30
D | 2.3 | T2.3 – All specific equipment under the horizontal contracts delivered for the locks of Noyon and Oisy | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D2.3
T | 2.4 | Connection to utility networks |  | 2025-01-01 | 2026-07-31
MS | 31 | T2.4 – Signature of the first convention for the connection to utility networks | M5 | 2025-01-01 | 2025-01-31 | 2025-02-28: MS31
D | 2.4 | T2.4 – Completion of all network deviation works necessary for the lock construction phase | M23 | 2026-07-01 | 2026-07-31 | 2026-08-31: D2.4
T | 2.5 | Works on the lock of Noyon |  | 2026-02-01 | 2027-12-31
MS | 32 | T2.5 - Launch of works on the lock of Noyon (Stage 1) | M18 | 2026-02-01 | 2026-02-28 | 2026-03-31: MS32
MS | 33 | T2.5 – Launch of Stage 2 on the lock of Noyon | M26 | 2026-10-01 | 2026-10-31 | 2026-11-30: MS33
D | 2.5 | T2.5 – Completion of Stage 2 on the lock of Noyon | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D2.5
T | 2.6 | Works on the lock of Catigny |  | 2026-04-01 | 2027-09-30
MS | 34 | T2.6 – Launch of works on the lock of Catigny | M20 | 2026-04-01 | 2026-04-30 | 2026-05-31: MS34
MS | 35 | T2.6 – Launch of Stage 2 on the lock of Catigny | M28 | 2026-12-01 | 2026-12-31 | 2027-01-31: MS35
D | 2.6 | T2.6 – Completion of Stage 2 on the lock of Catigny | M37 | 2027-09-01 | 2027-09-30 | 2027-10-31: D2.6
T | 2.7 | Works on the lock of Allaines |  | 2026-08-01 | 2027-12-31
MS | 36 | T2.7 – Launch of works on the lock of Allaines | M24 | 2026-08-01 | 2026-08-31 | 2026-09-30: MS36
MS | 37 | T2.7 – Launch of Stage 2 on the lock of Allaines | M36 | 2027-08-01 | 2027-08-31 | 2027-09-30: MS37
D | 2.7 | T2.7 – Completion of Stage 2 on the lock of Allaines | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D2.7
T | 2.8 | Works on the lock of Marquion |  | 2026-07-01 | 2027-08-31
MS | 38 | T2.8 – Launch of works on the lock of Marquion | M23 | 2026-07-01 | 2026-07-31 | 2026-08-31: MS38
MS | 39 | T2.8 – Launch of Stage 2 on the lock of Marquion | M33 | 2027-05-01 | 2027-05-31 | 2027-06-30: MS39
D | 2.8 | T2.8 – Completion of Stage 2 on the lock of Marquion | M36 | 2027-08-01 | 2027-08-31 | 2027-09-30: D2.8
T | 2.9 | Works on the lock of Oisy |  | 2025-08-01 | 2027-10-31
MS | 40 | T2.9 – Launch of works on the lock of Oisy | M12 | 2025-08-01 | 2025-08-31 | 2025-09-30: MS40
MS | 41 | T2.9 – Launch of Stage 2 on the lock of Oisy | M22 | 2026-06-01 | 2026-06-30 | 2026-07-31: MS41
D | 2.9 | T2.9 – Completion of Stage 2 on the lock of Oisy | M38 | 2027-10-01 | 2027-10-31 | 2027-11-30: D2.9
T | 2.10 | Works on the junction lock with Canal du Nord (Junction Lock) |  | 2026-08-01 | 2027-12-31
MS | 42 | T2.10 – Launch of works on the Junction lock | M24 | 2026-08-01 | 2026-08-31 | 2026-09-30: MS42
MS | 43 | T2.10 – Launch of Stage 2 on the Junction lock | M38 | 2027-10-01 | 2027-10-31 | 2027-11-30: MS43
D | 2.10 | T2.10 – Completion of Stage 2 on the Junction lock | M40 | 2027-12-01 | 2027-12-31 | [42 empty] | D2.10
T | 2.11 | Project planning review | M40 | 2025-01-01 | 2027-12-31
D | 2.11 | Progress report (M1 M12) | M12 | 2025-08-01 | 2025-08-31 | 2025-09-30: D2.11
D | 2.12 | Project planning review report (WP1 WP2) | M24 | 2026-08-01 | 2026-08-31 | 2026-09-30: D2.12
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0