## Event Calendar
Activities/Events/Materials | Number of Participants | Special Needs | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31 | 2028-01-31 | 2028-02-29 | 2028-03-31 | 2028-04-30 | 2028-05-31 | 2028-06-30 | 2028-07-31 | 2028-08-31 | 2028-09-30 | 2028-10-31 | 2028-11-30 | Notes
Launching Event (Opening Ceremony) | September 2025: 200 September 2026: 50
Coordination and steering meetings/workshops (hall rent, transportation, refreshments) | SCM in every 6 months (60 ppl.) TCM in every 3 months (35 ppl)
Annual team meetings (orientation, planning, review, empowerment, etc.) | 30 ppl each 4 meetings
Team meetings and staff empowerment (EF) | 30 ppl each 4 meetings
1.1.1. OUTREACH activities by VTC outreach teams
Training of outreach teams | 750
Assessment feedback outreach teams | 160
Refreshing trainings for outreach teams | 500
1.2.1. In-kind support to apprentice students
Consultation meetings on potential incentives | 90
1.2.2. Providing risk prevetion measures to apprentice students to ensure their graduation
Training for early identification mechanism for identifying students at risk of drop-out -emphasis on girls | 900
Assessment and feedback meetings | 90
1.2.3. Providing career guidance, mentoring, and administrative, legal, & in-kind entrepreneurship support scheme
Entrepreneurship ToT for grades 11th and 12th students/ career days/networking | 240
Conduct training for entrepreneurs | 1200
2.1.2 Developing and implementing a capacity building strategy for the selected VTCs
Providing training to school project team (400 pax VTC+15 people programme team*5 days) | 2075
Establishment of expert pool and orientation (50 pax*3 days) | 150
Training in all selected VTCs Students' work file software (school side) (3pax/VTC*2 days) | 240
Central and local level trainings (500 pax local + 25 trainers/3 days) | 150
2.1.4 Developing and implementing a model for strengthening VTC-Workplace partnership
Present the model to schools (2days/VTC) | 80
Implement the model (4 years)-school level meetings | 40
2.1.6 Providing small-scale rehabilitation and equipment support to improve practical learning environment at workplaces
Feedback meetings to finalize the checklists (50 pax/2 days/3 times) | 300
2.3.1 Identifying and developing relevant extracurricular activities
Consultation meetings with VTCs, enterprises, professional organisations,apprentice students 30pax/4 sessions/3 days | 360
Consultation meetings to receive feedback on developed content, material, assessment and evaluation system and proposed incentives (50 pax*3days) | 150
2.3.2 Implementing extracurricular activities in partner VTCs
Training VTC personnel on extracurricular activities (80 pax*2 days) | 160
Feedback gathering meetings with implementers (40 pax*2 days*3 times) | 240
Feedback gathering meetings with apprentice students (40 pax*2 days*3 times) | 240
2.3.3 Organizing social cohesion activities (including forums, solidarity events) in VTCs and workplaces
Train school teams to be assigned for social cohesion activities with special emphasis on inclusiveness (80 pax (2pax/VTC)/3 days) | 160
Implement the local level social cohesion activities | 34000
Apprenticeship Student Forums (40VTC*3pax+30*2days*4 years) | 1200
Social Solidarity activities (40VTC*6pax+30*2days*3 years) | 1620
2.3.5 Organising Institutional and local based awareness raising activities to promote apprenticeship training and fight against child labour
Organising information meeting to secondary education school counselors to promote apprenticeship training (50 school counselor/12 province) A. Activity for Middle School Counsellor Teachers: "Apprenticeship Training and Future Professions Informational Meeting" | 14 province*45 ppl=630 (14 events)
Organising experience sharing platforms with the participation of VTCs and workplaces (including study visits?) (50 participants/3 days/4 times) F. Experience Sharing Platform Activities "Field Visit and Knowledge Sharing for Social Benefit" (June 2026) | 600
4 study visits (school managers/leader students/workplace representatives) 20pax*4 times*3days G. Apprenticeship Training Study Visit: Best Practices (2027) | 240
Conduct community based outreach activities (mobilise community leaders, influencers) (125 pax/40 VTC/2 times) C. Community-Based Outreach Activities "Meetings with Community Leaders" | 14 province*27ppl*26 events
Awareness raising meetings on child labour (100 participants/12 province/3 times) E. Activities on Combating Child Labour (CCL): My Apprentice Students on the Path to Mastery | 3600
Organise information meetings to secondary education school counsellors to promote apprenticeship training B. VTC Circle Event to be organized by Vocational Training Centre Teams: “First Step on the Path to Mastery” | 11000
Note on O33: User: These meetings were budgeted but their realisation will depend on the desk-review study. There is possibility that these meetings may not take place.