## Financial offer
TRANCHE 1: PRELIMINARY ESIA STUDY (FIRM)
Deliverables | Unit | Quantity | Total (excl. VAT) | Total (incl. VAT)
1.1 Inception Report | LS | 1 |  | 0
Description of expected service: Preparation and submission of an Inception Report detailing the Contractor’s understanding of the project context, objectives, and expected outcomes. The report shall outline the proposed methodology for both the Preliminary and Final ESIA phases, the detailed work plan (Gantt chart), team composition and responsibilities, logistical and data requirements, interface arrangements with key stakeholders (SAJ, NWA, NEPA, Expertise France), and a launch plan for initial fieldwork and regulatory alignment. The report shall also identify risks, assumptions, and any proposed adjustments to the initial scope. Condition for payment: Payment will be made upon formal written approval of the Inception Report by the Client (Expertise France), including any necessary revisions requested within 15 calendar days of submission.
1.2 Scoping report | LS | 1 |  | 0
Description of expected service: Preparation and submission of a Scoping Report to define the scope and focus of the Environmental and Social Impact Assessment. The report shall include a refined description of the project and its area of influence, a preliminary identification of key environmental and social issues, a stakeholder mapping and engagement strategy, a proposed methodology for the baseline assessment and impact analysis, and an outline of the expected structure of the ESIA report. The Scoping Report shall also specify data gaps, institutional and legal considerations (including NEPA and IFI requirements), and a proposed structure for the Environmental and Social Management Plan (ESMP). Condition for payment: Payment will be made upon formal written approval of the Scoping Report by the Client (Expertise France), incorporating any requested revisions and provided no later than 15 calendar days after submission.
1.3 Preliminary ESIA report incl. Preliminary ESMP | LS | 1 |  | 0
Description of expected service: Preparation and submission of a Preliminary Environmental and Social Impact Assessment (ESIA) report based on the Preliminary Design. The report shall include a baseline analysis of key environmental and social conditions, a preliminary assessment of potential impacts, a summary of stakeholder concerns gathered during early engagement, and proposed mitigation and enhancement measures. The report shall also contain a Preliminary Environmental and Social Management Plan (Preliminary ESMP), outlining initial actions, responsibilities, and monitoring indicators. The deliverable must be compliant with both NEPA requirements and relevant international standards, notably the IFI Environmental and Social Standards and Equator Principles. Condition for payment: Payment will be made upon formal written approval of the Preliminary ESIA report and Preliminary ESMP by the Client (Expertise France), after review and integration of any comments received within 20 calendar days of submission.
1.4 Management of stakeholder consultations and public meetings | LS | 1 |  | 0
Description of expected service: Management of stakeholder consultations during the Preliminary ESIA phase, with the support of Expertise France and SAJ and/or NWA. This includes the planning, coordination, and implementation of consultation activities such as community meetings, interviews, and focus groups. The Contractor shall be responsible for preparing communication materials, ensuring inclusive and culturally appropriate engagement, and documenting stakeholder feedback. If public meetings are not required by NEPA, the Contractor shall still conduct appropriate consultations in line with IFI Environmental and Social Standards, particularly on stakeholder engagement. Condition for payment: Payment will be made upon submission and approval by the Client (Expertise France) of a public consultation report, including attendance records, meeting minutes, presentation materials, and a summary of feedback and responses, as well as the submission to NEPA and formal issuance of the NRCA environmental permit.
1.5 Management of interactions with NEPA | LS | 1 |  | 0
Description of expected service: Management of interactions with the National Environment and Planning Agency (NEPA) during the Preliminary ESIA phase, with the support of Expertise France and SAJ and/or NWA. The Contractor shall be responsible for coordinating exchanges with NEPA, clarifying applicable regulatory requirements, preparing and submitting all relevant documentation (including the Preliminary ESIA report and associated forms), attending coordination meetings, following up on NEPA inputs, and ultimately assisting in securing the NRCA environmental permit. The objective is to ensure early and full alignment of the ESIA process with national procedures and to anticipate formal requirements for any subsequent updates during the Final ESIA stage. Condition for payment: Payment will be made upon written confirmation by the Client (Expertise France) of satisfactory coordination of exchanges with NEPA, supported by documentation such as meeting notes, submission logs, correspondence records, and evidence of issuance of the NRCA environmental permit.
Sub-Total of the Tranche 1 : |  |  |  | 0
TRANCHE 2: FINAL ESIA STUDY (OPTIONAL)
Deliverables | Unit | Quantity | Total (excl. VAT) | Total (incl. VAT)
2.1 Final ESIA report incl. ESMP | LS | 1 |  | 0
Description of expected service: Preparation and submission of a Final Environmental and Social Impact Assessment (ESIA) report reflecting the outcomes of the Detailed Design phase. This update shall incorporate any necessary adjustments to the baseline, impact assessment (environmental and social), cumulative and residual impacts, as well as stakeholder feedback. It shall also include an updated Environmental and Social Management Plan (ESMP) detailing mitigation measures, institutional responsibilities, monitoring indicators, budget estimates, and grievance redress mechanisms. The Final ESIA shall ensure continued compliance with NEPA requirements and align with IFI Environmental and Social Standards and the Equator Principles. Condition for payment: Payment will be made upon formal written approval by the Client (Expertise France) of the Final ESIA report and ESMP, incorporating all revisions requested after internal and stakeholder reviews, and delivered in a final format ready for submission to NEPA as an addendum or supplementary documentation if required.
2.2 Management of stakeholder consultations and public meetings | LS | 1 |  | 0
Description of expected service: Management of stakeholder consultation, if required for the Final ESIA, in coordination with NEPA and with the support of Expertise France and SAJ and/or NWA. The Contractor shall be responsible for preparing and delivering presentation materials (including a non-technical summary), organising and facilitating the meeting(s), managing invitations and logistics, and drafting the official public meeting report. If NEPA does not require formal public meetings, the Contractor shall propose and implement a suitable public disclosure activity in accordance with IFI Environmental and Social Standards, ensuring meaningful consultation with affected communities and other stakeholders. Condition for payment: Payment will be made upon submission and approval by the Client (Expertise France) of the complete public consultation or disclosure report, including attendance records, meeting minutes, presentation materials, and a summary of feedback and responses.
2.3 Management of interactions with NEPA | LS | 1 |  | 0
Description of expected service: Management of interactions with NEPA for the update of the environmental authorisation following the Detailed Design phase, in close collaboration with Expertise France and SAJ and/or NWA. The Contractor shall take the lead in preparing and submitting any necessary addenda or supplementary documentation to the approved Preliminary ESIA, responding to technical comments or requests for clarification from NEPA, and participating in any required meetings or site visits. The Contractor shall ensure that the process remains fully aligned with NEPA’s regulatory procedures and that all administrative and technical obligations are met to maintain compliance with the existing environmental permit. Condition for payment: Payment will be made upon receipt of formal confirmation from NEPA or the NRCA validating the updated environmental documentation, as required to maintain or amend the existing environmental authorisation.
Sub-Total of Tranche 2 : |  |  |  | 0
GRAND TOTAL |  |  |  | 0

## Resource Planning Table
FIRM TRANCHE : PRELIMINARY ESIA STUDY
Deliverables | Unit | Quantity | Location
1.1 Inception Report
Team Leader | person-day
Environmental Specialist | person-day
Hydrology / Drainage Specialist | person-day
Water Quality / Marine Biologist | person-day
Air / Noise / Climate Specialist | person-day
Health & Safety Specialist | person-day
Social Specialist | person-day
Stakeholder Engagement Expert | person-day
Stakeholder Engagement Expert | person-day
GIS / Mapping Expert | person-day
Legal / Regulatory Advisor | person-day
Administrative / Logistics | person-day
1.2 Scoping report
Team Leader | person-day
Environmental Specialist | person-day
Hydrology / Drainage Specialist | person-day
Water Quality / Marine Biologist | person-day
Air / Noise / Climate Specialist | person-day
Health & Safety Specialist | person-day
Social Specialist | person-day
Stakeholder Engagement Expert | person-day
Stakeholder Engagement Expert | person-day
GIS / Mapping Expert | person-day
Legal / Regulatory Advisor | person-day
Administrative / Logistics | person-day
1.3 Preliminary ESIA report incl. Preliminary ESMP
Team Leader | person-day
Environmental Specialist | person-day
Hydrology / Drainage Specialist | person-day
Water Quality / Marine Biologist | person-day
Air / Noise / Climate Specialist | person-day
Health & Safety Specialist | person-day
Social Specialist | person-day
Stakeholder Engagement Expert | person-day
Stakeholder Engagement Expert | person-day
GIS / Mapping Expert | person-day
Legal / Regulatory Advisor | person-day
Administrative / Logistics | person-day
1.4 Management of stakeholder consultations and public meetings
Team Leader | person-day
Environmental Specialist | person-day
Hydrology / Drainage Specialist | person-day
Water Quality / Marine Biologist | person-day
Air / Noise / Climate Specialist | person-day
Health & Safety Specialist | person-day
Social Specialist | person-day
Stakeholder Engagement Expert | person-day
Stakeholder Engagement Expert | person-day
GIS / Mapping Expert | person-day
Legal / Regulatory Advisor | person-day
Administrative / Logistics | person-day
1.5 Management of interactions with NEPA
Team Leader | person-day
Environmental Specialist | person-day
Hydrology / Drainage Specialist | person-day
Water Quality / Marine Biologist | person-day
Air / Noise / Climate Specialist | person-day
Health & Safety Specialist | person-day
Social Specialist | person-day
Stakeholder Engagement Expert | person-day
Stakeholder Engagement Expert | person-day
GIS / Mapping Expert | person-day
Legal / Regulatory Advisor | person-day
Administrative / Logistics | person-day
Sub-Total of the Phase 1 :
OPTIONAL TRANCHE 1 : FINAL ESIA STUDY
Deliverables | Unit | Quantity | Location
2.1 Final ESIA report incl. ESMP
Team Leader | person-day
Environmental Specialist | person-day
Hydrology / Drainage Specialist | person-day
Water Quality / Marine Biologist | person-day
Air / Noise / Climate Specialist | person-day
Health & Safety Specialist | person-day
Social Specialist | person-day
Stakeholder Engagement Expert | person-day
Stakeholder Engagement Expert | person-day
GIS / Mapping Expert | person-day
Legal / Regulatory Advisor | person-day
Administrative / Logistics | person-day
2.2 Management of stakeholder consultations and public meetings
Team Leader | person-day
Environmental Specialist | person-day
Hydrology / Drainage Specialist | person-day
Water Quality / Marine Biologist | person-day
Air / Noise / Climate Specialist | person-day
Health & Safety Specialist | person-day
Social Specialist | person-day
Stakeholder Engagement Expert | person-day
Stakeholder Engagement Expert | person-day
GIS / Mapping Expert | person-day
Legal / Regulatory Advisor | person-day
Administrative / Logistics | person-day
2.3 Management of interactions with NEPA
Team Leader | person-day
Environmental Specialist | person-day
Hydrology / Drainage Specialist | person-day
Water Quality / Marine Biologist | person-day
Air / Noise / Climate Specialist | person-day
Health & Safety Specialist | person-day
Social Specialist | person-day
Stakeholder Engagement Expert | person-day
Stakeholder Engagement Expert | person-day
GIS / Mapping Expert | person-day
Legal / Regulatory Advisor | person-day
Administrative / Logistics | person-day
Sub-Total of Phase 2 :
GRAND TOTAL