Intellectual services procurement

Terms of Reference (ToR)

Adapted procedure

In application of article R2123-1 of the public procurement code

Purpose

Implementation and operationalization of the SETAVA (long-term support)

Table of Content

List of Abbreviations

1.	General information on the services’ background	4

1.1.	Background of EU FLEGT VPA Programme	4

1.2.	Global and specific objectives of the EU FLEGT VPA Programme	5

1.3.	Governance and contracting authority	6

2.	Context of the FLEGT VPA in Honduras	7

3.	Description of the service	8

3.1.	Objective of the assignment	8

3.2.	Main tasks expected of the service provider	9

3.3.	Deliverables	10

3.4.	Indicative calendar and deadlines	11

4.	Services to be provided by the Client	11

5.	Communication	11

6.	Indication of key position and expected profiles	12

7.	Estimated budget	14

List of Abreviations

AFD Agence Française de Développement

ALA Facility African and Latin American Facility

CSO Civil Society Organizations

DG-ENV Directorate-General Environment

DG-INTPA Directorate-General for International Partnerships

EFI European Forest Institute

EU European Union

EUTR European Union Timber Regulation

FSOs Forest Sector Operators

FLEGT Forest Law Enforcement, Governance and Trade

GFC Guyana Forestry Commission

GNP Gross National Product

ICF Instituto de Conservación Forestal

JIC Joint Implementation Committee

NGO Non-Governmental Organization

REDD+ Réduction des Emissions issus de la Déforestation et de la Dégradation forestière

SETAVA Secretaría Técnica del Acuerdo de Voluntario de Asociación

SIIAVA Interinstitutional Secretariat for the Implementation of the FLEGT VPA

SMEs Small and Medium-sized Entreprises

TLAS Timber Legality Assessment System

VPA Voluntary Partnership Agreements

# General information on the services’ background

## Background of EU FLEGT VPA Programme

In 2003, in a bilateral dialogue between the European Union (EU) and the main tropical producer countries aimed at strengthening forest governance, the participation of civil society in the implementation of their forest policies, and the elimination of illegal logging through the formalisation of their forest-timber value chains, the EU adopted the Forest Law Enforcement, Governance and Trade (FLEGT) Action Plan.

The EU FLEGT Action Plan protects tropical forests from the devastating effects of illegal logging. Forests support 90% of the world’s biodiversity, regulate water quality, and mitigate climate change by absorbing and storing close to half of the world’s terrestrial carbon. Trade related to the illegal logging of tropical forests has caused the price of tropical timber to fall by more than 30% on international markets. Interpol estimates that 50-90% of tropical forest logging is illegal. In 2018, the number of financial transactions linked to illegal trade in timber products was estimated at more than 100 billion dollars (Interpol, April 2019). Illegal logging is a recurrent subject of media campaigns and damages the image of tropical timber, which accounts for only a marginal share of the global forest-timber value chain (1% of global forest production) and erodes the confidence of European consumers. In tropical countries, it is detrimental both to the maintenance of the integrity of forest ecosystems and to forest-dependent populations, considered to be the poorest on the planet.

Voluntary Partnership Agreements (VPAs) are a key component of the EU Forest Law Enforcement, Governance and Trade (FLEGT) Action Plan to address illegal logging. A VPA seeks to ensure that timber and timber products imported into the EU from a partner country comply with the laws of that country.

To achieve this, a partner country must first decide which parts of its national legal framework it will use to define legality for the purposes of the VPA. The country must also have, and describe in the VPA text and annexes, a system to ensure legal compliance and issue legal products with FLEGT licenses. In most cases, a country will build on existing systems to achieve this.

However, the implementation of VPAs has been impeded by several institutional and technical requirements. Until today, one country has been authorised to issue FLEGT licenses (Indonesia), and eight other countries have committed to implementing a VPA (Cameroon, Central African Republic, Ghana, Guyana, Honduras, Liberia, Republic of Congo and Vietnam). Currently, these group of eight countries are included in the EU FLEGT VPA Programme wich are at different stages of progress.

To ensure the credibility of the entire process and allow the VPAs to achieve their full potential, it is necessary for the EU to continue its support for their implementation. The main constraints are country-specific, but generally involve the operationalisation of a Timber Legality Assurance System (TLAS), which relies on a complete national chain of transparency led by the country's administration. This presents many technical, financial, organisational and institutional challenges due to the changes in practices imposed on numerous historical or newly associated actors in the forest-based value chain.

The implementation of a VPA thus requires substantial investments and continuous, well-targeted technical and financial support. Within this framework (2021-2025), French Development Agency -AFD is implementing, through an EU funds delegation, a program whose purpose is to support the eight (8) countries mentioned above, recognized by the EU as its most committed partners in the fight against illegal logging, in the implementation of their VPAs.

This programme will complement and monitor support to FLEGT processes by international organisations, civil society organisations, multilateral agencies, and EU Member States in the current VPA partner countries, including:

- Action programmes that provide assistance to governments and financial support through calls for proposals to other stakeholders (CSOs and the private sector), funded by the EU or other donors. In particular, synergies will be fostered with the VPA ALA facility; the ‘Forest for the Future’ (F4) facility (led by the Environment, Sustainable Natural Resources Unit of the Directorate General for International Partnerships [INTPA.F.2], which aims at promoting forest value chains and stimulating private sector investments, or the FLEGT programme for regional Asia managed by DG-ENV.

- Action programmes focused on REDD+, which support the strengthening of land governance in third countries (monitoring and control of uses to maintain forest cover).

- To avoid duplicating efforts and resources, coordination will also be ensured at country level via an information exchange mechanism involving all actors engaged in FLEGT processes and through strengthened dialogue with the FLEGT and EU Timber Regulation (EUTR) expert group.

## Global and specific objectives of the EU FLEGT VPA Programme

The overall objective of the Programme is to contribute to the sustainable management of forests.

The specific objective is to improve forest governance and law enforcement in the countries implementing a VPA in order to stop illegal logging therein.

This programme has three main components:

- Component 1: Institutional support covering the actions necessary for the legal and equitable supply of timber by ensuring its traceability

- Component 2: Stakeholder support focusing on NGOs, communities and the private sector to build their capacity to contribute to the implementation of the VPA in their country

- Component 3: Programme management (technical coordination, financial and administrative management, monitoring/evaluation)

- Component 4 :  Technical support by the FLEGT Africa and Latin America (FLEGT-ALA) Facility led by FAO.

The EU FLEGT VPA Programme (2021-2025) aims to develop components 1 and 2 based on:

| Component 1/C1: Institutional support | Component 2 /C2: Stakeholder support to NGOs, communities, and the private sector |
| --- | --- |
| Content : - The latest conclusions of JMRC and its work plans - An analysis of the VPA implementation framework - An analysis of the financing gaps - The financial and technical assistance needs identified by the partner country and the EU-Delegation | Content: - Strengthening the capacity and the involvement of stakeholders to contribute effectively to the processes related to the implementation of the VPAs. - The targeted beneficiaries are: CSOs, Private Sector, Communities. - Demand-driven grant mechanism aligned with the objectives defined in each country's VPA implementation framework. |
| Main possible activities: - Support the development and deployment of Timber Legality Assurance Systems (TLAS) VPA-compliant. - Capacity-building of administration officers in charge of forests. - Contribution to national normative and legal reform in line with VPA requirements. - Strengthening transparency, monitoring, and controls mechanisms. - Strengthening of complaint/grievance mechanisms required by VPAs. - Coordination with other forest governance initiatives at the national level. | Main possible activities: - Continuing support to independent forest monitoring. - Strengthening the compliance of SMEs and micro-enterprises with TLAS. - Improving access of SMEs and microenterprises to capital, legal supply chains and markets. - Supporting the participation of women and youth in VPA-compliant forest management and small-scale wood processing enterprises |

The Programme is currently active in five countries: Ghana, Republic of Congo, Liberia, Honduras and Guyana.

In each of these countries, the beneficiaries of funding under this programme will be:

- on one hand, government institutions (component 1) for the implementation of actions to operationalize the VPAs: support to the national timber legality assurance system (LAS), adaptation of national legislation, transparency and monitoring and control mechanisms in the forestry sector, etc.;

- on the other hand, civil society organizations, communities and the private sector (component 2), in particular marginalized groups (indigenous peoples, women) and small businesses, to strengthen their capacity to effectively contribute to the VPA implementation process, and to ensure that this process does not exclude them from legality.

## Governance and contracting authority

AFD is the contracting authority of this programme and is leading a steering committee which includes representatives of the EU commission (DG INTPA and DG ENV), the management unit (technical operator and the administrative and financial operator) and the European Forests Institute as an observer.

AFD relies on the two operators of the management unit as contracting authority support:

- Eticwood/Nature+ (technical operator) in charge of the technical follow-up and the implementation of the activities in the countries included in the programme (establishing terms of reference for activities and following up deliverables) ;

- e-sud développement (administrative and financial operator) in charge of the administrative and financial management (procurement process, financial monitoring, invoices…).

# Context of the FLEGT VPA in Honduras

- About 5.4 million ha of Honduras, are covered by forests, which represent 47.7% of the land area. Since 2015, Honduras lost about 12.5% of its forest area. Anthropogenic causes such as deforestation and illegal logging amount to 0.5% (24.000 ha annually), while loss due to climate changes im-pact is 12% of which 11% (600.000 ha) is due to pest infestation, and 1% (56.000 ha annually) is due to forest fires.

- The basic types of forest land tenure include: private (35%), Indigenous (3%), State (27%), Municipal (4%), community  (10%), and the remaining (21%) have not been assessed to determine its land tenure.  A total of about 441 Forest Management Plans, or 304.000 ha (5%) of forests, which constitutes only 2% of the national policy target, are being executed. However, there are human activities in almost 80% of the forest area with the intrusion of, among other, illegal loggers, drugs traffickers’ money launders, and immigrants such as impoverished families seeking to improve their livelihood by entering into agroforestry and pastoral activities. Honduras forests are therefore being threatened by non-sustainable activities. The biological corridor of Central America, which constitutes part of such forests and plays a pivotal role in maintaining the biological richness of this region, is at risk.

- The forest sector amounted to an average of 3.6 % of the GNP in the last 16 years.  Since 2010 im-port values of timber products has risen only by 6% (from 45 to 48 million EUR), while exports have risen by 62% (from 44 to 71 million EUR).  Export values to Europe rose from EUR 1,5 million to EUR 3,5 million in 2016, which constitute only 4.9% of the exports. The USA continues to be the main trade partner with exports rising from EUR 20 million to EUR 27 million (35%) in 2016. However, ex-ports have noticeably risen in neighbouring countries with El Salvador and Nicaragua constituting EUR 20 million (28%), the second trade partners of Honduran timber products.

- In 2010, Honduras developed a strategy to fight illegal logging (Estrategia Nacional contra la Tala Ilegal). The implementation of this strategy was one of Honduras’ main reasons to enter into VPA negotiations, which started in January 2013. Honduras became thereby the first Latin American country starting to negotiate a VPA with the EU.

- In June 2018, the Parties, represented by the Minister-Director of Forests of Honduras and the Director-General of DEVCO, initialled the VPA in Tegucigalpa, witnessed by the President of Honduras and the Ambassador of the EU in Honduras. The Agreement was ratified by both Parties in 2021 and will soon enter into force, after which the implementation phase will formally commence.

- The first meeting of the pre-Joint Implementation Committee took place on 15 June 2018. During that meeting the EU and the Honduran government agreed on the need for the elaboration of a multi-year implementation plan, including specific annual operation plans, for the VPA. These plans were developed during the second semester of 2018. In March 2019, during the second pre-Joint Implementation Committee, the Parties agreed on the first draft of the multi-year implementation plan. In 2020, Honduras updated that document and produced a second draft of the multi-year implementation plan that has yet to be discussed and formalized by the Parties.

- The coordination of the implementation of the specific annual operation plans is the responsibility of the Administrative and Technical Secretariat of the Voluntary Partnership Agreement (SETAVA), a unit created to that effect by and hosted within the Honduras Forest Institute (ICF). Given its central role in the implementation of the Agreement, SETAVA should dispose of sufficient resources and capacity to fulfil its functions. Ensuring sufficient capacity at the SETAVA is therefore also featured in the multi-year implementation plan (first specific objective, first strategic area).

The Parties of the VPA, Honduras and the EU, are supported by the African and Latin American VPA Facility (ALA Facility), hosted by the European Forestry Institute (EFI) and funded by the EU, for implementing the VPA and for moving the process forward.

# Description of the service

## Objective of the assignment

The overall objective is to contribute to providing technical and strategic support to SETAVA to ensure that it can fulfil its mission as stipulated by the JIC and by ministerial decree.

The specific objectives are the following:

- SETAVA has sufficient capacity to oversee and coordinate the overall implementation of the Voluntary Partnership Agreement over the duration of the service

- Updated versions of the Joint Implementation Framework (‘Plan Plurinanual de Implementacion’ - PPI) and annual workplans underpinning the implementation of the VPA are adopted at a regular basis by the Joint Implementation Committee (JIC)

- The Parties of the VPA adhere to the PPI, and there is close monitoring and engagement done by the Parties and national decision-makers

- Joint Implementation Committees (JIC) and Technical Committee (‘Comite Tecnico’) meetings, and meetings of the Interinstitutional Secretariat for the Implementation of the FLEGT-VPA (SIIAVA), are held on a regular basis

- The SIIAVA is fully functional and fulfils its mission as it is stipulated in the VPA

- There is increased visibility of the VPA implementation process at the national and international level

- All the key stakeholders are involved in the implementation process and have the capacity to contribute effectively to the implementation process

- There is an in-depth understanding of the VPA implementation process and the requirements of the TLAS at the level of the SETAVA and the SETAVA provides technical assistance to advance on both the implementation of the VPA and the TLAS

- The different projects and programmes implemented in the framework of the VPA are streamlined

- Streamlining the VPA-process and the Forest Partnership workstream is ensured through proactive engagement with key stakeholders.

- Good coordination with IICA is ensured and results in the Bosques Vivos de Honduras programme being fully aligned with the PPI and contributing strategically to the implementation of the VPA.

- The Parties agree to, and the JIC endorses, the Rules of Procedure of the JMRC and the Working Procedures of Arbitration, through active stakeholder engagement.

## Main tasks expected of the service provider

AFD is seeking the services of a service provider to oversee and implement a support package for the SETAVA.

More specifically, the following tasks are expected from the service provider:

- Coordinate and monitor, in close collaboration with the Head of SETAVA, VPA implementation activities with both public institutions and non-governmental actors.

- Identify technical and political bottlenecks and delays during VPA implementation and propose strategic responses to the Head of SETAVA.

- Coordinate with all public institutions involved in the VPA and other non-governmental actors to ensure their full participation in the implementation of the VPA.

- Support the establishment and functioning of the various bodies involved in and coordinating the implementation of the VPA as the Technical Committee and the Interinstitutional Secretariat for the Implementation of the FLEGT VPA (SIIAVA).

- Support the Head of SETAVA in overseeing the different technical workstreams related to the implementation of the Agreement:

  - Prepare the draft updated multi-year implementation plan and specific annual operating plans that guide the VPA implementation process, coordinate stakeholder engagement activities related to those documents, prepare a final draft that can be discussed between the Parties at the (Pre-)JIC and monitor the plans once adopted;

  - Support the review of the legal framework and formulation of recommendations to ensure its compliance with the VPA, and advise on amending existing legal instruments, through engagement with decision-makers and stakeholders;

  - Support the Parties with the development and adoption of the Working Procedures of Arbitration;

  - Take stock of current forestry practices and develop improved procedures related to the forestry sector, including piloting these procedures, engaging stakeholders, and collecting inputs;

  - Conducting a review of the IT systems that are being used at the level of the ICF, collect stakeholder input in those systems, and formulate recommendations on how they can be improved to meet the requirements of the stakeholders;

  - Lead on the organisation of the following governance meetings foreseen in the VPA, and ensure the facilitation, technical backstopping, briefing and drafting the Aide Memoire: Joint Implementation Committee, Interinstitutional Secretariat for the Implementation of the FLEGT-VPA (SIIAVA), Technical Committee, and others as needed;

  - Formulate concept notes and terms of reference for contracting services, studies and others; and

  - Other as needed.

- Collaborate in close coordination with other external actors supporting the implementation of the VPA, including the focal point of the ALA facility and the VPA facilitator.

## Deliverables

The expected deliverables will be received by the EU FLEGT VPA Program Management Unit. They are listed below in chronological order.

Each report will include (i) a narrative part explaining the progress of the project, the activities carried out, the progress made and the difficulties encountered and (ii) a financial part which will detail the expenses incurred and gather all the supporting documents required according to the terms and conditions provided for in the contract. An additional part will be required once the monitoring and evaluation system has been put in place by the EU FLEGT VPA Programme.

Draft reports will be shared with the ALA Facility focal point and the VPA Facilitator to seek their input before submitting them to the Program Management Unit. All reports will be drafted in Spanish and in English.

- D0: Inception report: This report will contain a workplan for the project and include a first draft of the specific annual operating plan for discussion between the Parties. The methodology outlining the share of the activities and of the costs for the intellectual services of each operator and the purchase of working material will be proposed. The inception report will be submitted within a month after the start of the project.

- D1-D4: Regular progress reports: These reports will explain the progress of the project with respect to the activities identified in the workplan and the specific annual operating plan, it will contain the results achieved, the bottlenecks identified and recommendations to overcome those.  Progress reports will incorporate reporting on the utilisation of operational assets procured under the project.  These reports will be submitted at a quarterly basis. They will also contain the work plan of the upcoming quarter. Annual work plans will also be developed. Payment of the contractor will be subject to the submission of the interim reports.

- D5: Final report: A final report will be submitted at the end of the project period to cover all the activities carried out and possible recommendations.

In addition to these reports, the project must provide, before each JIC, a presentation summarizing the various activities carried out by the SETAVA and which will summarize the decisions taken and the deadlines set.

For all project deliverables, if circumstances prevent the service provider from providing what is requested in these ToRs, the reasons will be justified in the interim reports. The last report must contain all the documents listed above.

Payment of the different installments will depend on the validation of the narrative and financial parts of the deliverables listed above.

Regular progress meetings will be held with the Programme Management Unit to follow up on the project, the progress achieved and any challenges encountered.

## Indicative calendar and deadlines

This assignment will have a duration of 15 months.

| N° month | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Deliverables | D0 |  | D1 |  |  | D2 |  |  |
| N° month | M9 | M10 | M11 | M12 | M13 | M14 | M15 |  |
| Deliverables | D3 |  |  | D4 |  |  | D5 |  |

# Services to be provided by the Client

The Service will be awarded by the Client in the form of a single-award framework agreement with a lumpsum part (Coordinator and backstopping) and order forms (for the non-key profiles as well as the funding of equipment and meeting organizations).

The Client will ensure acceptance of the Key Expert by the National Authorities and the EU Delegation.

The Client will provide the necessary address book and introductions so that the contractor has access to as many contacts and information as possible to carry out the assignment

Documents available to the Client (possibly non-exhaustive list) will be provided to the service provider.

# Communication

The deliverables will be produced as part of the EU FLEGT VPA Programme implemented by the Agence Française de Développement (AFD and funded by the European Commission (EC).

The deliverables will present a disclaimer stating that the “publication was produced with the financial support of the European Union. Its contents are the sole responsibility of <name of the author/partner> and do not necessarily reflect the views of the European Union and the French Development Agency.”.

For any external communication within the framework of the EU FLEGT VPA program, the service provider will submit the materials to the Program Management Unit one week in advance in order to obtain approval for the communication.

The service provider will use the templates provided for the reports to be submitted, which can be amended as agreed, and he will mention the Programme and/or use the logo of the Programme on all deliverables and external communication about the Programme.

# Indication of key positions and expected profiles

The successful service provider must as a minimum meet the following criteria:

- Operational presence in Honduras (i.e. have a functional office) will be privileged.

- Solid experience with the implementation of programmes in Honduras funded by international donors (ideally including the EU) in the field of forestry, agroforestry, agriculture, or natural resources management.

- Ample experience in implementing sustainable development programmes with large budgets.

- Candidates with demonstrated experience in working on the above topics with the Government of Honduras and Honduran public institutions will be privileged.

- Candidates with working relations with a wide network of government officials in Honduras will be privileged.

- Experience in working with the private sector and the civil society.

- Ability to mobilise program and project resources quickly and without heavy bureaucratic procedures.

- Capacity to mobilise multidisciplinary team of experts related to targeted subjects on forest related topics.

- Ability to implement the current service using Spanish as operational language.

- Ideally, the service provider also has relevant experience with the EU FLEGT VPA implementation process.

When applying, the service provider will present in its technical proposal the CVs of the key staff and non-key staff of the SETAVA. More specifically, it will present CVs for the following key expert and 2 non-key experts. The non-key experts will be mobilized within the maximum number of days specified in the financial annex.

The service provider may add an additional profile for backstopping, whose CV must be attached to the offer.

Key expert: Coordinator (full time)

Qualifications, skills and professional experience:

- Has a university degree in forestry sciences, law, natural sciences, economics or equivalent through experience

- At least 15 years of experience in working at the policy-level of social-related issues, agriculture, forestry, environment, natural resource management and/or economy

- Knowledge of the Honduran legal framework, particularly related to the forestry sector, land management, and indigenous peoples

- Has a wide network among forest sector stakeholders, including within the government institutions, private sector, and civil society

- Experience in working with a wide range of stakeholders on complex processes in which stakeholders have different interests

- In-depth project and/or programme management experience

- Excellent interpersonal skills and strong communicator

- Team management and leadership skills, and able to manage conflicts

- Able to use computer software packages as Microsoft Word, Excel, Power Point and Outlook, and ideally strong command of project management software.

- Has a wide network among forest sector stakeholders, including within the government institutions, private sector, and civil society.

- Good understanding of the complexity of governance in the Honduran context, covering not only technical issues but also economic, social, cultural, political and legal issues

- In-depth understanding of the VPA process in Honduras

- Working experience in Honduras and excellent understanding of the Honduran political context

- Native Spanish speaker. Knowledge of English is essential to interact with the PMU.

Non-key expert 1: IT expert

Qualifications, skills and professional experience:

- Has a university degree in IT, or equivalent through experience

- At least 10 years of experience in IT system development or deployment

- Experience with the development of mobile and desktop applications, ideally with the development of IT systems focused on i. traceability; and/or ii. legality at the national level.

- Experience with database management and development (back-end)

- Understanding of forest traceability requirements

- Knowledge of operating systems (Windows, macOS or Linux)

- Knowledge of several programming languages (Python, Perl or BASH or equivalent)

- Knowledge of ERP, PLM and CRM environments or equivalent

- Knowledge of virtual server environments (Amazon AWS, Google Cloud Platform, Microsoft Azure or equivalent)

- Knowledge of the principles and methods of the web, but also IT and telecoms risks

- In-depth experience with project management

- Knowledge at maintaining PCs and laptops if needed

- Team spirit, with an ability to work independently

- Excellent interpersonal skills and strong communicator

- Understanding of VPA-processes is preferred

- Native Spanish speaker. Knowledge of English is not essential but will be considered as an advantage

- Passionate about his profession, able to adapt quickly to new technologies and with a constant desire to learn and improve

Non-key expert 2: Forestry expert

Qualifications, skills and professional experience:

- Has a university degree in forestry sciences, natural sciences, environmental science or equivalent through experience

- At least 10 years of experience in the natural resources management, preferably in the forestry sector

- In-depth knowledge of the Honduran forestry sector, and on the political context of the forest sector in relation to forest stakeholders (private sector, local communities, indigenous peoples, civil society)

- Is familiar with the legal context of the forest sector in Honduras

- Has an in-depth understanding of the Honduran code of practise for forestry operations, including sawmilling

- Is familiar with traceability tools and procedures for timber value chains

- Has a thorough understanding of the timber value chains, including of the economics, challenges, and profit margins in the forestry sector

- Strong affinity with the private forestry sector, and has a wide network among forest stakeholders, particularly in the private sector

- Strong environmental sensitivity, sense of responsibility, autonomy

- Team spirit, with an ability to work independently

- Native Spanish speaker. Knowledge of English is not essential but will be considered as an advantage.

# Estimated budget

The maximum budget is 100,000 €, which includes the 20,000 € work plan budget.

The contractor will have available a “work plan budget” to cover costs related to domestic travel, costs of meetings and workshops, and all expenses associated to trainings and coaching for a maximum of 20,000 €. The use of the work plan budget is subject to approval by the EU FLEGT VPA Programme Management Unit.

The contractor must be autonomous in all activities (transport, meetings, workshops, observation missions, ...), both from an operational and financial point of view.

This component was added to the Multi-Partner Contribution Agreement in May 2024 by addendum no. 1. It has been operational since October 2024.