## Financial appendix
|  |  | Name of the society / Leader consortium: | ………..
|  |  | Date: | …/…./…..
NB : This document is contractually binding.
FINANCIAL ANNEX - MOW - technical assistance, including design, supervision, and monitoring for Adwa and Abala Hospital Rehabilitation Projects |  |  |  |  | FINANCIAL OFFER SUMMARY MASTER OF WORK CONTRAT
N° poste | Missions | VAT rate, if applicable | Amount before tax in figures | Amount in figures, all taxes included | Estimated cost of work excluding VAT: | 9450000
Study phase
1 | Preliminary design studies (PDS) |  |  |  | Remuneration coefficient for project management (APS to AOR): |  | 0%
2 | Technical Design Studies (TDS) |  |  |  | Provisionnal remuration for the Master of Work : |  |  | 0
3 | Building/Construction Permit (BP)
4 | Open Consultation Document (OCD)
Subtotal Study phase |  |  | 0 | 0
Construction phase
5 | VISA for Execution and synthesis studies (VISA)
6 | Works Cantract Execution Direction (WED)
7 | Assistance to reception operations (ARO)
8 | As Built Documentation (ABD)
Subtotal Construction phase |  |  | 0 | 0
OVERALL TOTAL FOR THE MISSION |  |  | 0 | 0
Poucentage of the remuneration |  | 0%

## Repartition of the payments
BREAKDOWN OF CONTRACT FOR CONSORTIUM
NB: This table must be completed by the applicant if the project management fee is to be divided between co-contractors or subcontractors, for each project element. If it's a Subcontractor please indicate it.
Basic elements of the mission | % | Amount | Share of co-contractors in case of joint venture
|  |  | Company Name and mission | Company Name and mission | Company Name and mission | Company Name and mission | Company Name and mission | Company Name and mission
|  |  | Co-contractor 1 Authorized representative* | Co-contractor 2 | Co-contractor 3 | Co-contractor 4 | Co-contractor 5 | Co-contractor 6
Preliminary design studies (PDS)
Technical Design Studies (TDS)
Construction/Building Permit (BP)
Open Consulation Document (OCD)
VISA for Execution and synthesis studies (VISA)
Works Cantract Execution Direction (WED)
Assistance to reception operations (ARO)
As Built Documentation (ABD)
OVERALL TOTAL FOR THE MISSION |  | € ex-tax | € ex-tax | € ex-tax | € ex-tax | € ex-tax | € ex-tax | € ex-tax

## Work Program
EXPECTED OUTCOMES AND MAIN ACTIVITIES | OPERATIONAL PLANNING
| Year 1 (2025) | [11 empty] | Year 2 (2026) (by month) | [11 empty] | Year 3 (2027) (by month)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 / ACTIVITIES FROM THE LOGICAL FRAMEWORK
Launch phase (inception phase)
Activity IN.1 - Analyze the context and project documents and adapt the ToC / logical framework, as necessary.
Activity IN.2: Launch TPM tender
Activity IN.3 - Develop the M&E plan and identify indicator reference values (baseline)
Activity IN.4 - Analyze partner capacity and develop a strengthening plan
Activity IN.5 - Engineering Firm (TOR, contract and workplan): The engineering firm is the Master of Work (MoW) and intends to provide technical assistance to the Adwa–Abala hospitals’ rehabilitation during the design, execution, and post-execution phases.
Activity IN.6 Technical Detailed assessment, Design and Planning: The Master of Work is responsible for carrying out detailed preliminary technical assessments of both Adwa and Abala hospitals, covering existing and new buildings, solid and liquid waste management plants, electrical and electromechanical installations, solarization works, and the implementation of One-Stop Centres (OSCs). After submitting the preliminary assessment report and agreeing with stakeholders on the prioritization of critical healthcare facilities for rehabilitation, the Master of Work will conduct detailed technical design studies (TDS) for the prioritized facilities and prepare drawings, bills of quantities (BoQs), engineering cost estimates, open consultation documents (OCDs), as well as progress-tracking checklists and planning tools to monitor implementation.
Activity IN.7- Establish required project capacity: recruit and train staff, procure equipment:
Activity IN.8 - Develop and Sign partnership agreements (MoU) and establish a project steering committee with key stakeholders and partners
Activity IN.9 - Project Kick-off meeting and workshop with key stakeholders: The project was launched in the presence of key stakeholders, representatives from Expertise France (EF), and the French Embassy. Following the launch, donor requirements, project objectives, indicators, and the key project team were introduced to the stakeholders, and their roles and responsibilities were outlined during a steering committee meeting held after the Kick-Off.
Outcome 1. Target health infrastructures are rehabilitated and equipped to enable resumption of essential service provision in Adwa (Tigray region) and Abala (Afar region) hospitals
Activity 1.1 - Rehabilitation of target departments
ABALA HOSPITAL
1.1.1 Electrical - electromechanical installation and improvement (solar power): The major activities under this task includes: a. Upgrading the hospital’s electrical system to ensure reliable power supply. b. Installing solar energy systems and backup batteries to guarantee uninterrupted power for critical medical equipment and essential services. c. Providing and installing distribution boards, electrical fixtures, and internal electromechanical systems according to approved designs
1.1.2 Emergency and triage block expansion: The key activities under this task are: a, Constructing a dedicated emergency block to enhance patient flow, treatment efficiency, and patient safety. b. Equipping the block with necessary medical and life-saving facilities to handle emergency and critical care cases.
1.1.3 Solid Waste management works: The major activities of this task includes: a. Establishing a dedicated solid waste management zone with proper segregation, storage, and disposal facilities. b. Construction of a segregation block, supply and installation of prefabricated diesel incinerator for hazardous waste and glass crusher/compactor (to reduces waste volume, improves safety, and facilitates recycling for more efficient and environmentally friendly waste management) c. Ensuring that waste management practices minimize environmental risks and reduce infectious contamination.
1.1.4 Building improvements: The key activities of this task includes: a. Completing interior finishes, flooring, painting, and ceiling works for each service rooms according to the approved spec. b. Fixing windows and doors, supplying and installing sanitary fixtures including accessible facilities. c. Constructing access roads and improving overall functionality and aesthetics of the hospital buildings
ADWA Hospital
1.1.6 Water supply system improvement The major activities of this task includes: a. Restoring and upgrading water supply infrastructure to ensure reliable, safe water availability across hospital blocks. b. Rehabilitating damaged pipelines, storage tanks, and connections to support uninterrupted service delivery.
1.1.7 New block refurbishment works The major activities of this task includes: a. Finalizing the partially constructed B+G+2-expansion block, including structural repairs, interior finishes, and accessibility enhancements for each service room according to the approved spec. b. Installing necessary partitions, doors, windows, roofing, painting, and other building finishing works according to the approved spec.
1.1.7 New block electrical-electromechanical works The major activities of this task include: a. Completing installation of internal electrical systems, sub-distribution boards, electrical fixtures, data system, and power backups; b. Incorporating solar energy systems and equivalent generator capacity to ensure continuity of operations during outages;
1.1.8 Solid Waste management works The major activities of this task includes: a. Establishing a comprehensive waste management system, including segregation, recycling, and environmentally safe disposal; b. Installing power-driven incinerator, pits, and glass crushers to reduce contamination risk;
1.1.9 Liquid Waste management works (WWTP) The key activities of this task includes: a. Implementing a sustainable wastewater treatment system using friendly technology. b. Constructing dilution pits, grease/oil separators, equalization tanks, and treatment plant facilities for effective management of hospital liquid waste. c. Ensuring treated water meets environmental discharge standards or is suitable for reuse in laundry and cleaning
1.1.10 Building improvements The main work of this will be: a. Completing minor and major refurbishment works to restore functionality, structural integrity, and patient-friendly layouts in all hospital blocks
Activity 1.2 - Re-equipment of target departments
Abala Hospital Abala hospital will be requiped with required medical equipmenet which the Master of Works will provide technical assiatance during installation of the equipment in the disgenated rooms
Adwa Hospital At Adwa hospital will be requiped with required medical equipmenet which the Master of Works will provide technical assiatance during installation of the equipment in the disgenated rooms
Activity 1.3 - Capacity building and coaching sessions
Trainings on rehabilitated departments/sectors
Trainings on medical equipment/others
Outcome 2. One Stop Centres (OSCs) are established at target hospitals to provide comprehensive protection services
Activity 2.1: Set up of hospital-based One Stop Centres (OSCs)
2.1.1 OSC-GBV improvement works Abala The key activities of this task include: a. Review the existing design documents of one stop centre (OSC) obtained from stakeholder, b. Prepare standard building design, BoQs, engineering estimates of OSCs for the two hospitals in consulation with Project and Protection Officer. c. Secure construction/building permint (BP) for bidding purpose
2.1.2 OSC-GBV improvement works Adwa The key activities of this task include: a. Review the existing design documents of one stop centre (OSC) obtained from stakeholder, b. Prepare standard building design, BoQs, engineering estimates of OSCs for the two hospitals in consulation with Project and Protection Officer. c. Secure construction/building permint (BP) for bidding purpose
Activity 2.2: Training of health workers for treatment of GBV survivors
Abala
Adwa
2 / CROSS-CUTTING ACTIVITIES
Monitoring, Evaluation, Accountability and Learning
Monthly monitoring meeting (TL / PM)
Project Steering Reporting (PSR)
Update project compass (quarterly)
Project reviews (annual / bi-annual)
PM monitoring / quality control visit
Learning: lessons learned and knowledge sharing workshops
Donor reports
Annual collection of aggregated indicators (COM, THEMA, etc.)
Mid-term evaluation
Final evaluation
Coordination with partners and stakeholders
Steering Committees (COPIL)
Technical Committees The technical committee is the team of technical experts include representatives/engineers from stakeholders, Epertise France, Assistance master of work, Master of work and will be held at hospitals level to discuss on the key challenges, leassons learnt and put the way forwards throughout the project life span.
External coordination meetings
Periodical monitoring of partnership agreements
Partner capacity strengthening activities
Communications
Development of a communications plan
Development of an overview brochure of the project
EF Website creation
Communications strategy