Mission acting as Master of Works for the rehabilitation of the hospitals of Adwa and Abala, on behalf of EF, within the framework of the implementation of the project “Promoting Conflict-Affected Communities’ Access to Essential Services.”

Technical Specifications (TS)

Representative of the contracting authority

Mr. Jérémie Pellet, General Manager of EF

Subject of the contract

To provide technical assistance, including design, supervision, and monitoring for the Adwa Abala Hospital Rehabilitation Project

Content of the mission elements

The content of the mission elements complies with the provisions of Annex II to the decree of 22 March 2019 specifying the technical modalities for the execution of MoW mission elements entrusted by public project owners to private law providers.

SUMMARY

GLOSSARY	3

GENERAL INFORMATION	4

Project Background	4

TASKS ENTRUSTED TO THE MOW	5

1.	Preliminary Design Studies (PDS)	8

2.	Technical Design Studies (TDS)	8

3.	Construction/Building Permit (BP)	9

4.	Open consultation documents (OCD)	9

4.1 Commercial Documents	10

4.2 Tender Documents	10

4.3 Tender period	11

4.4 Technical screening of offers	11

5.	Visa for Execution and Synthesis Studies (VISA)	11

6.	Works Contract Execution Direction (WED)	11

Technical Management	11

Control the compliance of the achievements	12

Financial management:	12

7.	Assistance to reception operations (ARO)	13

8.	As-Built Documentation (ABD)	13

8.1 Services entrusted and Documents to be submitted to EF	13

Additional Missions entrusted to the MoW	15

# GLOSSARY

ABD:	As-Built Documentation

AMO: Assistant Master of Works

ARO:	Assistance to Reception Operations

BOQ: Bill of Quantities

BP: Building /Construction Permit

EF: Expertise France

GBV: Gender-Based Violence

KPI: Key Performance Indicators

MOH: Ministry of Health

MOW: Master of Works

OCD:	Open Consultation Documents

OSC: One-Stop Centres

PDS:	Preliminary Design Studies

SMC: Scheduling, Management, Coordination

TDS:	Technical Design Studies

VISA: 	Visa for execution and synthesis studies

WED:	Works Execution Direction

# GENERAL INFORMATION

## Project Background

The project “To enhance and sustain conflict-affected communities’ access to health and protection services through the rehabilitation and re-equipment of Abala and Adwa hospitals”. seeks to improve the well-being and resilience of conflict-affected communities in Ethiopia by enhancing the quality and effectiveness of healthcare and protection services. To achieve this, health infrastructures in Adwa (Tigray region) and Abala (Afar region) hospitals will be rehabilitated and equipped to enable the resumption of essential service provision. In addition, One Stop Centres (OSCs) will be established within these hospitals to provide comprehensive protection services that respond to communities’ health, safety, and justice needs, with a particular focus on addressing gender-based violence (GBV).

After two years of intense conflict in northern Ethiopia, healthcare facilities were severely damaged, with the Tigray, Amhara, and Afar regions being particularly affected. Hospitals and clinics were looted, destroyed, or left in disrepair, even as the healthcare needs of conflict-affected populations rose dramatically. This created a critical gap in service delivery.

Abala Hospital in the northern Afar region, which provides primary healthcare services to approximately 85,000 people, and Adwa Hospital in central Tigray, a secondary care facility serving around 1.2 million people, were among the most heavily impacted. By the end of the conflict, both hospitals were operating at less than half their intended capacity due to occupation by armed groups, widespread looting, and the destruction of vital infrastructure. Compounding these challenges were severe damages to water supply systems, inadequate solid and liquid waste management, and the loss of essential medical equipment—all of which further undermined healthcare delivery. Security conditions in the regions remain fragile, and civilians continue to face precarious living situations.

In response, this project aims to restore access to essential health services by rehabilitating and re-equipping both hospitals. This includes infrastructure repairs, the restoration and improvement of water supply systems, solid and liquid waste management systems, and the provision of medical equipment, and capacity-building training for key hospital staff. Additionally, the project seeks to establish One-Stop Centers (OSCs) at both hospitals to ensure that survivors of gender-based violence (GBV) receive comprehensive services aligned with national and international standards. Through these efforts, the initiative aims to support the stabilization of the affected regions and assist vulnerable communities in their recovery and transition toward post-crisis resilience.

# TASKS ENTRUSTED TO THE MOW

This consultation concerns the conclusion of a service contract for the provision of MoW services, Scheduling, Management, Coordination (SMC), and associated services related to the rehabilitation and equipment of Adwa Hospital (Tigray Region) and Abala Hospital (Afar Region), including the set-up of hospital based One-Stop Centers (OSCs) in both facilities. The technical specifications outline the scope of responsibilities for the selected contractor.

The estimated budget for the rehabilitation works outlined in these technical specifications is 9 450 000 € (nine million four hundred fifty thousand euros and zero cents) excluding VAT. The anticipated start date for construction is November 2025. Activities will take place in Ethiopia, specifically in Adwa (approximately 1,100 km north of Addis Ababa) and Abala (approximately 944km north of Addis Ababa).

The operations will be implemented in a firm tranche, following initial studies that will define the priorities and scope of work to be achieved within the available financial envelope.

The firm contracted by EF to deploy MoW at project site must obtain the necessary legal authorizations based the consultant’s nationality. Ethiopian Nationals firms must hold a valid and renewed business license, a legally signed contract agreement, and the consultant’s valid national ID. International firms, must hold an internationally recognized and valid business license, a valid work permit, a legal passport and VISA, and duly signed contract agreement documents.  Any fees to secure legal documents and authorization for the MoW and his/her personnel will be covered by the Firm.

The contractor will be responsible for the following tasks, among others:

| S/N | Item |  | Description |
| --- | --- | --- | --- |
| 1 | PDS | Preliminary Design Studies | Investigation and examination of existing healthcare facilities (feasibility/capacity analysis); Review secondary documents and technical drawings obtained from stakeholders; Review the rapid needs assessments conducted by EF and relevant secondary data (e.g., Ministry of Health, hospital management boards), and assist in prioritizing rehabilitation needs. Conduct comprehensive infrastructure assessments of hospital buildings, water and power supply systems, waste management facilities, and One-Stop Centre construction requirements. Prepare an inception report and validation presentation for EF and the Ministry of Health (MoH). |
| 2 | TDS | Technical Design Studies | Develop architectural and engineering drawings, technical specifications, bills of quantities (BoQs), engineering cost estimates of new and existing building, liquid and solid waste management plants, water supply system and progress monitoring tools for validation by EF. |
| 3 | BP | Building /Construction Permit (BP) | Prepare technical documents, drawings, bill of quantities for prioritized facilities for MoH to review and approve; Ensure all documents are accepted and approved by EF; |
| 4 | OCD | Open Consultation Documents | Preparation of Tender Documents to Award construction contracts, complete tender dossiers (technical, administrative, and design documentation) in accordance with EF’s procurement procedures. Assistance during Tender Period, Support in the screening of offers and Contract award Provide technical support to prospective bidders during the tendering process, including site visits. Analyse technical bids and present results in the form of comparative summary tables to EF. |
| 5 | VISA | Visa for execution and synthesis studies | Review of execution documents to ensure compliance with technical specifications; Preparation of summary statements outlining approvals or observations; Evaluation and approval of proposed materials and equipment; Technical arbitration on material and design choices; Review of execution document tracking tools as part of the Scheduling, Management, and Coordination (SMC) responsibilities (see Section 2.1); Check materials qualities supplied by the contractor/s and provide approval; |
| 6 | WED | Works Execution Direction | Develop and Conduct technical studies during works’ execution, following EF needs and requests. Ensuring contractor submissions are free from detectable errors, omissions, or contradictions; Verify compliance of execution documents and works in progress with approved design documents; Ensure contractors submissions are free from errors, omissions, or contradictions, and address any type of mistakes timely and clearly directly with Contractors; Monitor execution against contractual requirements, including adherence to quality control protocols and national standards; Issue service and work orders, prepare site reports, record observations, and organize weekly project meetings; Conduct weekly coordination calls with EF to review site progress and flag challenges, p providing timely updates on progress, projected timelines, and any significant deviations in scope or cost; Review payment requests submitted by contractors and forward them to EF for final decision and verification of interim payment certificates to confirm alignment with completed work before EF approval; Advise EF on modification requests, contract extensions, or claims raised by contractors; Maintain accurate and up-to-date site records and registration logs; Deliver continuous technical supervision to ensure construction quality and adherence to agreed plans; Regular participation in Technical Committee meetings; Close monitoring and supervision of construction progress as per the agreed work plan; Preparation and distribution of routine progress reports; Establishment and maintenance of comprehensive site documentation and records; Oversight of material compliance, safety protocols, and environmental safeguards; Technical review of proposed subcontractors and scope of subcontracted activities; Evaluation of contractor-issued change orders and recommendations for EF decision-making; Verification that materials and works meet quality standards outlined in the contract; Preparation of inspection and observation reports; Documentation of selected material samples and finishes for EF validation; Use of standardized checklists and reporting formats to ensure works conform to agreed specifications; Verification of interim payment certificates to confirm alignment with completed work before EF approval; Review of additional work proposals and supplementary specifications for EF consideration; Evaluation of contractor claims (technical, material, or cost escalations) in accordance with contractual terms and timelines; Regular participation in Technical Committee meetings; |
| 7 | ARO | Assistance to Reception Operations | Participate in the site handover and provide initial orientation to the selected contractor. |
| 8 | ABD | As-Built Documentation | Prepare a completion report and facilitate the provisional handover process. |

## Preliminary Design Studies (PDS)

Building on the existing needs assessments, EF will engage with key stakeholders (e.g., MoH, hospital management teams) to define infrastructure and equipment priorities aligned with the project’s budget. The MoW will support this process by helping to structure and prioritize needs for discussion. This process will be iterative, involving consultations with the target hospitals and MoH, and will culminate in formal validation by EF.

Assessment of the infrastructures and related works

Once priorities are confirmed in consensus with stakeholders, the MoW will conduct a detailed assessment of the prioritized works. This will include physical observations to the components of the buildings (electrical, sanitary, structural and other facilities) so as to examine the extents of damages, and current status to propose further analysis during project design studies phases.

During the design phase, the MoW will be responsible for conducting all necessary technical surveys and testing (as applicable) to ensure that proposed works comply with relevant national and international standards.  The preliminary design study documents prepared by the MoW will be reviewed by EF and assistance MoW before being submitted to relevant authorities for next level approval. The MoW is expected to address and incorporate all the comments arising at each approval stage without claiming any additional payment for the work.

## Technical Design Studies (TDS)

The MoW will be responsible for preparing a comprehensive set of design documents for the prioritized infrastructures (New and existing) projects, water supply system, liquid and solid waste management plants, and their respective components. These documents are essential for enabling EF to effectively utilize them for both tendering and informed decision-making purposes.

The design package will include, but not be limited to, the following:

- Technical Specifications:  Clearly defined requirements and standards suitable for procurement, ensuring consistency and quality across all works;

- Detailed architectural and engineering drawings: Visual and technical representations of the proposed infrastructure, providing a complete design references;

- Engineering cost estimates: Itemized projections of expected costs to support budgeting and resource allocation;

- Bills of Quantities (BoQs): Detailed breakdowns of materials, labor, and equipment required, supporting transparent procurement and evaluation processes;

- Project Implementation Schedules: Timelines outlining key phases, milestones, and deliverables for effective project execution and monitoring;

- Progress Tracking Checklists:  Tools for monitoring construction progress, quality, and compliance with agreed standards;

- Standard Operating Procedures (SOPs): Operational guidelines to ensure consistency, safety, and sustainability throughout project implementation;

- Once developed, these design documents will be validated jointly by EF and the Ministry of Health (MoH). This validation process will confirm the adequacy, accuracy, and compliance of the documents with technical, regulatory, and strategic requirements.

- The validated design documents will then serve as the official basis for initiating the preparation of bidding documents and for engaging external consulting or construction firms through a transparent procurement process

## Construction/Building Permit (BP)

Construction Permit/ other Commercial authorizations based on Ethiopia National Laws.

As outlined in Section 1 (PDS), the MoW will be responsible for preparing the detailed technical design documents required for obtaining the Building Permit. These will include all categories of drawings (architectural, sanitary, electrical, site plan/plot survey, and structural drawing for new buildings), technical specifications, bills of quantities, and soil test reports for construction of new facilities. And the MoW will submit these documents to EF for review to ensure that all necessary components are included and that they meet the agreed-upon standards.

The MoW prepares all documents within the scope of responsibility required for the building permit application, including the necessary regulatory, which align with the requirements of government of Ethiopia, Ministry of Urban Development and Construction. They also assist EF with the necessary preliminary procedures and consultations to secure the building permit.

The MoW submits the application to the relevant authorities and provides EF with a copy of the submission receipt. This formality constitutes their approval of the building permit application file. The MoW is expected to address and incorporate all the comments arising at each approval stage in the process of securing building permit without claiming any additional payment for the work.

During the building/construction permit application process, if additional mandatory documents beyond the responsibilities of the MoW are required, EF will coordinate with the relevant stakeholders, including Adwa and Abala hospital management, to ensure the provision of all necessary administrative information and documentation. EF will also facilitate the preparation and submission of documents such as the land/lease certificate and easements, including neighbor consent confirming the absence of land disputes or granting legal rights for Adwa/Abala hospitals to use land for the intended purposes.

Furthermore, the MoW is responsible for providing the Environmental and Social Impact Assessment (ESIA) and certification. The firm will facilitate the certification process and submit the necessary documents accordingly to Ethiopian National Laws.

After the building permit is obtained, the MoW shall provide EF with a copy of the permit decision, including all annexes, and shall complete the required on-site public notice posting. The preparation of an amended building permit application, if requested by EF, is included in this scope of work.

The MoW shall submit the following "project" and administrative documents to EF:

- The completed CERFA form

- All documents required by the CERFA form (including the safety report and accessibility report)

## Open consultation documents (OCD)

The MoW shall be responsible for preparing all necessary technical documents, including detailed designs, specifications, and tender/bidding documents. These will serve as the Open Consultation Documents (OCD), forming the basis for the transparent and competitive selection of contractors. To promote accountability and inclusiveness in the process, the MoW will share the prepared documents with the Project Officer and the Assistant MoW (AMO). This collaborative approach will help ensure transparency, facilitate consensus building among stakeholders, and enable the incorporation of expert input to strengthen the quality and reliability of the final documentation.

### 4.1 Commercial Documents

During the preliminary design phase, the MoW carries out physical inspections of the building’s components including electrical, sanitary, structural, and other facilities to assess the extent of damage. Based on these observations, an inception report is prepared to inform stakeholders of the current condition, support prioritization, and recommend areas for the preparation of final set of sales plans.

Before starting the preliminary assessment, the MoW will be provided with the rapid needs assessment report conducted by the project team, oral briefings on the project context and scope, draft unpriced Bills of Quantities (BoQs), and the presentation materials from the kick-off meeting.

Deliverables:

In addition to providing technical guidance and support to the project team, contractors, and stakeholders throughout the project’s span, the MoW is expected to deliver key outputs, including an inception report; design documents (drawings, specifications, Bills of Quantities, and engineering estimates); progress tracking checklists; monthly progress reports; and project Standard Operating Procedure (SOP) documents.

### 4.2 Tender Documents

For the execution of this assistance task, EF prepares the contractual administrative documents (letter of commitment, CCAP, administrative and financial clauses of the construction contract) that make up the Tender Documents.

The MoW is responsible for preparing the consultation of contractors in such a way that they can submit their bids with full understanding, based on a dossier made up of both the administrative and technical documents stipulated in the contract, as well as the documents prepared by the MoW.

Services and Deliverables (Tender Documents):

Preparation of the list of documents required for the consultation

The MoW prepares a list of the written and graphic documents necessary for the awarding of the construction contracts. This exhaustive list includes the documents prepared by EF, the MoW, and other consultants involved in the project, specifying, where applicable, their contractual order of precedence.

Development of the Tender Documents

The Public Tender Documents are prepared based on the procurement strategy selected by EF (separate trade packages, macro-lots, consortium, or general contractor). It reflects the design level chosen by the EF for launching the tender (detailed preliminary design, project design, or execution phase).

Compilation of the technical parts of the Tender Documents

The MoW gathers and compiles the written and graphic technical documents for the Public Tender Documents, based on studies approved by the client. These documents include the technical specifications, plans, and other written materials produced by the MoW, aligned with the design phase selected by the client for the consultation, as well as any additional documents provided by the client or other project consultants.

The MoW ensures the consistency of the entire dossier before it is sent to the construction companies:

Based on the MoW' proposal, the client defines the required technical and financial qualifications for contractors, as well as the content of their offers.

The MoW proposes and defines the scope for accepting variant bids.

The MoW provides the client with blank templates for the breakdown of the lump-sum price. When the MoW is responsible for the execution studies, they complete the breakdown form with quantities.

The MoW will be responsible for preparing the technical components of the tender dossier for the execution of rehabilitation works, in accordance with the French Public Procurement Code (2018) and its amendments. This includes:

- Drafting the Detailed Technical Specifications Document to establish construction needs and requirements;

- Preparing the Administrative Specifications Document;

- Developing the Consultation Regulations (Tender Rules), incorporating evaluation criteria provided by EF;

- Producing engineering estimates and Bills of Quantities based on prevailing local market rates

The contract will be issued on a global lump-sum basis, non-adjustable and non-revisable. Variants will be permitted within the limit of the tolerance margin established in the contract. EF will oversee the public tender launch and manage the shortlisting of eligible companies.

### 4.3 Tender period

During the tender period, the MoW is responsible for responding to technical queries from bidders within 48 hours in coordination with EF. All responses must be issued in writing and shared with all bidders. As site visits can take place for bidders to fully understand the scope of works, the MoW will support these visits by facilitating access and providing technical clarifications. EF will coordinate with the hospitals to secure authorization for site access. Costs for site visit will be bared by every bidder.

### 4.4 Technical screening of offers

In collaboration with EF, the MoW will participate in the bidders’ technical proposals evaluation by allocating points in accordance with the distribution established in the tenders’ terms of reference (ToR).  Any allocation or withdrawal of points must be clearly justified in the evaluations. A summary table model for tenders’ technical proposals evaluation will be provided. The technical examination of tenders will be carried out with the utmost confidentiality to the applicants until the contracts are signed and the works started. The tenders’ financial offer and final bid evaluation decision will be conducted by EF.

At the end of this first round, EF reserves the right to negotiate with all or some of the candidates to obtain the best possible offer. In this context, a delegation of EF will go on site to meet the selected bidders in order to negotiate the offers. The incumbent of this contract will accompany the delegation during these sessions.

## Visa for Execution and Synthesis Studies (VISA)

The MoW will verify that contractor-prepared execution documents comply with the approved project deliverables and will issue a “VISA” as confirmation. This review ensures adherence to the project specifications and identifies any anomalies detectable by a qualified professional. However, it does not replace full validation of the contractors' documents, and responsibility for execution remains with the contractor.

Included Services:

- Review of execution documents to ensure compliance with technical specifications;

- Preparation of summary statements outlining approvals or observations;

- Evaluation and approval of proposed materials and equipment;

- Technical arbitration on material and design choices;

- Review of execution document tracking tools;

- Oversight of material selection tables to ensure alignment with project requirements;

## Works Contract Execution Direction (WED)

The Works Contract Execution Direction (WED) ensures that all construction activities are implemented in alignment with the detailed assessments, technical designs, and contractual obligations. The MoW will be responsible for:

### Technical Management

- Verifying that execution documents and works in progress comply with approved design documents;

- Develop and Conduct technical studies during works’ execution, following EF needs and requests;

- Ensuring contractor submissions are free from detectable errors, omissions, or contradictions;

- Monitoring execution against the contractual requirements, including adherence to quality control protocols;

- Participation of the project management team in site meetings.

- Issuing service orders, preparing site reports, recording observations, and organizing weekly project meetings;

- Conducting weekly coordination calls with EF (EF) to review site progress and flag challenges;

- Providing timely updates on progress, projected timelines, and any significant deviations in scope or cost;

- Reviewing payment requests submitted by contractors and forwarding them to EF for final decision;

- Advising EF on modification requests, contract extensions, or claims raised by contractors;

- Maintaining accurate and up-to-date site records and registration logs;

- Delivering continuous technical supervision to ensure construction quality and adherence to agreed plans.

- Regular participation in Technical Committee meetings;

- Close monitoring and supervision of construction progress as per the agreed work plan;

- Preparation and distribution of routine progress reports;

- Establishment and maintenance of comprehensive site documentation and records;

- Oversight of material compliance, safety protocols, and environmental safeguards;

- Technical review of proposed subcontractors and scope of subcontracted activities.

- Manage oversight of administrative and contractual aspects, ensuring compliance with all contractual conditions, permits, and insurance policies, reviewing and endorsing payment certificates before EF validation.

- Coordinate with EF project team by facilitating clear communication with EF, engineers, contractors, and local site supervisors, attending, and participating in site meetings regularly.

- Communicate potential changes to scope, reviewing and advising on any proposed modifications or change orders in coordination with EF.

- Conduct regular quality monitoring and reporting to EF project team, verifying that quality assurance is implemented by site supervision teams, conducting regular site visits or request technical reports to assess project activity progress.

- Conduct regular risk and incident management, identify risks before they occur and responding promptly to any issues that arise (particularly those that may pose financial, reputational, or safety concerns) and communicating these issues to EF project staff in a timely manner.

- Observe safety and environmental compliance, confirming adherence to occupational health and safety protocols and environmental requirements, responding swiftly to incidents and communicating incidents to EF project team.

- Prepare for handover, ensuring that final commissioning, documentation, and operational testing are incorporated into the timeline and budget.

### Control the compliance of the achievements

- Evaluation of contractor-issued change orders and recommendations for EF decision-making;

- Verification that materials and works meet quality standards outlined in the contract;

- Preparation of inspection and observation reports;

- Documentation of selected material samples and finishes for EF validation;

- Use of standardized checklists and reporting formats to ensure works conform to agreed specifications.

### Financial management:

- Verification of interim payment certificates to confirm alignment with completed work before EF approval;

- Review of additional work proposals and supplementary specifications for EF consideration;

- Evaluation of contractor claims (technical, material, or cost escalations) in accordance with contractual terms and timelines.

## Assistance to reception operations (ARO)

The assistance provided to EF during the acceptance of the operations as well as during the warranty period of perfect completion of works aims to:

- To ensure the follow-up of the reservations formulated upon receipt of the work until their commencements;

- Helping with documentations and formal handover procedures;

- Identify any defects or unfinished works;

- Checking that all works conforms to the contract and designs;

- To organize the operations prior to accepting the work;

The proofreading and work necessary until the validation of the file of executed works required for the operation of the work based on the designs in accordance with the execution submitted by the contractor, monitoring schedules as well as operating manuals and maintenance requirements of the equipment suppliers implemented.

## As-Built Documentation (ABD)

### 8.1 Services entrusted and Documents to be submitted to EF

At pre-Acceptance Operations, the MoW will:

- Organize a provisional handover by coordinating and scheduling a site visit or meeting with relevant stakeholders including the contractor, architect, technical advisors, and EF project leads;

- Verify completion of works by assessing whether the works are substantially complete in line with contractual requirements, technical documentation, and construction drawings;

- Conduct site inspections with technical team of experts, inspecting all aspects of the work (e.g., structure, finishes, systems, etc.), identifying defects, non-conformities, or unfinished works;

- Compile a snag list (punch list), being a list of all works that require correction or completion prior to final acceptance. Validate the list with the contractor for follow-up;

- Verify documentation, submitting all required materials (e.g., as-built drawings, technical manuals, test and inspection reports, warranties and guarantees, maintenance instructions, etc.);

- Conduct compliance checks, by cconfirming that all works are in compliance with applicable legal, safety, environmental, and building regulations;

- Determine readiness for acceptance, deciding if the project can proceed to the next acceptance stage, or whether additional corrective work is needed;

- Document observations, recording all findings, action points, and agreed timelines in a formal report to EF;

- Coordinate with stakeholders, communicating with end-users, public authorities and/or beneficiaries (if applicable and agreed upon prior by the EF Project Manager) regarding readiness for commissioning or occupation;

- Facilitate final acceptance and handover, organizing and oversee the official handover, confirming the project meets contractual, regulatory, and quality standards (e.g., compliance certificates, permits); Sign formal acceptance documentation (e.g., acceptance form, certificates) to trigger the release of retention funds or guarantees pro-core.

- Ensure delivery of all critical close-out documents (e.g., as-built drawings, O&M manuals, warranties and guarantees, commissioning & testing reports, compliance certificates, health & safety file, etc.) to relevant stakeholders and archive these documents in an organized, accessible system for future reference

- Ensure closure of punch-out list, verifying that all defects and outstanding items are resolved and documented within agreed timelines.

- Engage in commissioning of systems and facilitating training of relevant stakeholders and beneficiaries, ensuring full system commissioning (e.g., HVAC, electrical, security) is carried out per design and operational requirements. Organize training, in close collaboration with EF project team, for facility management and end-users to ensure proper handover of operation & maintenance responsibilities

- Enforce warranty obligations, assuming responsibility for defects identified during the warranty period, the MoW must notify and oversee resolution. Contractors/design consultants may also have roles during warranty support and defect resolution.

- Track key performance indicators (KPIs) to ensure the project delivers intended value and functionality (e.g., efficiency, user satisfaction);

- Conduct periodic reviews (e.g., 3, 6, 12 months post-handover) to assess project outcomes and any early issues;

- Prepare and archive a project closure report that includes achievements, financial finalization, lessons learned, and improvement recommendations. Formally release remaining resources and teams.

After the execution period of the work/s, the MoW will:

- Facilitate final acceptance and handover, organizing and oversee the official handover, confirming the project meets contractual, regulatory, and quality standards (e.g., compliance certificates, permits); Sign formal acceptance documentation (e.g., acceptance form, certificates) to trigger the release of retention funds or guarantees pro-core.

- Ensure delivery of all critical close-out documents (e.g., as-built drawings, O&M manuals, warranties and guarantees, commissioning & testing reports, compliance certificates, health & safety file, etc.) to relevant stakeholders and archive these documents in an organized, accessible system for future reference

- Ensure closure of punch-out list, verifying that all defects and outstanding items are resolved and documented within agreed timelines.

- Engage in commissioning of systems and facilitating training of relevant stakeholders and beneficiaries, ensuring full system commissioning (e.g., HVAC, electrical, security) is carried out per design and operational requirements. Organize training, in close collaboration with EF project team, for facility management and end-users to ensure proper handover of operation & maintenance responsibilities

- Enforce warranty obligations, assuming responsibility for defects identified during the warranty period, the MoW must notify and oversee resolution. Contractors/design consultants may also have roles during warranty support and defect resolution.

- Track key performance indicators (KPIs) to ensure the project delivers intended value and functionality (e.g., efficiency, user satisfaction). Conduct periodic reviews (e.g., 3, 6, 12 months post-handover) to assess project outcomes and any early issues.

- Prepare and archive a project closure report that includes achievements, financial finalization, lessons learned, and improvement recommendations. Formally release remaining resources and team;

- Post-Execution Responsibilities

- Once the acceptance operations are completed, the MoW will be responsible for:

- Ensure formal project closeout sign-off on all deliverables and completion certificates. Trigger release of financial holdbacks once all requirements are satisfied.

- Confirm the transfer of a complete and organized package of final documents (e.g., compliance certificates, asset registers, commissioning and system test reports, O&M instructions, warranty and defect liability documentation, etc.) and asset delivery.

- Verify all systems are functioning and operational before handover to project beneficiaries. Provide on-site training for designated personnel responsible for upkeep and routine maintenance.

- Finalize all outstanding corrective works and submit documentation confirming their resolution according to the punch list.

- Follow up on all oversight activities related to warranty compliance. Set out response timelines and escalation procedures to address unresolved issues during the defect liability period.

- Organize a final debriefing session with EF and key stakeholders for knowledge transfer and lessons learned. Prepare a project closure summary highlighting successes, implementation challenges, and strategic takeaways.

# Additional Missions entrusted to the MoW

The MoW will carry out additional missions such participation in technical and steering committee meetings collaborate with stakeholders in scheduling site visits and monitoring. Besides, MoW will reflect on work progress, challenges and the way forwards. The MoW will also provide technical assistance to the suppliers upon installation of liquid waste planets and medical equipment in healthcare facilities.

In addition, based on the findings outlined in the Rapid Need Assessments document and subsequent site observations, the MoW shall conduct detail inspection to the prioritized health-care facilities. It will also analyse the ancillary components of these facilities in order to provide EF and concerned stakeholders with recommendations for further prioritization, informed decision-making, and detailed infrastructure assessment and inspections including but not limited to:

- Structural components of the prioritized health-care facilities (foundations, load-bearing members, joint and connections, superstructure elements and etc.);

- Surface and finishes of the selected facilities (pavement and walkways, floors, walls and ceilings, protective coats and painting works etc.);

- Utilities and services systems of the prioritized health-care facilities (water supply systems, sewerage and drainage systems, electrical systems, mechanical and HAVC system, communication and safety system etc.);

- Environmental and soil works in the proposed health-care compound (soil and ground stability, drainage and storm water management, flood protection and vegetation management etc.);

- Furthermore, the MoW shall carryout detail Project studies for new construction activities as outlined under section 3, and prepare technical documents for tendering and project monitoring.