TERMS OF REFERENCE AND TECHNICAL SPECIFICATIONS

EU4Innovation East – Technical Assistance for Managers

- General information

| # Assignment name | Capacity-Building and EU Collaboration for Managers of Entrepreneurial Support Programs |
| --- | --- |
| # Beneficiary | Expertise France – EU4Innovation East project |
| # Country | Republic of Moldova |
| # Assignment Duration | 18 months (tentatively December 2025 – May 2027) |

- Context and justification of the need

The EU4Innovation East is a regional project aiming at enhancing the competitiveness of the startup ecosystem within 5 countries of the Eastern Partnership (EaP): Armenia, Azerbaijan, Georgia, the Republic of Moldova and Ukraine. EU4Innovation East focuses on strengthening the performance of the local ecosystems to provide support to startups, improving access to funding and markets, and delivering targeted support to Ukraine’s tech ecosystem. The initiative combines co-financing, skills training, regulatory guidance, and gender-inclusive measures to promote long-term, sustainable innovation across the region.

The EU4Innovation East project is funded by the European Union, co-funded by the French government and implemented by Expertise France.

| Title: | Initiative “EU4Innovation East” – Support to Digital Innovation in the Eastern Partnership region |
| --- | --- |
| Geographic scope: | Multi-country Eastern Partner: Armenia, Azerbaijan, Georgia, Republic of Moldova and Ukraine |
| Duration: | • Duration: 54 months, i.e. 4.5 years (04/2024 - 10/2028) |
| Financed by: | • EU Commission: 20.000.000,00€ • France: 2.120.000,00€, earmarked for Ukraine |
| Implementing Agency: | Expertise France (EF) |
| Overall objective: | Strengthen the competitiveness and maturity of the EaP startup ecosystem |
| Specific Objectives: | SO1: Enhance early-stage funding access for EaP startups, especially those led or co-founded by women, by creating a new funding mechanism and improving incubation programs, including technology transfer initiatives. SO2: Foster innovation development in EaP ecosystems by structuring and improving the business environment. SO3: Amplify the visibility of EaP startups and strengthen connections with European investors, fostering both funding acquisition, market access, and increased local interest in the entrepreneurial journey. |
| Pillars description: | Pillar 1 - Early-stage funding Pillar 2 - Backing high added-value segments and high-performance incubation Pillar 3 - Strengthening Community ties Pillar 4 - International Spotlight for EaP Startups Integrating European emblematic events |

Local context

Moldova’s ecosystem of incubation, pre-acceleration, and acceleration programs is expanding, reflecting growing interest in entrepreneurship and innovation. However, its long-term impact remains constrained by several systemic challenges.

Institutional capacity is limited, with many program managers lacking exposure to international standards in startup support. Existing models are often fragmented or self-developed and simplistic, and there is limited access to professional training opportunities. Internal organization within support institutions tends to rely heavily on key personnel rather than robust processes, standardized services, or consistent training curricula and materials. This results in inefficiencies and limits scalability.

Moreover, the ecosystem suffers from weak funding opportunities, which restrict the development and sustainability of support programs. The absence of international players—such as global accelerators, venture capital firms, and experienced mentors—further isolates Moldovan initiatives from broader innovation networks and best practices.

There is also little systematic collaboration with European counterparts, who bring decades of experience in service design, investment readiness, and startup scaling. Without structured partnerships and knowledge exchange, Moldovan ecosystem actors struggle to evolve and compete regionally.

Key Challenges Identified:

- Limited professional development for program managers in designing, delivering, and evaluating startup support services.

- Inconsistent skills transfer, with no standardized curriculum to ensure continuity across organizations and timeframes.

- Inefficient internal organization, overly reliant on individual staff rather than institutionalized processes and materials.

- Weak funding landscape and lack of international engagement, limiting exposure and access to global innovation practices.

Proposed Response

To address these gaps, the EU4Innovation East project proposes two interlinked activities aimed at strengthening Moldova’s startup support infrastructure:

- Capacity-Building Program for Ecosystem Managers
A series of three intensive training rounds to be delivered during the calendar year 2026. Each round will train up to 15 managers and staff from Moldovan startup support organizations. The training program will focus on designing and delivering startup support services that respond to the specific needs of the Moldovan ecosystem, with the overarching goal of increasing the number and success rate of startups. It will also support participating organizations in strategically positioning themselves within the ecosystem, including the development of clear differentiation strategies to define their unique value propositions and roles.

- International Collaboration and Mentorship Framework Establishment

At least five structured collaborations are expected to be established between Moldovan support organizations and counterparts from the European Union (EU), Eastern Partnership (EaP) countries, and countries on the EU accession path. These partnerships will run from January 2026 to July 2027 and will include multiple mentorship and exchange iterations. The goal is to embed international practices into local service delivery, strengthen institutional capacity, and foster long-term relationships that support the evolution of Moldova’s startup ecosystem.

Together, these activities are expected to elevate the quality, credibility, and sustainability of Moldova’s startup support infrastructure, preparing it for smooth integration into the EU and global startup ecosystem.

- Objectives of the assignment

This TOR outlines a consulting assignment for an international organisation aimed at strengthening the institutional capacity and service quality of Moldovan tech entrepreneurial support organisations. This will be achieved through structured training and strategic international collaboration.

3.1. General objective

The overall objective of this assignment is to strengthen the institutional capacity and service quality of Moldovan entrepreneurial support organisations—particularly those involved in incubation, pre-acceleration, and acceleration—by equipping their managers with advanced skills and fostering long-term collaboration with international peers. All activities will be informed by a targeted needs assessment, ensuring that interventions are tailored to the specific gaps and priorities of the ecosystem and aligned with the principles of the EU Startup Nations Standards (SNS), which promote high-quality, inclusive, and innovation-driven startup support environments across Europe.

3.2. Specific objectives

The assignment aims to achieve the following specific objectives:

- Identify and address capacity gaps in Moldovan startup support organisations through a structured needs assessment.

- Equip managers and staff with practical competencies in service design, organisational strategy, project management, fundraising, and mentorship network development.

- Deliver three rounds of tailored training programs across the ecosystem.

- Facilitate at least five international mentorship collaborations to promote knowledge exchange and long-term institutional learning.

- Support the integration of international practices and sustainable service models aligned with the EU Startup Nations Standards and adapted to Moldova’s local context.

- Description of the assignment

4.1 Planned activities and tasks

To achieve the above objectives, the consultant will be responsible for the following tasks:

    - Training Program Design and Delivery

In order to design the training program, the selected entity should conduct a targeted needs review – a  focused assessment to identify the most relevant gaps, priorities, and opportunities within Moldova’s incubation, pre-acceleration, and acceleration programs. The review should concentrate on key areas such as service delivery, organisational structure, and strategic positioning, providing actionable insights to inform the design of the training curriculum and collaboration activities.

Based on the findings of the needs assessment, the consultant should design the curriculum and propose the most suitable training format—either by repeating the same course three times with different participant groups, or by engaging the same cohort in a phased training program that builds progressively on earlier modules. The proposed approach should reflect the diversity of organisational maturity levels and learning needs across the ecosystem.

Further on, the selected entity will develop and deliver three rounds of training (12-15 participants per round) tailored to the identified needs. Training topics will include:

- Service design using methodologies such as design thinking or human-centred design

- Organisational strategy and differentiation

- Project management and internal process optimisation

- Fundraising strategies and access to finance

- Development and growth of mentorship networks

- Selection and onboarding of mentors and trainers.

It is preferred that the training is delivered in person, each round consisting of a 2–3 day intensive program, designed to be highly interactive and practice-oriented. The sessions should incorporate a mix of case studies, role-playing exercises, group work, and real-world examples to ensure experiential learning. Active involvement of EU experts is highly desirable, either through direct facilitation or guest contributions, to provide insights aligned with EU Startup Nations Standards and international best practices.

The consultant should ensure that the training format encourages peer learning, reflection, and immediate application of concepts, while remaining adaptable to the specific needs identified during the initial assessment.

    - International Collaboration Facilitation and Integration of International Practices

The consultant is expected to facilitate at least five structured international mentorship collaborations aimed at strengthening the institutional capacity of Moldovan entrepreneurial support organisations. These collaborations may take the form of:

- Direct partnerships between Moldovan organisations and the consulting entity executing this assignment.

- Collaborations initiated and supported by the consultant with relevant organisations from the EU, Eastern Partnership countries, or countries on the EU accession path.

- Support for the creation of local chapters or representations of reputable international organisations, where appropriate, to foster long-term institutional alignment and access to global networks.

These partnerships should promote knowledge exchange, co-development of services, and long-term institutional learning, tailored to the strategic positioning and maturity of each participating organisation.

In parallel, the consultant will support Moldovan organisations in embedding international standards and sustainable service models, ensuring alignment with the EU Startup Nations Standards (SNS). This includes promoting practices that enhance transparency, inclusivity, scalability, and innovation-driven service delivery, while remaining adaptable to Moldova’s local context and ecosystem dynamics.

4.2. Anticipated deliverables

| Deliverable | Tentative Timeline |
| --- | --- |
| Targeted Needs Review Report | Month 1-2 |
| Training Curriculum and Materials | Month 3 |
| Delivery of Training Round 1 | Months 3-4 |
| Delivery of Training Round 2 | Month 6-8 |
| Delivery of Training Round 3 | Month 10-12 |
| Establishment of at least five international mentorship collaborations | Months 6-12 |
| Progress Reports on collaboration activities established | Months 12 and 15 |
| Final Report summarising all activities, results, and recommendations | Month 18 |

4.3. Coordination

The service provider will closely coordinate with EU4Innovation East, Startup Moldova, and local startup support organisations. EU or EaP partners will be selected through a transparent competitive process.

- Place, duration and terms of performance

The assignment shall be implemented primarily in the Republic of Moldova, with activities concentrated in Chișinău. Other relevant regional hubs might be included (Balti, Cahul), as identified during the Targeted Needs Review. The international organisation selected for this assignment is expected to ensure a local presence throughout the implementation period, facilitating direct engagement with stakeholders, beneficiaries, and institutional partners.

To maximize impact and foster meaningful capacity development, all training sessions are preferably to be delivered in person. This modality is intended to enhance peer-to-peer learning, foster trust-building, and allow for tailored, context-sensitive facilitation. Where necessary, hybrid or remote formats may be considered for mentorship activities or follow-up engagements, particularly in cases involving international experts.

The duration of the assignment is eighteen (18) months from the date of contract signature. The implementation will follow a phased approach aligned with the following indicative timeline:

- Months 1–2: Conduct a comprehensive Targeted Needs Review to identify priority areas and stakeholder expectations.

- Month 3: Develop and validate the Training Curriculum and Materials based on findings from the review.

- Months 3–4: Deliver the first round of in-person training sessions.

- Months 6–8: Deliver the second round of training, incorporating feedback and evolving needs.

- Months 10–12: Deliver the third and final round of training, with a focus on consolidation and sustainability.

- Months 6–12: Facilitate the establishment of at least five international mentorship collaborations, leveraging diaspora expertise and global networks.

- Months 12 and 15: Submit Progress Reports detailing the status and outcomes of mentorship collaborations and training activities.

- Month 18: Submit a Final Report summarising all activities, results achieved, lessons learned, and strategic recommendations for future programming.

The international organisation is expected to maintain flexibility in scheduling and location planning to accommodate local dynamics and ensure inclusive participation across sectors and regions.

- Qualifications and experience

The assignment is open to international organisations, consortia, or networks with a demonstrated track record in managing complex projects related to innovation and early-stage funding. Eligible entities must show proven experience in supporting startup development and ecosystem growth, with the capacity to deploy international experts to ensure a well-rounded and contextually relevant approach. While prior implementation of similar assignments is considered an asset, the primary emphasis is placed on the organisation’s ability to design and execute effective, needs-based interventions tailored to the local context and aligned with international best practices.

Essential Qualifications:

- Proven track record in implementing programs that support startup development, including incubation, acceleration, or entrepreneurial capacity-building initiatives.

- Experience in conducting needs-based assessments and translating findings into actionable training and support programs.

- Use of methodologies that have proven successful through previous iterations, particularly in training, mentoring, and organisational development.

- Demonstrated ability to mobilise qualified trainers, mentors, and international experts, especially from the EU, Eastern Partnership countries, or countries on the EU accession path.

Preferred Qualifications:

- Experience working in Eastern Europe or similar emerging ecosystems, with an understanding of local institutional and market dynamics.

- Capacity to support new partnerships or facilitate the creation of local chapters of reputable international organisations or networks.

- Ability to deliver interactive, in-person training using experiential learning methods (e.g., case studies, role plays, group work).

- Working proficiency in English is required; knowledge of Romanian or Russian is considered an asset.

Additionally, the organization must exhibit robust project management capabilities, including a clear methodology for coordinating the activities of experts, ensuring seamless integration of international insights with local realities to achieve sustainable and impactful results.

- Application documents

The application documents as well as all correspondence and documents relating to this assignment must be written in English.

In support of their offer, candidates must submit the following documents:

- A proof of legal registration (certificate of registration).

- The attached application form

- The attached GDPR compliance verification form, used to verify that the bidder has implemented appropriate technical and organisational measures such that data processing complies with relevant data protection laws and regulations (GDPR and French data protection legislation), thereby guaranteeing the rights of data subjects;

- The draft contract, including the candidate's financial offer, duly completed, dated and signed;

- A technical offer comprising:

- A description of the applicant organization, including its relevant credentials, track record, and previous experience that demonstrate its suitability for the assignment.

- Curriculum vitae (CVs) of the expert(s) proposed for the implementation of the activities, highlighting their qualifications, thematic expertise, experience in angel investment and prior relevant engagements.

- A detailed financial offer, including:

  - A breakdown of costs presented as a unit price schedule.

  - The schedule should indicate the price per man-day, provide an estimate of the total number of days required to complete the assignment, and cover all services to be delivered under the contract.

  - The financial offer must also include all associated costs, such as travel, accommodation, venue rental, catering, materials, and any other expenses necessary for the successful implementation of the assignment.

- A declaration of honour confirming compliance with exclusion criteria and absence of conflict of interest; and the Third Party Identification Sheet.

The documents requested above are mandatory. If missing, the tender submitted will not be compliant and will therefore be rejected.

Electronic submission via the French government procurement platform at https://www.marches-publics.gouv.fr is mandatory. Any submission via other means will be rejected.

Deadline for submission: November 5, 2025; COB Paris time.

The period of validity of the offers submitted is fixed at 90 calendar days from the deadline for submission of tenders.

- Evaluation and selection

Expertise France will first check the eligibility of the applications and their ability to provide the service. Subsequently, it will evaluate the offers according to the following criteria:

Criterion 1: Technical offer

Each technically conforming offer will be evaluated based on the following criteria, with a total of 70 points. The Technical Score (TS) will be calculated by summing the points awarded for each sub-criterion.

| Technical offer sub-criteria | Max pts. |
| --- | --- |
| 1. Understanding of the Assignment and Context | 20 |
| 2. Proposed Approach and Methodology | 15 |
| 3. Organisational and Team Experience | 20 |
| 4. Capacity to Mobilise Trainers, Mentors, and International Partners | 15 |

Minimum Technical Score to Qualify

Only bids scoring 50 points or more in the technical evaluation will proceed to financial assessment.

Criterion 2: Price of the services

The Financial Score (FS), with a maximum of 30 points, will be calculated to allow a comparative assessment of the financial offers submitted by all candidates with conforming bids. The lowest-priced bid will receive the full 30 points, while other bids will be scored proportionally using the following formula:

FS = Lowest Price / Bid Price × 30

Total score will be calculated as a sum of Technical and Financial scores.

- Negotiations

Following the initial analysis of bids by the Evaluation Committee, the contracting authority may enter into negotiations with all or selected bidders, ensuring equal treatment throughout. The contracting authority, however, reserves the right to award the contract without engaging in negotiations.

- Additional information

In order to access the tender consultation space, bidders must connect to the French government procurement platform at:  https://www.marches-publics.gouv.fr