TECHNICAL SPECIFICATIONS – TERMS OF REFERENCE INTELLECTUAL SERVICES

Contract n°ISR-2025-0390

French Development Agency

5 Roland Barthes

75598 Paris Cedex 12 - RCS PARIS B 775 665 599

Telephone: + 33 (0)1 53 44 31 31

Concerning the service

“Conducting a survey and preparing a report on sports practice, sports consumption, and sports-related employment among African households.”

SUMMARY

ARTICLE 1.	Presentation of the Prescriber Service	3

ARTICLE 2.	Subject of the contract	3

ARTICLE 3.	Context and objectives of the mission	3

ARTICLE 4.	Expected benefit	4

ARTICLE 5.	Deliverables expected	6

ARTICLE 6.	Execution modality	7

6.1	Expected methodology	7

6.2	Special requirement for implementation/ Conditions of execution	7

6.3	Execution schedule	7

ARTICLE 7.	Expected skills of the Service Provider	8

ARTICLE 8.	Means made available to the Service Provider	8

Annexes

# Presentation of the Prescriber Service

Research and innovation are essential pillars of the AFD Group’s overall strategy.

The Innovation, Strategy, and Research Directorate (ISR) brings together analytical, research design, management, and evaluation capacities, as well as expertise in knowledge dissemination and valorization. This enables it to fulfill three main missions:

- Strategic, operational, and forward-looking analysis, supporting developing countries in their economic, ecological, and social transitions, and complementing the AFD Group’s financing operations. In a “think-and-do tank” approach, applied research is carried out by multidisciplinary teams in collaboration with academic partners from both the Global South and North to co-design development pathways and identify the most context-appropriate public policies to achieve them.

- Catalyst for transformation, through support to high-impact initiatives, exploration of emerging subjects and technological frontiers of sustainable development, and the identification of innovative solutions to contemporary challenges.

- Knowledge creation and dissemination platform, promoting collective intelligence through the production, sharing, and debate of research and evaluation outputs. This includes training and capacity-building programs, the publication and dissemination of scientific and evaluation materials, and the organization of events bridging academia and policymaking.

# Subject of the contract

This contract concerns the conduct of a survey among African households on sports practice, sports consumption, and sports-related employment, as well as the preparation of an analytical report based on the survey findings.

The data and analysis will inform two chapters of a forthcoming report on Sport and Development in Africa, jointly produced by the Agence Française de Développement (AFD) and the World Bank Group. The report will be published and showcased alongside the Dakar 2026 Youth Olympic Games (October 31 – November 13, 2026).

# Context and objectives of the mission

Context

Sport is a significant driver of economic, social, and civic development. Recognized in the United Nations 2030 Agenda for Sustainable Development, sport contributes to several Sustainable Development Goals (SDGs) through its benefits to physical and mental health, education, and employability. Yet, sport’s potential in Africa remains underexploited: the sports industry accounts for less than 1% of the continent’s GDP, compared to roughly 2% globally.

Since 2019, the AFD Group has implemented a Sport and Development Strategy aimed at leveraging sport as a vehicle for social cohesion and SDG achievement across its partner countries. Over €230 million have since been invested in more than 200 projects across 50 countries—primarily in Africa—around four key pillars: i) financing of local sports infrastructure (urban and school-based); ii) support to public sports policies; iii) capacity-building and professionalization of the sports sector; and iv) support for social innovation led by civil society actors.

AFD has also positioned itself as a key convenor of sports and development ecosystems by: i) partnering with international sports organizations (FIFA, NBA, BAL, Paris 2024, IOC), French federations, and athletes engaged in development causes; ii) launching the Sport in Common platform, linking funders with project holders; iii) initiating, within Finance in Common, a coalition mobilizing public development banks to scale investment in the sports sector.

At the request of the French Republic President, AFD co-organized with the IOC the first Sport for Sustainable Development Summit, held on the eve of the Paris 2024 Olympic and Paralympic Games, gathering nearly 500 participants (including 55 heads of state or government, leaders of international organizations, sports representatives, civil society, and private sector actors). In this context, AFD pledged to invest €500 million in the sports sector by 2030 and to publish, with the World Bank Group, a joint report on Sport and Development in Africa to be released alongside the Dakar 2026 Youth Olympic Games (October 31 to November 13, 2026).

The report will follow a scientific approach to assess the current state of the sports sector, identify main barriers and challenges to its growth, highlight its economic and social potential, and develop policy recommendations.

One of the chapters will address sports practice and consumption among households, focusing on participation, spending on events, products, and services, and current and expected social and economic outcomes.

A second chapter will explore sports-related employment, including links between sport, skills development, employability, and youth economic empowerment along the sports value chain.

Both will combine existing data (literature, case studies related to projects funded or implemented by the report’s partners national statistics, World Bank household and employment surveys) with original data collected via a new household survey in 10 to 12 African countries.

In order to generate knowledge on these little-explored topics, a household survey will be conducted in ten to twelve African countries, selected to be representative of the continent's diversity in terms of geography, income level, and the sports sector maturity (percentage of GDP generated by the sector, organization of major international sporting events, presence of ad hoc public policy, etc.). The Senegalese case will be included in all cases; potential others include South Africa, Côte d’Ivoire, Egypt, Madagascar, Morocco, and Rwanda.

Main Objectives

- Objective 1: Generate new knowledge on (i) sports practice (individual and collective) and consumption, and (ii) sports-related employment through household surveys in 10–12 African countries.

- Objective 2: Analyze these findings to draft a report that could serve as the basis for two chapters of the report ‘Unlocking the Potential of Sports in Africa’, focusing respectively on (i) the practice and consumption of sport in Africa, and (ii) on sports-related employment.

# Expected benefit

The Service Provider will be responsible for designing and implementing the household survey, and analyzing household survey data on sports practice, sports consumption, and sports-related employment.

1 – Scoping and Methodological Framework: Proposal for a questionnaire and methodology for conducting a survey of African households

After a validation exchange with AFD regarding selected countries and cities, the Service Provider will:

- Define representative samples per country (number and selection criteria of households and target cities).

- Draft the questionnaire aligned with the research questions, covering:

  - Sports practice: types of sport (collective, individual, leisure), frequency, place of practice (school, club, informal settings, etc.), context (free or supervised), motivations, barriers (infrastructure, socio-economic factors etc.), and perceived effects on individuals and communities (health, education, inclusion, social cohesion, inequality perception, etc.). Gender aspects must be explicitly integrated.

  - Sports consumption: consumption of sports products and services (equipment, memberships in sports associations or clubs, coaching, etc.) or sports-related products and services; amounts spent by type of expenditure; participation in major international sporting events, or other sporting events; attendance at spectator sports facilities;  viewing of competitions or sports programs: type of sport, venues/channels, factors facilitating or hindering consumption; sports tourism perceived effects, particularly in terms of social ties; economic and social effects of sports consumption. Where applicable, link between consumption and individual and collective sports participation.

  - Employment: quantification of formal and informal jobs directly or indirectly linked to sport, and the impact of sports practice on employment (through skills, employability etc.)

• Formalise a survey methodology (number of questions, appropriate approach for interviewing households, data collection methods, etc.).

The various questions should provide insight into the practices, consumption and employment of all members of the households surveyed, and map the practice and consumption of sport and sport-related jobs by gender, age group, income level and socio-professional category.

The proposal submitted by the Service Provider must be validated by the Prescribing Service, which will verify its consistency with the research questions. This validation may be the subject of an ad hoc meeting with the AFD departments, with the participation of other partners in the project, if applicable.

2 – Survey Implementation

The Service Provider will conduct telephone and/or online surveys of approximately 1,000 households per country (≈600 in the capital, ≈400 in a secondary city), across 10–12 countries (10,000–12,000 households total). The survey methods will be validated with the Prescribing Service based on the proposal made by the Service Provider. Field visits are not expected.3 – Data Analysis and Reporting

The Service Provider will produce a 12,000–14,000-word analytical report based on the collected data, complemented by existing academic and statistical sources (from national sports ministries, World Bank employment surveys, etc.).

The report will include:

- Part I: Sports practice and consumption (to form a chapter of Unlocking the Potential of Sports in Africa).

- Part II: Sports-related employment (to form another chapter of Unlocking the Potential of Sports in Africa).

Each part will include both country-level analyses and cross-country comparisons considering institutional, socio-economic, and cultural contexts. The report will be produced by one or more individuals with knowledge of the sports sector, ideally in the context of developing countries. AFD will validate the final report.

# Deliverables expected

The Service Provider shall submit the following deliverables:

| Milestones | Dates |
| --- | --- |
| Start of service provision | Date of notification + 1 week |
| Scoping report and methodology | Date of notification + 4 week |
| Final version of the questionnaire | Date of notification + 6 week |
| Restitution of raw survey data (anonymized) | Date of notification + 11 week |
| Interim Analytical Report (2-part, including a comparative analysis) | Date of notification + 14 week |
| Final report (in 2 parts, including a comparative analysis), put in the format defined by the prescribing service | Date of notification + 16 week |

This schedule may only be modified by the Prescriber in the following cases:

- The work cannot begin on the scheduled date or cannot proceed as agreed for reasons attributable to the Prescriber;

- Modifications or additions are requested by the Prescriber.

The Service Provider undertakes to provide the Prescriber with the following deliverables, produced in accordance with the expectations specified in Article 4 above:

- A scoping report (approximately 5,000 words) including: (i) a sampling proposal, (ii) a data collection strategy proposal, including anonymization and storage methods, (iii) an analysis methodology proposal. This report shall include elements justifying the proposed choices in terms of scope (including sampling and choice of countries) and methodology, enabling the surveys to be carried out and the research questions posed by the report to be answered. It shall be delivered four weeks after notification.

- A finalised questionnaire, taking into account any comments made on the scoping report, six weeks after notification. This work may be carried out in two stages if necessary: the first stage aims to test the questionnaires and survey methods on a limited number of households and countries, in order to adjust, if necessary, the questions asked, the methods of conduct (time slots, management of local constraints, etc.); the second stage will consist of distributing questionnaires to all the samples surveyed.

- Anonymised raw data from the surveys, 11 weeks after notification.

- A provisional report of approximately 12,000 words, 14 weeks after notification, consisting of:

  - a section analyzing data on sports participation and consumption, including a comparative analysis between countries and between capital cities and secondary cities;

  - a section analyzing data on sports-related jobs, including a comparative analysis between countries and between capital cities and secondary cities.

- A final report of approximately 12,000 to 15,000 words (excluding appendices), 16 weeks after notification, consisting of:

  - a section analyzing data on sports participation and consumption, including an analysis of each country/city and a comparative analysis between countries and between capital cities and secondary cities, including summary graphs and tables. This section may be transformed into a separate chapter of the report ‘Unlocking the Potential of Sports in Africa’.

  - a section analyzing data on sports-related jobs, including an analysis of each country/city and a comparison between countries and between capitals and secondary cities, including summary graphs and tables. This section could be transformed into a second chapter of the report ‘Unlocking the Potential of Sports in Africa’.

The Service Provider shall be required to provide these reports in electronic format to the address provided at the service launch meeting.

The Prescriber shall validate each compliant report. Only the express written validation of each report by the Prescriber shall constitute proof of compliance.

In the event of a non-compliant report, the Prescriber, through the project manager, shall send comments/observations by any means within seven working days of receipt of the report. These comments/observations must be taken into account by the Service Provider, who shall submit a revised report within seven working days of the Prescriber sending their comments.

# Execution modality

## Expected methodology

The Service Provider shall propose the methodology deemed most appropriate for carrying out its activities, as well as teams and overall project management, in order to provide the necessary elements at each stage to enable AFD to meet the above objectives. Its proposal shall include elements justifying the choices made in terms of scope (including sampling and choice of countries) and methodology.

The Service Provider will favour telephone and/or online survey methods, which may be adapted according to the contexts (countries, cities) where the data is collected.

The Service Provider undertakes to comply with the principles of research ethics, professional conduct and scientific integrity, in particular the free and informed consent of participants and respect for confidentiality and the protection of personal data (GDPR).

The final methodology proposal will be validated by the Prescribing Department.

## Special requirement for implementation/ Conditions of execution

The project manager will be the Service Provider's contact person. The information necessary for communication will be provided to the Service Provider at the contract launch meeting.

The Service Provider undertakes to appoint a single contact person responsible for monitoring this contract.

Each deliverable must be approved by the Prescriber.

The Prescriber undertakes to provide written observations, comments and any requests for changes no later than seven working days after their submission by the Service Provider. If necessary, during this period, the Prescriber may convene a meeting between its teams and those of the Service Provider to discuss the deliverables and any possible modifications.  At the request of the Prescriber, representatives of the partner institutions of the report ‘Unlocking the Potential of Sports in Africa’ may participate in these meetings.

The Service Provider undertakes to take into account any recommendations and to make the requested changes, in accordance with the Contract and its Annexes.

The deliverables will be produced in English.

## Execution schedule

The Service Provider shall comply with the timeline set out in Articles 5 above.

# Expected skills of the Service Provider

The Service Provider shall mobilize qualified staff with appropriate experience to achieve the objectives of these Terms of Reference. In particular, he will designate a project manager who will be, among other things, responsible for the entire operation for the provider vis-à-vis the AFD, and principal counterpart for AFD.

More specifically, the team mobilized by the Service Provider must have the following capabilities and skills:

- Strategic vision

- Strong expertise in sports economics and sociology

- Ability to design suitable methodologies

- Capacity to conduct/commission large-scale multi-country household surveys (10,000–12,000 households)

- Capacity to conduct/commission a qualitative and quantitative analysis of the survey’s data

- Excellent drafting skills

# Means made available to the Service Provider

AFD will provide relevant databases available within the framework of this study.

The budget ceiling for this assignment shall not exceed €135,000 (one hundred thirty-five thousand euros).

# Annexes

Concept Note of the joint AFD–World Bank Group report “Unlocking the Potential of Sports in Africa.”