Ref: [•]

Terms of reference for (i) conducting a diagnosis of BRD and and (ii) facilitating the launch of a policy-based loan to be financed by AFD

CONTENTS

I.	Introduction	2

II.	Beneficiary	2

III.	Scope of work of the assignment	3

IV.	Expected deliverables	5

V.	Expected methodology and time frame	6

VI.	Required expertise	7

Appendix 1: Breakdown of tasks and additional information	9

Appendix 2: AFD policy-based loan to financial institutions	11

Appendix 3: Projection description of AFD first policy-based loan to BRD	15

Appendix 4: Project Description of AFD Credit Line to support IREME Invest initiative	17

Appendix 5: Outline of a co-construction workshop to define an institution’s transformation path	18

Appendix 6: AFD’s exclusion list	19

Appendix 7: AFD’s exclusion list gap analysis	23

# Introduction

Rwanda is a small, landlocked country in East Africa, home to approximately 13 million people on a small territory. With a GDP of around USD 14 billion and a per capita income of about USD 1,000, Rwanda remains classified as a low-income country. Yet, it has achieved remarkable progress over the past 25 years in terms of economic growth, institutional reform, and social development. It is now widely recognized as a model of stability and structural transformation on the African continent.

The country’s long-term development agenda is anchored in Vision 2050, which aims to transition Rwanda to an upper-middle-income country by 2035, and to high-income status by 2050, ensuring high quality of life for all. Vision 2050 is built around three key pillars of transformation:

- Driving industrialization and structural transformation of exports;

- Achieving a green, climate-resilient economy;

- Building a competitive, knowledge-based economy integrated into global value chains.

To implement this vision, the government has adopted the Second National Strategy for Transformation (NST2, 2024–2029), building on progress made under NST1 (2017–2024). NST2 focuses on accelerating economic transformation through:

- Private sector–led growth;

- Development of smart and green infrastructure;

- Greater financial inclusion for households and MSMEs;

- Strong mobilization of domestic and international investment.

It targets an ambitious average annual GDP growth rate of 9.3% over the next five years, driven by increased domestic savings, exports, productivity, and private investment. This path also relies on strengthening human capital, digitalizing the economy, and creating a vibrant innovation ecosystem.

However, these ambitions are pursued in a context of significant climate vulnerability. While contributing less than 0.0003% of global emissions, Rwanda is highly exposed to physical climate risks — including droughts, floods, and landslides — due to its reliance on rainfed agriculture, hydropower, and sensitive watershed ecosystems. The country ranks 125th out of 182 on the ND-GAIN Climate Resilience Index, highlighting the urgency of promoting low-carbon, inclusive, and resilient growth, a priority explicitly integrated into NST2.

As Rwanda’s national development bank, the Banque Rwandaise de Développement (BRD) plays a central role in financing these long-term priorities. BRD has actively integrated ESG considerations into its operations and has developed a green finance strategy and pipeline of projects under the dedicated climate finance facility, Ireme Invest. In this context, AFD is considering the design of a policy-based loan to BRD up to EUR 30 million along with a Technical Assistance Programme of up to EUR 300,000. The policy-based loan will be mainly structured around performance-based indicators on ESG (including climate, social, governance and biodiversity indicators) but could include process indicators. This innovative financing structure would reinforce BRD’s leadership in sustainable finance while supporting Rwanda’s broader policy goals in green growth, inclusion, and resilience against climate change.

# Beneficiary

The Beneficiary

The Banque Rwandaise de Développement (BRD) is Rwanda’s sole national development bank and plays a central role in financing the country’s transformation agenda. Founded in 1967, BRD is majority-owned by the Government of Rwanda through the Agaciro Sovereign Fund (71.98%) and the Rwanda Social Security Board – RSSB (26.4%), together holding over 98% of its share capital. Other shareholders include the Government of Belgium (0.9%), SONARWA (0.3%), and the Bank of Kigali (0.1%).

Historically focused on agricultural lending, BRD gradually expanded its operations to other areas of the economy. It became a key government financial vehicle in 2005, officially tasked with supporting the implementation of national development priorities. In line with the first National Strategy for Transformation (NST1), BRD launched its 2018–2024 strategic plan to realign its operations with national objectives.

Under its new 2024–2028 Strategic Plan, BRD has sharpened its focus on contributing to the second National Strategy for Transformation (NST2). The bank aims to scale up long-term financing in several priority sectors, including agriculture, export promotion and industrial transformation, energy, green finance and the digital economy, public infrastructure, and affordable housing.

BRD has also committed to strengthening its Environmental, Social, and Governance (ESG) performance, with the objective of aligning 75% of its loan portfolio with ESG standards by 2028. Furthermore, the bank aims to allocate 30% of its lending to climate-related projects, and another 30% to gender-responsive investments. Fully impact-oriented, BRD aligns its lending with the Sustainable Development Goals (SDGs) and has adopted performance-based financing models, including sustainability-linked instruments that enable it to mobilize concessional and innovative resources. Since 2023, BRD has successfully issued two Sustainability-Linked Bonds (SLBs).

The BRD-AFD Partnership

This new project builds upon the strong and evolving partnership between AFD and BRD. This collaboration has supported BRD’s ambitious institutional and green transformation journey, initiated through a first AFD policy-based loan in 2021 and its associated technical assistance programme. These interventions enabled the development of several foundational tools, including a climate finance strategy, a reinforced Environmental and Social Management System (ESMS), a Gender Action Plan, a revised Investment Strategy a climate risk management tools and an M&E system currently under operationalization.

This structuring support has firmly positioned BRD as a leading sustainable finance actor in Rwanda, paving the way for:

- Two Sustainability-Linked Bond (SLB) issuances (with climate and gender KPIs)

- BRD’s accreditation with the Green Climate Fund (GCF) in 2025

- A new AFD line of credit in 2023 under IREME Invest initiative to reinforce BRD’s pipeline and expertise in climate mitigation and adaptation.

In line with this strategic shift and building on this strong partnership, BRD has requested financial and technical assistance from AFD to structure a new policy-based loan that will build on previous projects. This initiative will contribute to reinforcing BRD’s climate, biodiversity and social impact trajectory, while more broadly supporting Rwanda’s transition towards a green, inclusive, and competitive economy, as envisioned in the NST2.

# Scope of work of the assignment

The main objective of this assignment is to carry out a comprehensive feasibility study for the structuring of a policy-based loan to BRD, including:

- A review of BRD’s overall strategy and achievements accomplished since the launch of the AFD-BRD programmes, as a base for the new structuring.

- A review of BRD’s ESG-related commitments and strategic objectives, including its climate, biodiversity, gender, and sustainable development commitments and targets, and how these align with national and international frameworks (e.g. NST2, SDGs, Paris Agreement, KM-GBF).

- The design of an action plan and matrix including the identification and formulation of robust indicators for the policy-based loan.

- The definition of the components of the technical assistance programme associated to this policy-based loan, including support to the transformation plan/roadmap and capacity building and training programme.

- The design of a disbursement mechanism based on verified indicators and performances.

- Recommendations on the governance, monitoring, and risk management framework of the project.

The Service Provider will be expected to perform the following tasks:

Activity 1: Institutional and strategic analysis of BRD

- Review BRD’s strategic plan (2024–2028), ESG policies, investment strategy, climate strategy (including the bank’s positioning/commitments with regard to fossil fuel activities), biodiversity strategy, gender action plans, existing SLB Framework and project pipeline;

- Assess BRD’s existing capacity in terms of ESG, climate, biodiversity, gender and social integrations, data management, and impact monitoring;

- Assess BRD’s portfolio breakdown and performance against its previously established objectives (including adherence to ESG policies, climate goals – in terms of both mitigation and adaptation, biodiversity goals and gender considerations) to serve as a foundation for defining new indicators;

- Assess BRD’s potential portfolio exposure to climate physical and transition risks, and mitigation measures if any, especially whether Nature based solutions are taken into account as mitigation options;

- Assess current level of Environmental and Social Management System (ESMS) implementation (details presented in Appendix 1);

- Assess current level of development and implementation of the climate risk management tool, and potential areas for improvement, taking into account the recent developments financed through the previous AFD project;

- Reflect on the achievements and operational lessons learned from previous AFD–BRD programmes (1st policy-based loan, Ireme invest credit line).

Activity 2: Design of the action plan, matrix and associated indicators

- Building on the diagnostic conducted in Activity 1, collaboratively develop a draft action plan and matrix with BRD, outlining clear objectives aligned with BRD’s strategic plan and AFD’s policy-based loan (details presented in Appendix 1).

- Propose a shortlist of ambitious, relevant, verifiable and time-bound indicators, aligned with BRD’s strategic goals and SDGs, and designed as a continuation of those developed under previous AFD projects. These will include indicators potentially linked to climate finance (including, ideally a specific and ambitious target for adaptation), gender mainstreaming, green infrastructure, biodiversity finance, climate and/or E&S risk management, social inclusion or governance.

- For each proposed indicator, (i) establish a definition and a calculation methodology (including data sourcing),  (ii) conduct a portfolio screening to set a clear baseline with intermediary and final targets, and (iii) implement a verification methodology.

- Include process-oriented indicators, where appropriate, if they contribute meaningfully to institutional transformation or the operationalisation of BRD’s commitment on SDGs (e.g., adoption of internal framework or strategy on biodiversity, implementation of tracking systems, etc.);

- Ensure that these indicators are suitable (i.e. with a clearly identified baseline and target) for an integration into a policy-based loan disbursement framework, and that they are coherent with the indicators contained in BRD’s SLB framework.

Activity 3: Design of the policy-based loan and its technical assistance programme.

- Finalize the action plan and matrix, specifying objectives, the actions needed to achieve them, associated risks with mitigation measures, and required technical support.

- Recommend a structure for the policy-based loan’s disbursement schedule (3 tranches targeted) with performance-based triggers tied to selected indicators.

- Assess the feasibility of different verification modalities and identify capacity-building needs if relevant.

- Propose a monitoring and evaluation framework, including data collection protocols and reporting formats.

- Qualify and size BRD’s technical support needs for the implementation of the policy-based loan. This activity will include the definition of the components of the technical assistance programme (including a dedicated capacity building programme), the specification of the modalities of structuring and carrying expertise and the proposition of a detailed budget for each activity.

# Expected deliverables

The Consultant shall provide the following deliverables:

- Deliverable 1: Diagnosis report covering:

  - Review of BRD’s strategic documents (strategic plan, ESG policies, investment strategy, climate strategy, biodiversity strategy, gender action plan, SLB Framework, etc.);

  - Completed ESMS diagnostic tool with findings and conclusions;

  - Identification of potential areas of improvement in recently developed climate risk management tools and assessment of their effective integration into the bank’s processes;

  - Identification of existing monitoring systems, data availability, and institutional readiness to implement potential indicators related to climate, social, gender and biodiversity indicators;

  - Analysis of BRD’s portfolio breakdown and performance against its previously established objectives.

  - Identification of potential areas for performance-based structuring and ESG result areas, in continuity with previous projects implemented with BRD.

- Deliverable 2: Draft of action plan including the indicator framework and structuring scenarios

  - Outline of objectives in alignment with BRD’s strategic plan and AFD’s policy-based loan.

  - Proposal of a shortlist of relevant, ambitious, and verifiable indicators, aligned with BRD’s strategic targets on climate, social, gender and biodiversity, including their definition and calculation methodology;

  - For each proposed indicator, establishment of baseline values and targets, and identification of data sources and validation methods;

  - Preliminary proposition for i) the content of the matrix (3 tranches) of the policy-based loan and ii) the content of the related TA Programme;

  - Preliminary risk analysis and early recommendations on governance and monitoring of the project.

- Deliverable 3: Final Feasibility Report and Operational Recommendation

  - Final structuring proposal for the policy-based loan (including the matrix) and the technical assistance programme, with validated indicators, disbursement mechanism, and verification methodology;

  - Proposal for a monitoring and evaluation framework including reporting formats.

Each deliverable shall include:

- A detailed report in Word format (no specific outline),

- An executive summary in Word format, summarizing the content of the report,

- A PowerPoint presentation summarizing the content of the report,

AFD and BRD will review and comment the draft versions of the deliverables. The Consultant will reflect those comments on the final version of the deliverables, which will be ultimately validated by AFD.

The Consultant will write all deliverables in English.

# Expected methodology and time frame

In its technical offer, the Service Provider shall explain the methodology it intends to follow to perform each activity of the expected service. The methodology shall clearly distinguish between tasks that can be performed on desk, and those which must be performed on site with BRD.

The Service Provider shall organize at least the following meetings:

- one kick-off meeting following contract notification by AFD;

- one feedback meeting with AFD following the field mission;

- one feedback meeting with BRD and AFD following the submission of deliverables 1 and 2;

- meetings with relevant stakeholders throughout the study.

In its proposal, the Service Provider will include any comment or suggestion deemed relevant about the methodology.

The study should mobilize about 80 experts / day for an estimated period of 10 - 12 weeks, with the following indicative schedule:

| Activity | Deliverables | Indicative workload |
| --- | --- | --- |
| Activity 1 Institutional and strategic analysis of BRD | Diagnostic report of BRD’s strategic documents (strategic plan (2024–2028), ESG policies, investment strategy, climate strategy, biodiversity strategy, gender action plans, existing SLB Framework and project pipeline), implementation of ESMS, data and monitoring systems, and potential areas for performance-based indicators’ structuring | 20 days |
| Activity 2 Design of action plan and associated indicators | Draft of action plan including the indicator framework and structuring scenarios | 35 days |
| Activity 3 Design of the policy-based loan and its technical assistance programme | Final feasibility report and operational recommendations regarding the policy-based loan structure and its technical assistance programme | 25 days |

# Required expertise

The Service Provider may be a consulting firm or a consortium of firms specializing in the area of ESG mainstreaming for financial institutions (on risks and positive impact assessment). He must have proven experience in project engineering for development support projects in multi-stakeholder environments involving public organizations and financial institutions. It must also demonstrate its ability to mobilize high-level expertise in the banking and financial sectors. Expertise on the financial system will be required. Finally, prior experience in setting up development projects / carrying out feasibility studies, as well as knowledge of AFD Group's tools and procedures, would be significant assets.

In total, the team proposed by the Service Provider will need to have strong expertise in the areas outlined above and could be organised as follows (indicative proposal, the Service Provider being free to adapt his team proposal with justification):

Team Leader / Sustainable Finance Expert

The Service Provider will propose a team leader to act as a central focal point for the project, from a technical and/or administrative level, support the coordination of all Service Provider activities under the assignment, lead report writing, and provide backstopping if necessary. The Programme coordinator shall be a senior expert (at least 10 years of experience) in development finance or banking, with a strong track record in ESG mainstreaming and structuring of policy-based loans or similar performance-based mechanisms.

Pool of experts:

The Service Provider shall provide a team with a wide set of skills. The expertise that is expected to be mobilized in the context of this assignment are outlined below:

Climate finance, biodiversity and ESG expertise

The Service Provider shall provide expertise on a range of climate finance, biodiversity finance and ESG topics to be deployed with a variety of clients each with specific needs. The climate and biodiversity finance, and ESG expert shall demonstrate deep experience in the development and implementation of climate strategies, green finance mechanisms and ESG integration in financial institutions. He shall demonstrate ability to work on climate-related indicators (mitigation, adaptation), biodiversity indicators and international reporting frameworks (e.g. SDG alignment, Paris Agreement, GCF accreditation, KM-GBF monitoring indicators). He shall demonstrate a strong experience in portfolio screening and impact analysis.

Gender and social inclusion expertise

The Service Provider shall provide expertise in gender mainstreaming and social impact assessment for financial institutions. This expertise shall demonstrate strong knowledge in the design of gender/social indicators and results frameworks for financial institutions.

ESG risk management expertise

The Service Provider shall provide experts with specific expertise in ESG risk management and Environmental and Social Management Systems within Fis. Experience in evaluating the implementation and operationalization of ESMS, and in aligning with international standards (e.g. World Bank and AFD framework) is required.

Monitoring & Evaluation/ Result based financing expertise

The Service Provider shall provide expertise in designing monitoring frameworks and performance indicators linked to financial disbursements. Strong background in evaluation methodologies, indicator definition (including process indicators), baseline assessments, and data validation are required.

Organization management expertise

The Service Provider shall demonstrate strong organization management expertise, with proven experience in providing strategic and organizational support to financial institutions. This includes work on transformation projects, institutional capacity building, restructuring, and strengthening governance within the banking sector. Key competencies include:

- Project and change management experience, including the ability to design and facilitate workshops effectively.

- Experience working with banks in emerging markets, with specific exposure to financial institutions in Eastern Africa and Rwanda considered a strong asset.

- Excellent interpersonal, facilitation, and communication skills, both verbal and written.

The Service Provider is free to propose other particular expertise it finds relevant in response to the TORs. These should be added by the Service Provider into the Schedule of Unit Prices document, and the Service Provider should highlight whether these additional experts are senior, confirmed or junior profiles.

# Appendix 1: Breakdown of tasks and additional information

Activity 1: Assess current level of Environmental and Social Management System (ESMS) implementation

The Consultant will Establish a diagnostic on the level of maturity of the ESMS covering the following key requirements:

- Exclusion list compliance. Screening for exclusion based on AFD’s exclusion list.  In particular, applying the correct methodology to verify that article 17. Biodiversity and Article 19. forced eviction, are not triggered (see annex 1).

- Categorisation tool methodology.  Verify that the categorisation tool is based on a methodology that covers multiple criteria and provides a final category that aligns with AFD.  100% of sub-projects must be screened. Baseline data has to be reliable and sufficiently detailed.

- Level of due diligence associated with the E&S category.  Once a subproject is categorised, the level of detail of the environmental and social impact assessment has to be compatible with AFD’s own requirements (A = detailed ESIA; B+ = focused ESIA; B = simplified ESIA; C= any relevant E&S measures as established during the screening).

- Preparation of ToR for ESIA studies. Based on the project specific screening and categorisation, ToR must reflect the highlighted risks and impacts. ToR must also make reference to the applicable standards as requested by the donor. Selection of competent consultant in order to conduct the studies.  Presence of generic TOR and templates for ESIA, SEP, RAP, monitoring plan.

- Quality control of ESIA studies.  Once a study has been submitted to BRD it must be quality controlled by an independent expert (internal or external).  The quality control must be documented.  In case of major non-compliance, the ESIA study must be revised. Minor non-compliances have to be addressed through an ESAP.  Establish capacity of BRD to conduct this quality control for each level of E&S risk.

- E&S clauses in the financing agreement.  The financing agreement with the final beneficiary or the partner financial institutions have to reflect all E&S requirement from the donor. Monitoring and reporting requirements must be clearly established.

- E&S resources available. The internal resources dedicated to the E&S need to be sufficient and competent in order to process each sub-project.  External resources can be made available to support the bank.  Internal expertise needs to reflect the portfolio in terms of sector, risk category and main impacts (biodiversity, OHS, resettlement, …).

Activity 2 and 3: Design of the action plan, matrix and indicators

It is to be noted that, one of the most critical steps in the deployment of a policy-based loan is the development of an ambitious, yet realistic and adapted action plan that BRD will have to follow. The Service Provider will thus lead the development of a draft action plan in co-construction with BRD, to prepare clearly defined objectives linked to BRD’s strategic plan and policy-based loan ambitions, on which AFD and RBD shall jointly agree (level of ambition and targeted indicators to be included in the Action Plan).

This work will follow a co-construction approach, and be mostly built through co-construction workshops that will bring together representatives of BRD from managerial and non-managerial positions. This method should ensure that the CAP will be tailored to the capacities, willingness and business context of BRD.

Workshops should be structured to meet the following objectives:

- Alignment on the strategic plan of BRD and definition of objectives: Identify the bank’s challenges in order to achieve them, discuss the diagnosis’ recommendations, and determine the main work streams in the form of change objectives arranged in the relevant timeframe.

- Identify projects and actions required to achieve the change objectives, including change management actions, Again, the action plan will result in contractual obligations (in the form of matrix of change) and key project documents in the framework of a climate policy-based loan to be signed between AFD and BRD. The Action plan must be constructed in reference to clearly identifiable and measurable goals and indicators across the axes identified for improvement. The change matrix will be built from the selection of relevant actions (not all actions from the action plan need to qualify as a disbursement trigger).

- Identify risks and mitigation measures for each action;

- Identify technical support requirements: The Service Provider will clearly qualify and size BRD’s technical support needs for the implementation of the action plan and the achievement of the targeted results. This activity will include the definition of the components of the technical assistance programme, the specification of the modalities of structuring and carrying expertise and the proposition of a detailed budget for each activity. The focus of the TA should be to support existing BRD teams that will be in charge of implementing the action plan toward targeted results.

The service Provider should also assess the impacts of the proposed plan and matrix on all areas of the bank’s organisation and propose a project management organisation that will secure the implementation and delivery of the results.

Should the Service Provider have any questions regarding the advised co-construction methodology, it will be able to refer back to AFD transformation expert. Examples are also provided in Appendix 5.

# Appendix 2: AFD policy-based loan to financial institutions

Under this approach, AFD has developed a specific loan dedicated to FI, the policy-based loan tool. The funds made available through this loan can be used to finance general activities of the FI (with the exception of those on AFD’s exclusion list; see Appendix 6) and are not earmarked for any specific use of funds.

The funds are released in several drawdowns under specific conditions linked to the achievement of objectives for change predefined in an action plan/matrix of changes that contains milestones in terms of transformative actions towards the integration of green, climate and social finance within the FI. Those milestones, which serve as triggers to disbursements, are specifically designed to best meet the FI’s needs and are spread over a three-to-four years period to ensure a gradual, sustained and yet realistic momentum.  Examples of transformative matrices addressing climate, biodiversity, and gender are presented below. These serve as illustrative models that should be tailored and redesigned to reflect the specific characteristics and needs of each individual IF profile.

To support the FI in achieving these triggers and milestones, AFD’s policy-based loan is usually accompanied by a dedicated grant for the implementation of a technical assistance programme.

To be eligible for this loan, the FI must also demonstrate the effectiveness of disbursements on "Paris Agreement aligned'' financing equivalent to the amount of the loan in the AFD's countries of operation's list during the Implementation Period. ln practice, this means that the FI must demonstrate to AFD a disbursement equivalent to the amount of the loan, in all asset categories, with the exception of the following assets:

- Any activity included on the Exclusion list for AFD Group in foreign countries (see Appendix 6),

- Any coal-fired power plant project,

- Any activity included in the AFD Group's strategy for energy transition which is misaligned with a Paris Climate Agreement's trajectory: any project for power plants based exclusively on fuel oil or diesel, any exploration or production projects, or projects dedicated exclusively to the transport of coal, gas or oil, any infrastructure associated with a facility for exploring, producing or storing fossil resources (mines, processing units, refineries, storage, etc.) or for fossil fuel power generation, any large mining infrastructure associated with exploring, producing, transforming and/or exporting mining resources, any activity related to large petrochemicals industries.

Example of a climate action plan/Matrix of changes

This example is provided on an indicative basis, all these actions correspond to specific cases and respond to individual institutional profiles)

| Project Action Plan and Drawdown Triggers |  |  |  |
| --- | --- | --- | --- |
| Principles | Drawdown 1 | Drawdown 2 | Drawdown 3 |
| 1: COMMIT to climate strategies | T#1 There is a clear evidence of the engagement of the relevant Departments in the Climate Finance Proposal elaboration T#2 A climate task force has been established with a clear mandate for the Climate Finance Proposal elaboration no later than end of XX | T#5 A Climate Finance Strategy has been elaborated (including specific targets and KPIs) and the climate task force is in charge of its implementation T#6 The Climate Finance Strategy has been endorsed by the Bank’s top management | T#14 The Climate Finance Strategy has been adopted by the Board of Directors and is part of the Bank's strategic framework |
| 2: MANAGE climate risks | T#3 The Bank has implemented a list of exclusion | T#7 An E&S risks policy is being implemented, including exclusion list, E&S risks categorization and classification with adapted due diligences and internal processes for projects review on E&S risks (during both project appraisal and implementation) T#8 A strategic workshop on climate finance has been held involving all relevant Departments, which included an awareness session on climate-related risks | T#15 An E&S training program has been implemented for employees involved in project financing #16 The Bank has experimented a climate risks screening process within its portfolio |
| 3: PROMOTE climate smart objectives | - | T#9 An opportunity study for innovative climate finance facilities /instruments adapted to the Bank’s business model has been conducted | T#17 Based on the opportunities identified, the Bank has launched a pilot instrument dedicated to climate finance on the continent |
| 4: IMPROVE climate performance | - | T#10 The Bank has implemented a capacity building program on climate for its staff from relevant Departments T#11 The Bank has identified required measuring tools to track and monitor climate performance | T#18 The Bank implemented adapted measuring tools in order to tack and monitor its climate performance |
| 5: ACCOUNT for your climate action |  | T#12 The Bank has defined relevant indicators to monitor its climate activity and establishes a baseline T#13 The Bank has reviewed the adequacy or its information system to monitor those indicators | T#19 The Climate Finance Strategy has been published and presented in the Annual General Meeting T#20 The Bank includes a climate section in its annual report that accounts on progress in the implementation of its Climate Finance Strategy |

Example of a Biodiversity action plan/Matrix of changes

| Project Action Plan and Drawdown Triggers |  |  |  |
| --- | --- | --- | --- |
| Principles | Drawdown 1 | Drawdown 2 | Drawdown 3 |
| Governance | 1.1 Establishment of an awareness program on biodiversity for all levels of the institution (Board of Directors, relevant committees, vice-presidencies, key personnel). Organization of training sessions covering 100% of the identified personnel. - Awareness materials developed and attendance lists for different awareness sessions. | 2.1 Establishment of a training program on climate change and biodiversity for members of the ESG Committee, cooperative governance, relevant committees, vice-presidencies, management, and staff of the institution – 50% of identified personnel covered. - Training materials developed and invitations issued for the different training sessions, including attendance lists. | 3.1 Establishment of a training program on climate change and biodiversity for members of the ESG Committee, vice-presidents, management, and key staff of the institution – 90% of the staff covered. - Training materials developed and invitations issued for the different training sessions, including attendance lists. |
| Strategy |  | 2.2 Launch of a diagnostic and alignment process with the Global Biodiversity Framework to define an action plan approved by the Board of Directors. Includes conducting a diagnosis and proposing an action plan considering the bank’s activities, peer practices in Colombia and the region. - Presentation of reports to the Board and adoption of the action plan. | 3.2 Definition and approval by the Board of Directors of a biodiversity strategy, including measurable objectives adapted to the bank’s activities. The joint strategy is based on the diagnostic and alignment process with the Global Biodiversity Framework (GBF). - Presentation of the strategy to the Board and its approval. - Extract of the Board of Directors’ meeting minutes. |
| Risk Management |  |  | 3.3 Development of a mapping of risks, dependencies, and opportunities related to biodiversity, along with an action and training plan for the risk management team to assess biodiversity-related financial risks, in preparation for a TNFD report. - Diagnostic mapping, action plan, and training materials. |

Example of a Gender action plan/Matrix of changes

| Project Action Plan and Drawdown Triggers |  |  |  |
| --- | --- | --- | --- |
| Principles | Drawdown 1 | Drawdown 2 | Drawdown 3 |
| Gender and Diversity, Equity, and Inclusion (DEI) Policy | 1.1 Adoption of a DEI action plan with annual objectives approved by the Board of Directors. - Extract from the minutes of the recommendation/approval of the action plan by the extended ESG Steering Committee and/or the Board of Directors. | 2.1 Implementation of a training program on gender equality and DEI for committees, vice-presidents, management, and staff of the institution – 50% of identified personnel covered. - Training materials developed and invitations issued for the various training sessions, including attendance lists. 2.2 Monitoring of the achievement of the annual objectives set out in the DEI action plan. - Compliance report and extract from the minutes of presentation to the ESG Committee. | 3.1 Implementation of a training program on gender equality and DEI for steering committees, vice-presidents, management, and staff of the institution – 90% of identified personnel covered. - Training materials developed and invitations issued for the various training sessions, including attendance lists. 3.2 Achievement of the annual objectives set out in the DEI action plan. - Compliance report and extract from the minutes of presentation to the ESG Committee. 3.3 Development of a financial line and a non-financial product specifically aimed at reducing gender inequalities identified through a diagnostic exercise on sectoral and regional disparities financed by technical assistance. - Guidelines for financial and non-financial products – format depending on the mechanism to which it will be applied (direct credit or intermediation). |

# Appendix 3: Projection description of AFD first policy-based loan to BRD

I – PROJECT DESCRIPTION

The project aims to support the implementation of Rwanda’s National Strategy for Transformation (NST1) by strengthening the financial and operational capacities of its national development bank, the Banque Rwandaise de Développement (BRD). This support will enhance BRD’s ability to fulfill its development finance mandate and achieve the ambitious objectives set by the Government of Rwanda. The transformational credit line instrument selected by AFD, in agreement with BRD, is designed to contribute to the bank’s institutional strengthening, with the following specific objectives:

- Support the growth of BRD’s lending activity;

- Improve BRD’s strategic positioning as a development bank, enabling it to generate additionality within the Rwandan financial sector and promote sustainable growth in priority sectors of the economy;

- Strengthen BRD’s risk management and financial oversight capacities, in line with its new strategy derived from NST1;

- Increase BRD’s development impact by supporting its positioning as a “green bank,” including through the definition of a Climate Strategy and the enhancement of its Environmental and Social (E&S) risk management and monitoring practices.

The project comprises two complementary components:

- A policy-based loan designed to support the bank’s lending activity, linked to a set of institutional changes outlined in a matrix of reforms; and

- A technical assistance programme to support BRD in implementing the identified structural reforms.

II – STAKEHOLDERS AND IMPLEMENTATION MODALITY

BRD is the beneficiary and implementing agency of the programme. AFD’s support includes:

- A EUR 20 million-equivalent non-sovereign concessional loan (in USD), with a 13-year maturity and 3-year grace period. The loan will be disbursed in three tranches, each conditional upon the achievement of specific institutional changes detailed in a reform matrix structured around four pillars, all contributing to the project’s overarching objective:

  - Pillar 1 – Governance and Institutional Infrastructure: Strengthening of audit, HR, risk, and financial management functions in line with BRD’s new strategy, as well as the deployment of internal information systems;

  - Pillar 2 – Investment Strategy: Definition and implementation of a new investment strategy, with quantitative and qualitative targets aligned with NST1 and supported by technical assistance;

  - Pillar 3 – Resource Mobilization: Strengthening of BRD’s fundraising function and rollout of a more proactive commercial approach; accreditation to the Green Climate Fund (GCF);

  - Pillar 4 – Climate Strategy and E&S Risk Management: Design and implementation of a Climate Strategy and improvement of E&S risk management and impact monitoring practices for funded projects.

- A grant envelope of up to EUR 500,000 (funded by FAPS) to support technical assistance for implementing the reforms identified in Pillars 1, 2, and 4, and to provide cross-cutting support—particularly on climate-related commitments.

II – EXPECTED RESULTS

At the end of the project, BRD is expected to have achieved the targeted results, including:

- Reinforced its positioning as a public development bank in line with the mandate and objectives set by the Government, serving the private sector and, in particular, the country's priority sectors;

- Enhanced its capacity in risk management and financial oversight in accordance with its new strategy;

- Developed and operationalized a robust Climate Strategy and effective E&S risk management practices aligned with national challenges; and

- Secured additional financial resources to be allocated to its lending activities in accordance with its mandate and strategic goals.

# Appendix 4: Project Description of AFD Credit Line to support IREME Invest initiative

I – PROJECT DESCRIPTION

The objective of this project is to support Rwanda in its ambition to scale up green finance dedicated to low-carbon and climate-resilient projects, in line with the country’s ambitious climate and development goals. It entails technical and financial assistance to the Banque Rwandaise de Développement (BRD) to support the implementation of the ambitious initiative “IREME Invest,” launched by the President of the Republic of Rwanda at COP27. IREME Invest aims to facilitate the financing of green and climate-resilient projects.

Although it does not have its own legal status, IREME Invest is an initiative designed to bring together, under a common banner, operations managed respectively by the Rwanda Green Fund (FONERWA) and BRD. These two institutions have partnered to offer, in a coordinated but independent manner, a range of financial tools to address existing barriers to building strong climate project pipelines. FONERWA manages a Project Preparation Facility (PPF), while BRD manages a Credit Facility (CF), which AFD proposes to support through this project.

AFD’s financial and technical contribution to BRD comprises two main and complementary components:

- A EUR 20 million (USD equivalent) credit line to BRD;

- A EUR 1 million technical assistance programme to support BRD in achieving its climate ambitions and implementing green and climate-related projects aligned with the goals of the IREME Invest initiative.

II – STAKEHOLDERS AND IMPLEMENTATION MODALITY

BRD is the primary beneficiary of both components of the project:

- Component 1 will take the form of a non-sovereign loan granted to BRD to finance eligible final beneficiaries—Rwandan enterprises (public and/or private) implementing climate-positive investments;

- Component 2 will be locally implemented under BRD’s management and governed by a dedicated grant agreement.

To date, BRD and FONERWA have jointly mobilized over €200 million in commitments from various development partners (AFD, FCDO, EIB, CDP, SIDA) to finance the first projects under the “IREME Invest” label. Of these, €170 million is being made available to BRD to deploy direct loans to Rwandan enterprises. These initial commitments are expected to generate a demonstration effect across the broader Rwandan financial system.

III – EXPECTED RESULTS

The project is expected to:

- Contribute to strengthening the local financial system by providing accessible and affordable financing for low-carbon or climate-resilient green projects;

- Reinforce BRD’s role as a central actor in greening Rwanda’s financial system, enabling the reorientation of available financial flows toward the financing of a low-carbon and climate-resilient economy.

Through the IREME Invest label, BRD and FONERWA aim to support USD 367 million in private sector investment, create 367,000 green jobs, and avoid 1.32 MtCO₂.

# Appendix 5: Outline of a co-construction workshop to define an institution’s transformation path

N.B: the content of a following example was built as a general transformation roadmap.

# Appendix 6: AFD’s exclusion list

- Preamble

Context and objectives

The Agence française de développement (AFD) Group is supporting and accelerating the transitions towards a more just and resilient world. It contributes to France’s commitment to the global commons – the planet, social link, peace, partnerships and economic prosperity – and the Sustainable Development Goals. The Group has established high standards for social responsibility in order to ensure that its mission and its commitments are in coherence with the quality of its interventions and their sustainable development impacts. The present exclusion list is one of the tools used to implement these standards.

The objective of the exclusion list is to clearly indicate the activities that the Group refuses to finance due to ethical, regulatory, environmental or social criteria, and arising from the application of normative requirements as well as its strategic choices. Available for public consultation by AFD Group’s external stakeholders (partners, clients, civil society...), the exclusion list is published on the websites of the Group’s entities.

The exclusion list is part of a system aimed at ensuring that the Group’s operations effectively contribute to the core aims of sustainable development:

- The exclusion list identifies the activities that the Group a priori refuses to finance, which shapes upstream the actual composition of the activities portfolio.

- The Group has set up other tools to select its financing. Additional exclusions stem from the strategic frameworks (for example, climate selectivity) and the sectoral intervention frameworks, available on the Group’s website. These selectivity doctrines, regularly updated, are intended to be used within the project appraisal framework.

- While the exclusion list precedes the appraisal and evaluation process of the operations considered, it remains a useful reference throughout the entire cycle of funded projects. As such, it can lead the Group to withdraw the operation in the event of manifest non-compliance noted during a project’s appraisal or execution.

- The Group’s activity is also framed by a General Policy to prevent and combat prohibited practices, including corruption, fraud, anti-competitive practices, money laundering and terrorist financing, since such practices constitute major impediments to development.

- Lastly, AFD Group has formulated a policy on non-cooperative jurisdictions for tax purposes and the fight against money laundering and terrorist financing, aimed in particular at preventing and managing any risk of fraud and tax evasion.

Scope of application

- The present list updates the previous exclusion list (2011). The present exclusion list is a result of cross-cutting work by the Group and is applied by its member entities: AFD and its subsidiaries Proparco and Expertise France (together referred to hereinbefore and hereinafter as “AFD Group” or the “Group”).

- The list concerns all of the new financing granted in foreign States and in Overseas France.

- The Group’s exclusion list will be reviewed about every five years.

- Part 2(a) and (b) apply to the Eligible investments, Part 2(c) applies to all the Borrower’s financing

- AFD Group’s exclusion list

  - Illegal activities

AFD Group excludes financing for activities involving the production or trade in illicit products, as well as any activity that is illegal under the laws of the destination countries or of France, under national or international regulations applicable in the destination countries or in France, as well as under international conventions or agreements creating commitments for the destination countries or for France.  It involves in particular:

- Any equipment, sector or service subject to economic sanctions issued by the United Nations, the European Union or France, without absolute or relative restriction regarding the amount;

- Production or activity involving forced labour, child labour or trafficking in human beings;

- Illicit activities involving organs, tissues and products of the human body, or genetic engineering activities banned by the national bioethical standards of France or of the host country, and by relevant applicable European or international standards;

- Trade, production, breeding or possession of animals, plants or any natural products in breach of the provisions of CITES;

- Fishing activity using a driftnet in excess of 2.5 km in length;

- Research, purchase, promotion or multiplication of genetically modified seeds;

- Production, use or trade of hazardous materials (such as asbestos fibres) and all products (including chemical products, pharmaceuticals, pesticides/herbicides, ozone-depleting substances or any other hazardous product) the production or use of which is banned or which will be phased out in the regulations of destination countries or internationally;

- Transboundary trade of wastes, except those consistent with the Basel Convention and its underlying regulations;

- Exploitation of diamond mines and marketing of diamonds in countries that have not adhered to the Kimberley Process;

- Illicit trade or activities that facilitate the illicit traffic of cultural property.

  - Activities not aligned with AFD Group’s commitments to sustainable development

The strategic orientations of AFD Group reflect the mandate conferred on it by the French State, within the framework of the 2030 Agenda of the Sustainable Development Goals and the Paris Agreement.  In this capacity, it promotes social and environmental sustainability through its activities and excludes financing for the following activities whose demonstrable or potential detrimental impacts on human rights, inequalities, the climate or biodiversity are deemed incompatible with this objective:

- Production or trade:

  - relating to pornography or prostitution;

Production or trade in:

  - weapons and/or munitions;

  - tobacco;

  - alcoholic beverages (excluding beer and wine);

  - gambling establishments, casinos or equivalent enterprises;

- Production and distribution or participation in media that is racist or anti-democratic or which promotes discrimination against part of the population;

- Operations resulting in an irreversible alteration or a significant displacement of a critical element of cultural heritage;

- Projects to construct, extend or refurbish fossil fuel-fired power plants;

- Infrastructure associated to a facility for producing, storing or processing fossil energy resources (mines, processing facilities, storage, etc.) or for generating electricity from fossil energy sources, referred to in point 14 of this list;

- Projects for the exploration, production or processing or dedicated exclusively to the transport of coal, gas and oil (conventional or non-conventional);

- Biodiversity:

- Any financing in the (a) sites of the Alliance for Zero Extinction (AZE) / ,(b) natural and mixed sites on the Unesco World Heritage List20 and (c) legally protected areas (IUCN categories) and,

- Any operation leading to an adverse and irreversible residual impact on a critical habitat; /

- Any forest project or agricultural project with broad coverage (>100 ha) that does not implement a methodology ensuring zero-deforestation;

- Projects whose purpose and/or approach are inconsistent with human rights, and in the case of private sector financing, projects underpinned by rationales that clearly contradict the United Nations Guiding Principles on Business and Human Rights;

- Projects where it is known that a forced eviction within the meaning of the United Nations was carried out on the impact site of the proposed project, and which eviction can be causally linked to the purpose of this project and which is materially impossible to compensate.

  - Application to financial institutions

AFD Group requires the financial institutions with which it collaborates to apply exclusions to their financial activities, applicable to all their financing. These excluded activities include at least the items listed below, which are from AFD Group’s own exclusion list:

      - Production or trade in illicit products, as well as any illegal activity under national or international laws applicable in the destination countries;

      - Production activities or other activities involving the use of forced labour and/or child labour;

      - Trade, production, breeding or possession of animals, plants or any natural products in breach of the provisions of CITES;

      - Transboundary trade of wastes, except those consistent with the Basel Convention and its underlying regulations.

# Appendix 7: AFD’s exclusion list gap analysis

Project reference - Counterpart

AFD’s exclusion list - gap analysis

Date

A. Illegal activities

| AFD | Counterpart | Alignment and justification | Counterpart’s response |
| --- | --- | --- | --- |
| 1. Any equipment, sector or service subject to economic sanctions issued by the United Nations, the European Union or France, without absolute or relative restriction regarding the amount; |  | Aligned Partially aligned Not aligned Stricter Short description of the gap | Response to the gap identified and actions to be taken. |
| 2. Production or activity involving forced labour 4, child labour 5 or trafficking in human beings6; |  |  |  |
| 3. Illicit activities involving organs, tissues and products of the human body, or genetic engineering activities banned by the national bioethical standards of France 7 or of the host country, and by relevant applicable European or international standards; 8 |  |  |  |
| 4. Trade, production, breeding or possession of animals, plants or any natural products in breach of the provisions of CITES; 9 |  |  |  |
| 5. Fishing activity using a driftnet in excess of 2.5 km in length; |  |  |  |
| 6. Research, purchase, promotion or multiplication of genetically modified seeds;10 |  |  |  |
| 7. Production, use or trade of hazardous materials (such as asbestos fibres) and all products (including chemical products, pharmaceuticals, pesticides/herbicides, ozone-depleting substances 11 or any other hazardous product) the production or use of which is banned or which will be phased out in the regulations of destination countries or internationally; |  |  |  |
| 8. Transboundary trade of wastes, except those consistent with the Basel Convention 12 and its underlying regulations; |  |  |  |
| 9. Exploitation of diamond mines and marketing of diamonds in countries that have not adhered to the Kimberley Process; |  |  |  |
| 10. Illicit trade or activities that facilitate the illicit traffic of cultural property.13 |  |  |  |

B. Activities not aligned with AFD Group’s commitments to sustainable development

| AFD | Counterpart | Alignment | Counterpart’s response |
| --- | --- | --- | --- |
| 11. Production or trade: (i) relating to pornography or prostitution; Production or trade in:14 (ii) weapons and/or munitions; (iii) tobacco; (iv) alcoholic beverages (excluding beer and wine); (v) gambling establishments, casinos or equivalent enterprises;15 |  | Aligned Partially aligned Not aligned Stricter Short description of the gap | Response to the gap identified and actions to be taken. |
| 12. Production and distribution or participation in media that is racist or anti-democratic or which promotes discrimination against part of the population; |  |  |  |
| 13. Operations resulting in an irreversible alteration or a significant displacement of a critical element of cultural heritage;16 |  |  |  |
| 14. Projects to construct, extend or refurbish fossil fuel‑fired power plants;17 |  |  |  |
| 15. Infrastructure associated 18 to a facility for producing, storing or processing fossil energy resources (mines, processing facilities, storage, etc.) or for generating electricity from fossil energy sources, referred to in point 14 of this list; |  |  |  |
| 16. Projects for the exploration, production or processing or dedicated exclusively to the transport of coal, gas and oil (conventional or non-conventional); |  |  |  |
| 17. Biodiversity: (i) Any financing in the (a) sites of the Alliance for Zero Extinction (AZE) 19 / 20 , (b) natural and mixed sites on the Unesco World Heritage List 20 and (c) legally protected areas (IUCN categories) 21 and, (ii) Any operation leading to an adverse and irreversible 22 residual23 impact on a critical habitat; 24 / 25 (iii) Any forest project or agricultural project with broad coverage (>100 ha) that does not implement a methodology 26 ensuring zero-deforestation; |  |  |  |
| 18. Projects whose purpose and/or approach are inconsistent with human rights, and in the case of private sector financing, projects underpinned by rationales that clearly contradict the United Nations Guiding Principles on Business and Human Rights; 27 |  |  |  |
| 19. Projects where it is known that a forced eviction within the meaning of the United Nations 28 was carried out on the impact site of the proposed project, and which eviction can be causally linked to the purpose of this project and which is materially impossible to compensate.29 |  |  |  |

C. Application to financial institutions

| AFD | Counterpart | Alignment | Counterpart’s response |
| --- | --- | --- | --- |
| 1. Production or trade in illicit products, as well as any illegal activity under national or international laws applicable in the destination countries; |  | Aligned Partially aligned Not aligned Stricter Short description of the gap | Response to the gap identified and actions to be taken. |
| 2. Production activities or other activities involving the use of forced labour 30 and/or child labour; 31 |  |  |  |
| 3. Trade, production, breeding or possession of animals, plants or any natural products in breach of the provisions of CITES; 32 |  |  |  |
| 4. Transboundary trade of wastes, except those consistent with the Basel Convention 33 and its underlying regulations. |  |  |  |

For instance, on BRD's climate-related and gender-related lending and investments.

https://www.afd.fr/en/combating-corruption

https://www.afd.fr/fr/media/download/4064 (in French).

Following the integration of Expertise France into AFD Group.

“Forced labour” refers to any work or service performed involuntarily and exacted from an individual by threat of force or punishment as defined in the conventions of the International Labour Organization (ILO).

Employees must be at least 14 years of age as defined in the ILO’s Declaration on the Fundamental Principles and Rights at Work (C138 – Minimum Age Convention, Article 2), unless local laws require compulsory schooling or a minimum age for admission to employment or work. In such circumstances, the highest age requirement must be used.

Council of Europe Convention on Action against Trafficking in Human Beings (2005); Directive 2011/36/EU.

V. AR. 16 à 16-14 of the French Civil Code (mainly as set out in Law No. 94-653 of 29 July 1994 on the respect for the human body and Law No. 2004-800 of 6 August 2004 on bioethics).

The Convention for the Protection of Human Rights and Dignity of the Human Being with regard to the Application of Biology and Medicine: Convention on Human Rights and Biomedicine (Oviedo, 04/04/1997); Council of Europe Convention against Trafficking in Human Organs (Saint-Jacques-de-Compostelle, 25/03/2015).

CITES: Convention on International Trade in Endangered Species of Wild Fauna and Flora (Washington, 1973).

Programming Act No. 2021-1031 of 4 August 2021 on inclusive development and combating global inequalities prohibits financing by AFD of activities involving the purchase, promotion or multiplication of genetically modified seeds (LPDSLI – Cadre de partenariat global [Global Partnership Framework] Part II – B – b / - 3 - paragraph 6). AFD adds research activities to this (Territorial and Ecological Transition Strategy 2020-2024).

Any chemical component which reacts with, and destroys, the stratospheric ozone layer leading to the formation of “holes” in this layer. The Montreal Protocol lists ozone depleting substances (ODS), their reduction targets and the deadlines for phasing them out.

The Basel Convention on the Control of Transboundary Movements of Hazardous Wastes and their Disposal is available at: www.basel.int

Trade in cultural property is regulated by the Convention on the Means of Prohibiting and Preventing the Illicit Import, Export and Transfer of Ownership of Cultural Property (1970).

If these activities represent more than 10% of the turnover of the counterparty financed or, if the client is a financial intermediary, more than 10% of the outstandings of its portfolio.

Any direct financing of these projects or activities including them (for example, a hotel incorporating a casino). It does not concern urban development plans that could subsequently integrate such projects.

"Critical cultural heritage” is considered to be any part of the heritage that is internationally or nationally recognised as being of historical, social or/and cultural interest.

Except for projects involving mini-grids served by hybrid power plants (combining renewable energies and fossil fuels).

The term “associated Infrastructure” is used when the infrastructure is associated with a production facility using fossil fuel if the two following conditions are fulfilled: i) the infrastructure would not have been built in the absence of this fossil fuel facility, and ii) the fossil fuel facility would not be economically viable without the infrastructure.

Unless the  area of influence of the funded activities and their associated facilities does not encroach on zones that effectively meet the criteria for being designated as an AZE site – https://zeroextinction.org/site-identification/aze-site-criteria/

Unless the financing aims to conserve or restore these areas.

Unless the financing aims to conserve or restore these areas or complies with the management and spatial planning arrangements for the latter, such as those formalised in plans with international standards relating to the activities being financed – categories I-VI in World Database on Protected Areas | IUCN.

Irreversible impact: permanent conversion or degradation of biodiversity or of the ecological functions or characteristics that warranted the critical habitat designation.

Residual impact: a project’s measurable impact on a biodiversity value, after implementation of avoidance and mitigation measures, but before implementation of restoration and compensation measures.

Critical habitat: within the meaning of the World Bank’s Environmental and Social Standard 6 – 2018 or IFC-GN PS6 2019.

Unless the said project is of overriding general interest for the destination country, in which case a derogation can be presented to the Group’s governance for a decision.

Methodology including (i) a reference tool equivalent to the HCS approach, allowing for forest classification, (ii) a guarantee that no high carbon stock forest will be converted under the project and (iii) monitoring of forest cover (field or satellite monitoring).

https://www.ohchr.org/documents/publications/guidingprinciplesbusinesshr_en.pdf

United Nations Sub-Commission on Human Rights Resolution 1993/41: “Forced Eviction”. “The term ‘forced evictions’ […] is defined as the permanent or temporary removal against their will of people, families and/or communities from the homes and/or land which they occupy, without the provision of, and access to, appropriate forms of legal or other protection (Committee on Economic, Social and Cultural Rights, General Comment No. 7).

Due to the project sponsor’s refusal or its inability to identify the populations that are victims of forced evictions. Projects for which an effective remedy can be provided for violated rights will not be excluded.

”Forced labour” refers to any work or service performed involuntarily and exacted from an individual by threat of force or punishment as defined in the conventions of the ILO.

Employees must be at least 14 years of age as defined in the ILO’s Declaration on the Fundamental Principles and Rights at Work (C138 – Minimum Age Convention, Article 2), unless local laws require compulsory schooling or a minimum age for admission to employment or work. In such circumstances, the highest age requirement must be used

CITES: Convention on International Trade in Endangered Species of Wild Fauna and Flora (Washington, 1973).

The Basel Convention on the Control of Transboundary Movements of Hazardous Wastes and their Disposal is available at: www.basel.int