# Terms of reference

# and technical specifications

- General information

| # Name of the tender | # Implementation of the technical assistance program: EU-ProGreen, SMEs acceleration and training of financial institutions in evaluation of green projects in the Dominican Republic. |
| --- | --- |
| # Beneficiary | # Small and medium-sized enterprises and financial institutions |
| # Country | Dominican Republic |
| # Estimated total number of months | # 14 months |

- Context and justification of need

  - Expertise France

Expertise France (EF) is a public inter-ministerial agency for international technical cooperation, a subsidiary of the Agence Française de Développement group (AFD group). As the second largest agency in Europe, it designs and implements projects that sustainably strengthen public policies in developing and emerging countries on issues related to governance, security, climate, health, education. It operates in key areas of development and contributes together with its partners to the implementation of the Sustainable Development Goals (SDGs).

For further information: www.expertisefrance.fr

  - The Euroclima programme

Euroclima is the main cooperation programme of the European Union (EU) on environmental sustainability and climate change in Latin America and the Caribbean (LAC). Its objective is to contribute to the LAC region’s green transition, through efforts to mitigate and adapt to climate change and protect and conserve biodiversity. Under the Euroclima programme, two main outcomes are expected:

- The enabling environment for a green transition (integrated policies, legal frameworks, sectoral plans and financial instruments) will be strengthened in line with climate, biodiversity and circular economy objectives.

- Transformative approaches in key areas for the green transition will be developed, demonstrated and scaled up through mobilization of public and private funds.

Euroclima contributes to the implementation of the Global Gateway’s Investment Agenda in the region. Global Gateway is the EU’s offer to reduce the infrastructure investment gap by using public funding to mobilise private capital and investments for projects that contribute to the transition to a green and digital economy. In the Caribbean region, Euroclima is funded by the European Commission for a period of 5 years and implemented by agencies or EAMs from EU Member States (AECID, Expertise France, FIIAPP, GIZ) and the UN (ECLAC, UNDP, UN Environment). The programme is part of the regional initiatives of the Europe Team "Green transition in Latin America and the Caribbean" and "A partnership for a green Caribbean agreement".

Through Euroclima, the EU has initiated dialogues with countries to strengthen their role in defining cooperation priorities. Country-specific dialogue is conducted with key climate action institutions in each country, which allows for alignment of the programme strategies with priorities established at the national level to ensure cohesion and synergies with other activities. In consultation and coordination with the country, and under the direction of the National Focal Point (NFP), the programme supports the design of the dialogue process on a case-by-case basis.

For more information: https://www.euroclima.org/

  - The Euroclima program in the Dominican Republic

In the Dominican Republic, Euroclima’s national action includes activities to support the transition to a green economy, especially for SMEs. The European Adaptation Fund (EF) aims to help the financial and productive sectors adapt to climate change, with an emphasis on facilitating access to green finance for local businesses. This action is aligned with the Green Taxonomy of the Dominican Republic and the Carbon Emissions Boundary Adjustment Mechanism (CBAM) of the EU, focusing on promoting sustainable and low-carbon business models and improving the capacity of the local financial sector to finance green projects.

To promote this action, EF seeks a company or consortium of companies (the "Consulting Company") with experience in developing green finance products in financial institutions and SMEs (small and medium-sized enterprises), as well as in acceleration-advice on green projects.

    - Background to the action

In July 2023, at the EU-CELAC Summit, the European Union (EU) committed itself to a renewed bi-regional partnership, marked by the EU-CELAC Global Gateway Investment Agenda (GGIA). This agenda seeks to close the investment gaps in sustainable development through projects in climate-related sectors, closely aligned with Euroclima’s objectives and priorities. Within the framework of this programme, action 2.1 is being developed for the Dominican Republic which seeks to "strengthen the capacities of the financial and/or productive sector in climate change issues" through the development of activities to support green economic transitions, The SME’s in particular.

As part of Action 2.1 of Euroclima, a diagnosis was carried out with the aim of developing an initial information survey and supporting the design of the Logical Framework for Intervention. This document provides a basis for addressing the main needs of the domestic productive and financial sector over a two-year period. For the development of this document, an in-depth analysis was carried out focusing on green finance, the SME sector and its alignment with the country’s green transition goals. Green Finance is the one that, in addition to funding environmental aspects, seeks to fund the transition to a low-carbon and environmentally friendly economy. They include financing of renewable energy projects, investments in energy efficiency technologies and specialized funds in low-carbon companies.

As a result of the diagnosis, it was evident that although the country has witnessed important advances, both the financial sector and the national productive sector face significant challenges to implement a green and fair transition (GJT), and mobilize financial flows to facilitate the fulfilment of their nationally determined contribution (NDC). In the financial sector, a major need was identified to build capacities to be able to drive green finance, and to place green portfolios in the real sector.

SMEs in particular lack the skills and resources to be able to meet the technical requirements associated with purchasing green products. The productive sector requires assistance to transform its business models and acquire green financial products (meeting technical requirements).

- Objectives and desired results

  - General objective

The results of the diagnosis commented indicate that the Dominican Republic has taken strong steps to move towards climate action and there is a marked interest in working towards a just, green and inclusive transition (GJT) within the national productive and financial apparatus. The country has institutions that have a mandate to work on climate change and production issues with a focus on SMEs, such as: the Ministry of Environment and Natural Resources (MMARN), and the Ministry of Industry, Commerce and SMEs (MICM) with their respective Deputy Ministers and units working with SMEs. In addition, the country has a NDC (Determined Contribution at National Level) with clear ambition, which has acceded to the main international agreements on sustainable development and climate change, works with international cooperation and has developed a climate finance strategy, with a Green Taxonomy implemented.

Within the financial sector, it is noted that there are already entities that have launched green bonds and green financial products. Also, platforms such as Enterprises for the Climate have been developed, which seeks to align the business sector with the commitments set out in the NDC of the Dominican Republic. The banking sector has joined the Green Protocol, which seeks to institutionalize responsible and sustainable financial practices to address climate change challenges. The main business associations, such as CONEP, AIRD and ANJE have developed public actions in favor of climate action.

Although the country has seen significant progress, both the financial sector and the domestic productive sector face major challenges in transitioning to a TJG and mobilizing financial flows to facilitate compliance with its NDC:

- In the financial sector, a major need was identified to build capacities to be able to drive green finance and place green portfolios in the real sector.

- The productive sector faces challenges in understanding and assimilating environmental requirements that must be met when purchasing a green loan. There are sectoral challenges from the clients and also from the staff of the financial institutions themselves to be able to understand, channel and present what concerns environmental permits and authorizations necessary.

- In particular, SMEs lack the capacities and resources to be able to adapt to the technical requirements associated with purchasing green products and providing services under sustainability criteria. The productive sector requires assistance to transform its business models and acquire green financial products (meeting technical requirements).

- It is important to improve the green financial products currently offered to adapt them to the needs of SMEs. This is because the real sector, particularly SMEs, does not perceive tangible benefits for their businesses associated with the supply of green products due to the high rates offered in the market and compliance requirements that represent more bureaucracy and resources for them.

Two examples are given to illustrate these challenges:

Example 1: Those sectors that are under the CBAM (Carbon Boundary Adjustment Mechanism) and who seek to export to the European market, will have to adapt to new technical requirements, such as reporting their emissions and purchasing carbon adjustment certificates. SMEs may face technical and financial challenges in meeting the requirements. It is important to support the priority sectors in their transition process.

Example 2: In discussions with PRODOMINICANA, they reported that an important challenge is the challenges faced by SMEs to understand, comply with and conform to EU-requested environmental, social and governance (ESG) standards. These require support to transform their value chain into a more sustainable and efficient one, and also to be able to meet the EU requirements for being able to export. One case mentioned during the exploratory phase was that of banana exporters to the EU. They often complain about the costs associated with EU compliance, perceiving that they lose profitability for this. It was also reported that many SMEs face challenges to meet the requirements of free zones, because they are often requirements that must comply with ESG regulations and lack the knowledge and skills necessary to meet them.

  - Specific objectives

As part of the proposed work, two intervention components have been identified which are derived from the above diagnosis and will make it possible to strengthen the capacities of the productive and financial sector for a TJG. The two components of intervention are:

Component I: Support SMEs in the transformation of operations and business models for a TJG in the productive sector and in the financial sector with acceleration-advice programmes on green business ideas.

Component II: Strengthening the capacities of the productive and financial sector with green training programmes for financial institutions (multiple banks, savings and loan banks, savings and credit associations and SMEs).

  - Expected results

At the end of the project, it is expected that specific results will be achieved which will have a positive impact on the transition to a more developed green market:

- Identify SMEs with tangible projects that can be banked by potential funders (financial institutions, investment funds and other funders).

- On the other hand, it is hoped that the Financial Institutions of the Dominican Republic will have the opportunity to receive training that will allow them eventually to develop and evaluate green products, expanding the commercial base and market for these products.

- Description of tasks

The project below proposes to incorporate activities that cover the objectives described in Components I and II above.

From Phase 1 to Phase 2, activities will focus on meeting the needs described in Component I. It is proposed to implement technical assistance targeted at a set of SMEs, customers of financial institutions that have already purchased a green product with these entities, or potential non-bank customers. This, to support them through this action with an accompaniment in acceleration or advice of green business models that allow their feasibility and financing, thus facilitating a transition GJT.

Phase 3 focuses on meeting the needs described in Component II. It is proposed to train a set of financial institutions in the Dominican market in the identification, evaluation and approval of green credits.

Kick-off

During this phase the Consulting Firm will work on the Initial Report of the entire project. This report will confirm your understanding of the objectives requested and provide a detailed plan for the implementation of activities. This document will ensure that all parties agree on the technical approach, scope of work and coordination arrangements before moving to the next stages. This first report should summarize the following:

- Understanding of the project and its context

- The Consulting Firm should prepare a clear and structured description of the understanding of the project’s objectives, rationale, expected results and strategic context.

- The economic sectors should be selected to select SMEs that will be part of the training programme. These economic sectors may be transport, water, energy and agriculture, or projects related to the circular economy in any of the above sectors. The Consulting Firm should try to balance the selected sectors.

- The sector prioritisation will be reviewed and approved during the kick-off phase by Expertise France, with additional comments and review by the Technical Committee to be formed for project supervision which will include representatives from the Ministry of Industry, Trade and Mid-SMEs (MICM), the Ministry of Environment and Natural Resources (MMARN)  and/or the Association of Multiple Banks of the Dominican Republic (ABA).

- Detailed work plan and methodology

- The Consulting Firm should describe the overall approach and proposed methodology for the implementation of activities. This includes a clear sequence of proposed key analytical activities and tools and methods.

- A detailed Gantt chart or equivalent showing timelines, milestones and interdependencies shall be provided.

- For illustrative purposes, an informative work plan is presented in paragraph 7 of this document, which may be reviewed, expanded and/or modified at the discretion of the Consulting Company.

- In relation to SME acceleration programmes, the Consulting Firm is expected to produce a work plan which will include at least:

- Understand the status of the projects in question, funding requirement, progress to date,

- Understanding of green products, funders, etc.,

- Coaching in the preparation of presentation material such as pitch deck, investment deck, business plan, impact report, and support material available in a data room for each of the 45 projects.

- Composition and responsibilities of the team

- A full presentation of the consulting company’s team should be included, specifying the roles and responsibilities of each expert (e.g. Project Leader, Senior Green Product Advisor, Senior Green Acceleration Advisor); as well as the additional equipment proposed by the Consulting Company to implement the proposed work.

- Estimated contribution (in person-days) per expert and per phase should be reported.

- Initial stakeholder mapping and participation plan

- Preliminary mapping of key stakeholders, including government agencies, private operators, etc.

Deliverable 1: The Initial Report will be the basis for project implementation. Formal written approval by Expertise France and the Technical Committee, and for all project deliverables, will be a prerequisite before proceeding with subsequent activities.

Phase 1: SME selection and presentation of acceleration-advice methodology

The following activities should be worked on during this phase.

- Preparation of public launch of programme

- An open invitation process should be established for SMEs to apply for the proposed green programme, according to the sectors selected and agreed in the Kick-off phase.

- Selected SMEs may be clients of Financial Institutions. It may be coordinated with the Association of Banks (ABA), so that through this association, a sample of SMEs per financial institution can be invited. To this end, it is possible to coordinate privately with the ABA and to issue a public invitation through networks for SMEs which are clients of financial institutions. On the other hand, the consulting firm may invite non-bank-based SMEs, for which it must establish a selection methodology and communication process in public networks.

- The project launch should have two parts. The first one where companies are invited to present their case, and the second where the Consulting Company selects a sample of companies to carry out the acceleration-advice of SMEs.

- For the first part, the consultant must work on the initial application forms and criteria following the guidelines established by EF and the Technical Committee, and in coordination with them.

- For the second part, once applications have been received, the Consulting Company should propose selection criteria to select 45 companies that will be accelerated-advised by the programme, for which work should be done on defining the selection criteria of these SMEs.

- For the initial invitation and selection of the 45 SMEs, it should be taken into account that some will be SMEs with more developed projects and therefore with debt-type financing needs, while for early life projects, the financing required will most likely be of the VC type.

- The financing needs of SMEs are expected to be related to energy saving innovations, clean energy production, organic waste management; in general, any sustainable production project; circular economy and/or sustainability associated with the use of resources. The objective of the financing sought may be to:

  - implement a green solution in the company’s operation,

  - present the development of a new project aimed at providing services to its end customers to mitigate the effects of climate change.

- For the invitation of SMEs and selection of these, you must have agreed and approved sectors in the kick-off stage, and should consider the definition of Small and Medium Enterprise in the Dominican Republic: Small Business (have 11 to 50 employees and their annual gross sales are up to RD$61,553,187), Medium-sized company (have 51 to 150 employees and their annual gross sales do not exceed RD$230,254,516).

- The entire program should be based on national standards of the Dominican Republic and international EU, permissiology, use of green taxonomies and others for the definition of internationally acceptable green products. The consultant must carry out a preliminary investigation to cover these requirements in all activities to be developed in the project.

- Note: it is important that exporting companies are invited to trade or have high potential to trade with the European Union, and produce materials under the sectors established in CBAM, or must comply with EU requirements.

- Presentation of the acceleration-advice methodology to SMEs

- During this stage of the project, the consulting firm presents a methodology for stages, defined by the consulting firm, in the process of acceleration-advice.

- The proposal should be differentiated according to the type of project, it may be acceleration (for projects that are just starting) or more business advice for existing projects or further development.

- For acceleration projects, it is understood that the financing to be sought is related to risk capital in pre-seed or seed stages, while for existing or more developed projects it is likely to be debt.

- The proposal must begin with a preliminary diagnosis of the status of the projects under consideration and their financing needs.

- The work of the Consulting Company should focus on coaching and follow-up to companies for the achievement of the goals set and preparation of their documents. This should be done by setting up an advisor/team of advisors, who will set up customised working hours for contact, follow-up and review of the material proposed per firm, based on a set of individual hours of proactive coaching for each phase per firm, and groups where appropriate.

- The methodology should consider local standards of the Dominican Republic, international EU, percolology, use of green taxonomies and others, for the definition of internationally acceptable green products, as well as compliance with environmental obligations under existing national legislation.

Deliverable 2: Report presenting the application/selection criteria (1a) and the acceleration–advisory methodology (1b).

Phase 2: Implementation of acceleration-advice and matchmaking events

The following activities should be worked on during this phase of the project.

- Invitation to SMEs to participate

- Based on the established criteria for applications, the call is launched according to the Work Plan.

- The Consulting Company shall manage the process of sending invitations, receiving responses and applications.

- Selection of SMEs selected for acceleration -advice

- Using the approved selection processes and qualification criteria, the Consulting Company will select and communicate to the 45 SMEs that will continue in the acceleration-advice process.

Deliverable 3: Summary report of all applications received (2a) and list of pre-selected SMEs (2b).

- Implementation of acceleration process -advice

- At this stage of the consultancy, the Consulting Company will have to implement the personalised consultancy for the acceleration-consultancy of the selected SMEs.

- As discussed above, the Consulting Company is expected to execute among others, suggested by the Consulting Company, a work plan for i) understanding its status, funding requirement, progress to date, ii) understanding of green products, financiers, and identification of environmental obligations at the permisological level, etc., iii) preparation of presentation material such as pitch deck, investment deck, business plan, impact report, and supporting material available in a data room for each of the 45 projects.

- Once the SMEs have their first versions, the Consulting Firm should review and recommend improvements. With these improvements, the Consulting Company must obtain final versions of a minimum information package to be held by each company and additional support, incorporating the requested modifications (data room).

- Also, work should be done on pitch deck training sessions to a private sample of investors (financial institutions, investment funds, other investors).

- Key personnel of the SMEs in the sample should be trained to improve their preparation processes for applying for green financing at financial institutions based on the gap identified.

- Organization of SME matchmaking event with investors

- To carry out the matchmaking, the Consulting Company should prepare a list of potential investors interested in evaluating these projects (financial institutions, investment funds, others; depending on the type of debt-equity financing required, early stage or mature project life stage, amount of financing and availability of financial products). Some of the invited investors may include the European Investment Bank, AFD, Proparco, etc.

- While it is expected that Financial Institutions will be invited, the Consulting Company should evaluate the incorporation of other investors interested in early-stage companies such as VC investment funds, impact funds, etc.

- The Consulting Company should work on the logistical preparation of the event.

- Invitations are sent out to potential investors with details of their participation.

Deliverable 4: Three periodic activity-tracking reports (2c, 2d), according to the work plan.

Deliverable 5: Final information packages for each selected company, including: i) business pitch deck; ii) business investment deck detailing the business strategy based on the proposed green innovation and the requested requirements; iii) quantification of environmental impact; iv data room.

Deliverable 6: After the matchmaking process, a final report summarizing investor interest in each company (type of instrument, amount of financing, availability, etc.).

Phase 3: Implementation of training programme in financial institutions

- Preparation of the training programme for financial institutions

- Work should be done on developing a training programme to meet the needs of the financial sector for green credit.

- As a first task, the methodology and structure of the proposed training programme should be presented. The objective of this training will be for Financial Institutions to understand about green financing, local and EU requirements, Green Taxonomies, including for the provision of funding and the use of methodologies to assess green credits and green credit allocations.

- These workshops must be given to selected teams from each of the existing financial institutions, the invitation must be pre-selected with the ABA (there are 18 Multiple Banks, 14 Savings and Credit Banks, 3 Credit Corporations, 10 Savings and Loan Associations, and 2 Public Entities, total 47 entities).

- For example, a group of about 3 people per Financial Institution could be invited, which would make a total of about 150 people. Depending on the size of the workshop proposed by the consulting company, for the face-to-face training stage, the group could be divided into 2, thus giving 2 workshops separately (in addition to the virtual training process that is proposed).

- The Consulting Company should consider for the development of training, that part of the companies to be evaluated by financial institutions are exporting companies that market or have high potential to trade with the EU, and producing materials under the sectors established in CBAM, or must meet EU requirements.

- For this diagnosis, the current process used by financial institutions for the assessment and granting of green credits ("as it is") should be identified. On the other hand, the consultant should present the green credit assessment process under international and local best practices ("as it should be").

- Preparation and presentation of training materials

- The proposed methodology will involve the preparation of training material: reports, reports, presentations, case studies, etc.

- The training scheme should be detailed and proposed. This is expected to be material that could be dictated in a virtual and/or face-to-face space. As an example, the work plan proposes a virtual phase and a face-to-face phase. The training presentation scheme should be proposed by the consulting company, detailing whether there is a virtual and/or face-to-face stage and how many days will be required for each stage.

- All training material should be free of ownership, and delivered to counterparts for internal/replication use.

Deliverable 7: Report including: i) the methodology and structure of the proposed training program (activity 3a); ii) the primary materials and supporting materials for the training (3b).

- Development of the training programme

- Based on the training programme and proposed work and implementation plan, the planned training should be carried out. Workshops should include presentation of training material, assessment tools, minimum required KPIs, etc., that allow financial institutions to train themselves to assess and grant green credits.

- Take into account that, within the group of participants in the training programme, a group of persons representing the Ministry of Environment and Natural Resources and other agencies will be invited additionally; this will be communicated in due course.

Deliverable 8: Training program report, including attendance list, workshop summaries, results achieved, lessons learned, etc.

Deliverable 9: Final report of the technical assistance “EU-Proverde: SME Acceleration and Capacity Building for Financial Institutions in Green Project Evaluation,” including results achieved, lessons learned, and best practices.

- Roadmap for a green, fair and inclusive transition for the Dominican Republic

- Based on the project development and lessons learned "EU-Proverde, acceleration of SMEs and training of Financial Institutions in green project evaluation", the Consulting Company is requested to prepare a Roadmap for a green, fair and inclusive transition for the Dominican Republic.

- This Roadmap should serve as a basis for a "Policy Brief" that will help to define the strategy of the Dominican Republic in the green transition proposed from the approach set out in the project, for the financial sector and for the minimum environmental considerations that the Dominican Republic must take into account in implementing this green, fair and inclusive Transition Route.

Deliverable 10: Roadmap for a green, just and inclusive transition for the Dominican Republic, including recommendations on financial and environmental aspects ( basis for a “Policy Brief”).

- Planned deliveries

| Phase | Deliverables* | Intended format | Proposed completion date |
| --- | --- | --- | --- |
| Kick-off: | Deliverable 1: Presentation of the initial report. | - The Initial Report will serve as a basis for project implementation. | Week 2 from the Kick off Meeting (KoM) |
| Phase 1: | Deliverable 2: Report presenting the application/selection criteria (1a) and the acceleration–advisory methodology (1b). | - Presentation of a report defining the mechanisms for inviting SME companies to submit their initial applications (application forms) and the selection criteria for the 45 SMEs to be invited to the program. - Presentation of the acceleration–advisory methodology, differentiated for newly initiated projects and for existing or mature projects. | Week 8 from the KoM |
| Phase 2: | Deliverable 3: Summary report of all applications received (2a) and list of pre-selected SMEs (2b). | - Invitations sent to SMEs and receipt of applications. - Report presenting the list of selected SMEs based on the established criteria and the ranking of companies. | Week 20 from the KoM |  |
|  | Deliverable 4: Periodic activity-tracking reports (2c, 2d). | - The report must detail the tasks carried out in each phase to implement the acceleration–advisory processes, the results obtained, etc.. | Weeks 28, 37, 44 from the KoM |
|  | Deliverable 5: Materials prepared by the SMEs. | - Final decks and supporting information (data room) for each selected company, including: i) the business pitch deck; ii) the business investment deck detailing the business strategy based on the proposed green innovation and the requested requirements; iii) quantification of environmental impact. | Week 48 from the KoM. |
|  | Deliverable 6: Matchmaking event execution. | - Final event report (including attendance list, photos, etc.) summarizing investor interest in each company (type of instrument, amount of financing, availability, etc.) | Week 48 from the KoM |
| Phase 3: | Deliverable 7: Presentation of the methodology and structure of the proposed training program for Financial Institutions, along with the primary training materials and supporting materials. | - Presentation of the methodology and structure of the proposed training program for Financial Institutions. - Delivery of training materials, including academic content, tools, case studies, etc. | Week 15 from the KoM |
|  | Deliverable 8: Report on the training workshops delivered. | - Final report of the training phase summarizing the offline activities and training workshops, if applicable, including attendance list, workshop summaries, results achieved, lessons learned, etc.. | Week 29 from the KoM |
|  | Deliverable 9: Final report of the entire project. | - That reflects lessons learned and best practices for the future implementation of the program in a second version. | Week 51 from the KoM |
|  | Deliverable 10: Policy Brief on the Roadmap for a Green, Just, and Inclusive Transition for the Dominican Republic. | - Defines the Dominican Republic’s strategy for the proposed green transition from the project’s perspective, covering both the financial sector and the minimum environmental considerations.. | Week 51 from the KoM |

* The approval of each deliverable will be formally and in writing by Expertise France, with the support of the Technical Committee that is set up to monitor this project, which will include representatives from the Ministry of the Environment and Natural Resources.

The service provider will include a tight work schedule in its proposal: time optimization to deliver expected reports is welcome.

Deliverables and supporting information (e.g. questionnaire, surveys) must be submitted in digital format and independently on the agreed delivery date. The service provider will provide all products according to the agreed schedule. Please note:

- The service provider cannot prejudge the validation of products: it is necessarily carried out by a written approval (e-mail) of the responsible for the Euroclima project when each deliverable is considered satisfactory.

- Both the Euroclima team, in consultation with the national technical focal point, and the contractor will do their utmost to ensure that the results are validated as soon as possible.

- Coordination and contacts

The service provider shall designate a single contact person for the implementation of the project.

Expertise France’s contact person will be:

Orion VIENNE, Euroclima project officer, will be the main contact person for the service provider for Expertise France

E-mail: orion.vienne@expertisefrance.fr

Cc: Anne-Laure DUBILLY, Programme Manager

E-mail: anne-laure.dubilly@expertisefrance.fr

The national focal point of Euroclima will receive a copy of the key coordination emails and will be informed by the service provider about progress made and difficulties encountered, as appropriate.

The contact persons, as indicative, for the Ministry of Environment and Natural Resources are :

Ivan M. Cruz Burgos

Director of Financial Mechanisms and Portfolio Management

E-mail: ivan.cruz@ambiente.gob.do

Cc: Melisa María Guzman Bencosme - meguzman@ambiente.gob.do

Cc: Oscar Eduardo Polanco Reynoso - oscar.polanco@ambiente.gob.do

Gabriela C. Márquez

Director of Climate Change Mitigation and Adaptation

E-mail: Gabriela.Marquez@ambiente.gob.do

CC: Lisandra Rodriguez, Lisandra.Rodriguez@ambiente.gob.do

Cc: Georgina Canario Féliz, Georgina.Canario@environmente.gob.do

One kick-off meeting shall be held no later than 15 days after the contract award has been notified. The meeting will bring together relevant representatives. There should be close collaboration with all stakeholders from the preparation of the task to its completion. Regular exchanges should also take place on the progress of the mission and any difficulties that may arise. Any change in contact shall be notified by the party concerned to the others.

- Work plan, location and duration

Work Plan: The service provider will provide a detailed work plan in its technical proposal. Any modification of the provisional agenda shall be duly justified. The previous page details an informative work plan that may be modified at the best of the Consulting Company’s knowledge. Consider the time required for EF to review and approve deliverables.

Mission site: work will be carried out remotely and in person. The consultant should propose in his work plan the mix of remote and face-to-face work that he considers appropriate according to the activities to be carried out.

Estimated implementation period: April 2026 to May 2027.

Effective duration per assignment: 14 months.

- Required experience and profile

Business experience - Consortium with local or regional expertise and knowledge of the business context in the Dominican Republic and the Caribbean. Proposals have credentials that support previous experience with local or regional expertise, or with financial institutions in consulting, acceleration or previous projects in credit assessment for green products and acceleration of companies. The company has a strong track record of relevant cases and commitments in the past.

A gender balance in the composition of the team will be positively appreciated. All team members must have a good command of the written and oral expression of the Spanish language. The Consultant must respect the composition of the team as specified and cannot make any changes without prior approval from Expertise France.

The minimum required profiles are:

Project Manager

- At least 10 years of experience leading consulting projects in the financial sector.

- Experience working on at least 3 projects in Latam Banks including financial design of products and at least one acceleration project.

- Project work experience in the Dominican Republic.

- Experience leading at least 3 consulting projects related to green products creation in banks under EU standards.

Senior Advisor green products

- At least 7 years of experience leading consulting projects in the financial sector.

- Experience working on at least 3 training projects and/or product creation in Latam Banks.

- Experience in green product development, financial regulation, understanding of the business sector, etc.

Senior Green Acceleration Advisor

- At least 7 years of experience leading acceleration projects.

- Experience working on at least 3 green project acceleration projects.

- Practical information

- Language of assignment: Spanish.

- The technical proposal submitted by the Consulting Firm cannot exceed 30 pages, excluding annexes.

- All travel will be provided by the service provider and included as part of the financial proposal. Experts remain solely responsible for organising their own travel, accommodation, transport, insurance, communications and internet costs.

- The Government of the Dominican Republic will facilitate meetings with stakeholders as appropriate.

- The Government of the Dominican Republic will assist with documentation necessary to enter and work in the Dominican Republic.

- During the implementation of the mission, the visibility of the European Union as a donor to the Euroclima programme should be ensured in accordance with the communication and visibility rules of the Euroclima programme, take into account the European Union’s requirements for communication and visibility: https://international-partnershi.ec.europa.eu/knowledge-hub/communicating-and-raising-eu-visibility-guidance-external-actions_en. All reports and submissions must include the emblem of the European Union (with the words "Financed by the European Union"), the logos of the Euroclima programme and of Expertise France, the logos of the Ministry of Environment and Natural Resources of the Dominican Republic, as well as the following "disclaimer": "This publication has been produced with financial support from the European Union. The contents are the sole responsibility of <name of author/partner> and do not necessarily reflect the views of the European Union or the Ministry of Environment and Natural Resources of the Dominican Republic"

At the time of writing, the sectors covered by CBAM were: cement, iron and steel, aluminium, fertilizers, electricity and hydrogen. These sectors were selected for their high emission intensity and the high risk of production relocation to countries with less stringent climate regulations.