## ESP
Actividades |  |  |  | 2026-04-01 |  |  |  | 2026-05-01 |  |  |  | 2026-06-01 |  |  |  | 2026-07-01 |  |  | 2026-08-01 |  |  |  | 2026-09-01 |  |  |  | 2026-10-01 |  |  |  | 2026-11-01 |  |  |  | 2026-12-01 |  |  |  | 2027-01-01 |  |  |  | 2027-02-01 |  |  |  | 2027-03-01 |  |  |  | 2027-04-01 |  |  |  | 2027-05-01
Semanas
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55
kick-Off
| a) | Reunión inicial kick-off con equipo consultor
| b) | Revisión de tareas y presentación del plan de trabajo
Entregable 1: Presentación de Informe Inicial | bar: Semanas 2
EF revisión y aceptación (2 semanas min) | bar: Semanas 3 to Semanas 4
Fase 1: Selección de PYMEs y presentación de metodología de aceleración-asesoramiento
| a) | Preparación de lanzamiento público del programa de aceleración-asesoramiento
Definición de criterios de selección para primer filtro ~ 45 empresas PYMEs/proyectos aprox.
Preparación de mecanismo de invitación a empresas
| b) | Presentación de metodología de aceleración-asesoramiento
Propuesta de metodología de aceleración-asesoramiento por etapas
Entregable 2: Informe presentando los criterios de postulación / selección (1a) y metodología aceleración-asesoramiento (1b) | bar: Semanas 8
EF revisión y aceptación (2 semanas min) | bar: Semanas 9 to Semanas 10
Fase 2: Implementación de aceleración-asesoramiento y eventos de matchmaking
| a) | Invitación de PYMEs a participar
Invitación a PYMEs y aceptación de participación en el programa
| b) | Selección de PYMEs para programa de Aceleración-Asesoramiento
Sistema de selección según criterios pre establecidos
Entregable 3: Informe resumen de todas las postulaciones recibidas (2a) y lista de PYMES pre-seleccionadas (2b) | bar: Semanas 20
EF revisión y aceptación (2 semanas min) | bar: Semanas 21 to Semanas 22
| c) | Implementación proceso de aceleración-asesoramiento
Implementación de asesoría para desarrollo de plan de pitch deck, plan de negocios, investment deck, etc.
Presentación de deck final e información de soporte (data room) - evaluación inicial
Sesiones de entrenamiento de presentación de pitch deck a muestra privada de inversionistas
Presentación de versión final de documentos con comentarios alcanzados
| d) | Organización de evento de matchmaking para presentación de casos a potenciales inversionistas - evento abierto
Preparación del evento invitación de inversionistas participantes
Invitaciones enviadas a inversiones, empresas finales, aceptadas - matchmaking
Entregable 4: Informes periódicos de seguimiento de actividad (2c, 2d) | bar: Semanas 28; Semanas 37; Semanas 44
EF revisión y aceptación (2 semanas min) | bar: Semanas 29 to Semanas 30; Semanas 38 to Semanas 39; Semanas 45 to Semanas 46
Entregable 5: Decks finales e información de soporte (data-room) por cada empresa seleccionada que incluya: i) pitch deck del negocio, ii) investment deck del negocio detallando la estrategia del negocio en base a la innovación verde propuesta, y requerimientos solicitados, iv) cuantificación del impacto ambiental, v) data room | bar: Semanas 48
Entregable 6: Informe final del evento ( incluyendo lista de participación, fotos, etc.) que resuma interés de inversionistas por cada empresa (tipo de instrumento, cantidad de financiamiento, disponibilidad, etc.) | bar: Semanas 48
EF revisión y aceptación (2 semanas min) | bar: Semanas 49 to Semanas 50
Fase 3: Implementación de programas de capacitación en entidades financieras y cierre de la AT EU-Proverde
| a) | Preparación del programa de capacitación para entidades financieras
Presentación de metodología y estructura del programa de capacitación propuesto
| b) | Preparación y presentación de material de capacitación
Preparación de material de capacitación: informes, reportes, presentaciones, casos, etc.
Entregable 7: Informe incluyendo: i) La metodología y la estructura del programa propuesto de capacitación (actividad 3a), ii) Los materiales primarios y material de soporte para la capacitación (3b) | bar: Semanas 15
EF revisión y aceptación (2 semanas min) | bar: Semanas 16 to Semanas 17
| c) | Desarrollo del programa de capacitación
Selección de empresas financieras a invitar, envío y confirmación de invitados
Desarrollo de programa de capacitación off-line/in-situ
Entregable 8: Informe del programa de capacitación, incluyendo lista de presencia, resumen de los talleres, resultados obtenidos, lecciones aprendidas, etc. | bar: Semanas 29
EF revisión y aceptación (2 semanas min) | bar: Semanas 30 to Semanas 31
Entregable 9: Reporte final de la Asistencia técnica “EU-Proverde, aceleración de PYMES y capacitación de Entidades Financieras en evaluación de proyectos verdes” incluyendo resultados obtenidos, lecciones aprendidas y buenas prácticas | bar: Semanas 51
EF revisión y aceptación (2 semanas min) | bar: Semanas 52 to Semanas 53
Entregable 10: Hoja de Ruta de Transición Verde, justa e inclusiva para República Dominicana, incluyendo recomendaciones sobre los aspectos Financieros y Ambientales (base para un “Policy Brief”) | bar: Semanas 51
EF revisión y aceptación (2 semanas min) | bar: Semanas 52 to Semanas 53
Entregable
Revisión y aprobación EF
Trabajo en campo

## ENG
Activities |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10 |  |  |  | Month 11 |  |  |  | Month 12 |  |  |  | Month 13 |  |  |  | Month 14
Weeks
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55
kick-Off
| a) | Reunión inicial kick-off con equipo consultor
| b) | Review of tasks and presentation of the work plan
Deliverable 1: Presentation of initial report | bar: Weeks 2
EF review and approval (minimum 2 weeks) | bar: Weeks 3 to Weeks 4
Phase 1: SME selection and presentation of acceleration-advice methodology
| a) | Preparation for the public launch of the acceleration–advisory program
Definition of selection criteria for the first screening ~ approximately 45 SMEs/projects
Preparation of the invitation mechanism for companies
| b) | Presentation of the acceleration–advisory methodology
Proposal of a staged acceleration–advisory methodology
Deliverable 2: Report presenting the application/selection criteria (1a) and the acceleration–advisory methodology (1b) | bar: Weeks 8
EF review and approval (minimum 2 weeks) | bar: Weeks 9 to Weeks 10
Phase 2: Implementation of acceleration-advice and matchmaking events
| a) | Invitation of SMEs to participate
Invitation to SMEs and acceptance of participation in the program
| b) | Selection of SMEs for the Acceleration–Advisory program
Selection system based on pre-established criteria
Deliverable 3: Summary report of all applications received (2a) and list of pre-selected SMEs (2b) | bar: Weeks 20
EF review and approval (minimum 2 weeks) | bar: Weeks 21 to Weeks 22
| c) | Implementation of the acceleration–advisory process
Implementation of advisory support for the development of the pitch deck, business plan, investment deck, etc.
Presentation of the final deck and supporting information (data room) – initial evaluation
Pitch-deck presentation training sessions with a private sample of investors
Presentation of the final version of documents incorporating received comments
| d) | Organization of a matchmaking event for presenting cases to potential investors – open event
Preparation of the event and invitation of participating investors
Invitations sent to investors and selected companies, confirmations received – matchmaking
Deliverable 4: Three periodic activity-tracking reports (2c, 2d), according to the work plan | bar: Weeks 28; Weeks 37; Weeks 44
EF review and approval (minimum 2 weeks) | bar: Weeks 29 to Weeks 30; Weeks 38 to Weeks 39; Weeks 45 to Weeks 46
Deliverable 5: Final information packages for each selected company, including: i) business pitch deck; ii) business investment deck detailing the business strategy based on the proposed green innovation and the requested requirements; iii) quantification of environmental impact; iv data room | bar: Weeks 48
Deliverable 6: After the matchmaking process, a final report summarizing investor interest in each company (type of instrument, amount of financing, availability, etc.) | bar: Weeks 48
EF review and approval (minimum 2 weeks) | bar: Weeks 49 to Weeks 50
Fase 3: Implementation of training programmes in financial institutions and closing of the AT EU-Proverde project
| a) | Preparation of the training program for financial institutions
Presentation of the proposed training program methodology and structure
| b) | Preparation and delivery of training materials
Preparation of training materials: reports, briefs, presentations, cases, etc.
Deliverable 7: Report including: i) the methodology and structure of the proposed training program (activity 3a); ii) the primary materials and supporting materials for the training (3b) | bar: Weeks 15
EF review and approval (minimum 2 weeks) | bar: Weeks 16 to Weeks 17
| c) | Development of the training program
Selection of financial institutions to invite, sending of invitations, and confirmation of participants
Implementation of the training program off-line/on-site
Deliverable 8: Training program report, including attendance list, workshop summaries, results achieved, lessons learned, etc. | bar: Weeks 29
EF review and approval (minimum 2 weeks) | bar: Weeks 30 to Weeks 31
Deliverable 9: Final report of the technical assistance “EU-Proverde: SME Acceleration and Capacity Building for Financial Institutions in Green Project Evaluation,” including results achieved, lessons learned, and best practices | bar: Weeks 51
EF review and approval (minimum 2 weeks) | bar: Weeks 52 to Weeks 53
Deliverable 10: Roadmap for a green, just, and inclusive transition for the Dominican Republic, including recommendations on financial and environmental aspects (as the basis for a “Policy Brief”) | bar: Weeks 51
EF review and approval (minimum 2 weeks) | bar: Weeks 52 to Weeks 53
[5 empty] | Entregable | [7 empty] | Revisión y aprobación EF | [10 empty] | Trabajo en campo