TERMS OF REFERENCE

- General information

| Assignment name | Provision of a capacity-building programme to selected Business Support Organizations (BSOs) under the FEF+ AI Mediterranean project, including delivery of an AI Diagnostic Toolkit, AI Support Playbook, tailored trainings, mobilisation of an AI expert network, a knowledge-sharing platform, and a study visit in France. |
| --- | --- |
| Beneficiary | Expertise France |
| Countries | Algeria, Egypt, Lebanon, Morocco, Tunisia (Primarily remote programme, with an in-person study visit in France and optional punctual in-person sessions in-country if validated by Expertise France.) |
| Total estimated | Up to a total maximum EUR 100,000 (incl. VAT) (through purchase orders), over a period of 6 months. |

- Context and justification of the need

2.1 EXPERTISE FRANCE

Expertise France (www.expertisefrance.fr) is the public agency for international technical cooperation. The agency addresses the technical assistance needs of partner countries in the main fields of public action: democratic and financial governance, security, sustainable development, and human development. Through its action in the field, it contributes to the objectives of solidarity and influence of French and European development policy.

With a turnover of 390 million euros, Expertise France (EF) operates in 147 countries and manages more than 350 projects. Expertise France has more than 450 employees at its Paris headquarters and more than 600 partners worldwide.

2.2 The FEF+ AI Mediterranean project (FEF)

The FEF+ AI Mediterranean project aims to position the Southern Mediterranean as a strategic AI hub by structuring a dynamic and integrated ecosystem across Algeria, Egypt, Lebanon, Morocco and Tunisia. The project adopts a systemic approach that combines capacity building for Business Support Organizations (BSOs), targeted support to high-potential AI startups, mobilisation of a regional expert continuum, and the strengthening of Euro-Mediterranean cooperation through strategic dialogue and flagship events such as the Mediterranean AI Forum.

A regional needs assessment conducted in 2025 by the project team highlighted structural and recurrent gaps among BSOs supporting AI ventures. While many incubators and accelerators have solid experience in digital entrepreneurship, they remain insufficiently equipped to support AI-native startups. Key challenges identified include limited internal AI expertise to assess technical robustness, detect “AI-washing”, or guide startups through complex data pipelines and model deployment phases. BSOs also lack AI-specific diagnostic tools and structured methodologies adapted to machine learning lifecycle management, data governance, MLOps, and AI risk assessment.

In addition, access to specialised AI experts remains fragmented and uneven across countries, reducing the ability of BSOs to provide high-level technical mentorship. The study also revealed weak coordination between BSOs at regional level, leading to duplication of efforts, limited knowledge sharing, and missed opportunities for joint positioning toward investors and international partners. Finally, many BSOs have not yet integrated AI into their own operational processes (startup screening, monitoring, reporting, mentor matching, impact measurement), which limits their efficiency and credibility when supporting AI-driven ventures.

To address these challenges, Expertise France will select one BSO per country and deploy a structured capacity-building and peer-learning programme. This programme will provide AI-specific tools (Diagnostic Toolkit and Support Playbook), tailored training and coaching, structured access to an AI expert network, and a regional knowledge-sharing mechanism. It will also foster peer exchanges between BSOs and organise a study visit in France, strengthening exposure to international best practices.

Through this targeted intervention, the project seeks to professionalise and standardise AI-focused support services, reinforce regional cooperation, and ultimately improve the technological maturity, scalability and investment readiness of AI startups across the Mediterranean.

- Objectives and desired results

  - General objective

The objective of this assignment is to strengthen the institutional, technical and strategic capacities of five selected Business Support Organizations (BSOs) — one per country — in order to improve the quality and impact of AI startup support across Algeria, Egypt, Lebanon, Morocco and Tunisia.

The intervention aims not only to upgrade technical competencies, but also to structure a regional community of practice, professionalise AI-focused incubation models, and foster sustainable Euro-Mediterranean collaboration.

  - Specific objectives

The service provider shall implement a structured and phased intervention covering the following objectives:

### Conduct a structured needs assessment per BSO

- Assess the current AI support maturity of each BSO (methodologies, tools, internal skills, governance, partnerships, access to experts).

- Analyse current startup selection processes and identify risks of AI-washing or technical mis-evaluation.

- Evaluate the BSO’s ability to assess data preparation and governance, data pipeline orchestration, model robustness and monitoring, MLOps maturity, infrastructure scalability adapted to local constraints and AI-related risks (bias, compliance, cybersecurity).

- Evaluate the BSO's ability to assess AI-specific business dimensions, including compute infrastructure costs, barriers to replication and alignment with investor expectations.

- Evaluate the BSO's ability to assess AI team and organizational capacity, including AI-specific roles and competencies, team structure, skill gaps and clear ownership for data quality and model maintenance.

- Identify gaps in expert access, compute access, regulatory understanding and investor dialogue.

- Define priority capacity-building areas aligned with both national ecosystem realities and regional objectives.

### 2. Design and implement a tailored AI capacity-building programme

The service provider shall design a blended programme combining collective learning, individual coaching and peer exchange.

The programme must:

- Be adapted to country-specific contexts (language, ecosystem maturity, regulatory environment).

- Combine technical and operational dimensions of AI venture support.

- Include practical tools and templates directly usable by BSOs.

- Strengthen both AI startup support capacity and internal AI adoption.

### 3. Develop and deploy an AI Diagnostic Toolkit

The AI Diagnostic Toolkit shall be a structured and operational set of tools enabling BSOs to evaluate AI startups rigorously and consistently.

It shall include:

- Data preparation and governance, data pipelines orchestration assessment grids.

- Model evaluation template (performance, robustness, scalability, monitoring and drift detection capability).

- MLOps and infrastructure maturity assessment (continuous integration/deployment, infrastructure scalability adapted to local constraints)

- AI team and organizational capacity assessment (AI-specific roles and competencies, team size and structure, skill gaps, clear ownership for data quality and model maintenance)

- AI risk assessment grid (bias, data and AI compliance, cybersecurity exposure).

- AI due diligence assessment (technical maturity and AI-specific business dimensions, e.g., compute infrastructure costs, barriers to replication, alignment with investor expectations…)

- AI-readiness scoring framework to reduce “AI-washing” risk.

The toolkit must be simple enough for operational use, yet technically robust, and adapted to Mediterranean ecosystem realities (compute constraints, regulatory fragmentation, data access limitations).

### 4. Develop and deploy an AI Support Playbook

The AI Support Playbook shall serve as a structured operational manual for AI-focused incubation and acceleration programmes.

It shall include:

- Guidelines for integrating AI-specific modules into incubation programmes.

- Recommended mentoring pathways for AI startups (data preparation → model development → MLOps → deployment → model monitoring → scaling)

- Best practices for AI-specific economic evaluation (compute infrastructure cost analysis, cost-per-inference tracking, pricing models, identification of competitive advantages and algorithmic innovation).

- Guidance on AI team and organizational capacity assessment.

- Responsible AI and compliance guidance (data governance, ethics, local and international regulations awareness including AI Act).

- Templates for AI programme structuring (bootcamps, demo days, technical reviews).

- Suggested KPIs for AI startup monitoring and impact measurement (technical metrics model performance, drift… and AI-specific business metrics : compute costs, cost per inference…)."

The Playbook must be operationalised within each selected BSO and not remain theoretical.

### 5. Mobilise and structure access to an AI expert network

The service provider shall:

- Identify and formalise a roster of AI experts (technical, MLOps, data governance, responsible AI, cybersecurity, AI productisation). Particular attention will be paid to inclusiveness and diversity in the composition of the expert roster.

- Define access and referral mechanisms for BSOs.

- Clarify engagement modalities (office hours, technical review sessions, due diligence support).

- Ensure regional balance and linguistic accessibility.

The expert network shall reinforce BSOs’ technical credibility vis-à-vis startups and investors.

### 6. Facilitate structured peer learning and establish a shared knowledge-sharing mechanism

The service provider shall design and animate a structured regional peer-learning framework connecting the five selected BSOs, with the objective of fostering continuous exchange, mutual learning and progressive harmonisation of AI incubation standards across countries.

This shall include:

- Organisation of regular regional peer-learning sessions (online or hybrid);

- Facilitation of thematic exchanges (AI evaluation methodologies, investor dialogue, compute access, regulatory interpretation, impact measurement, etc.);

- Documentation and consolidation of lessons learned and emerging good practices;

- Progressive alignment of diagnostic and support standards across participating BSOs;
Establishment of a lightweight but structured knowledge-sharing system, including:

  - A shared repository of tools, templates and resources;

  - Documented case studies and practical examples;

  - Access to recorded sessions and pedagogical materials;

  - Structured communication channels enabling continuous interaction.

### 7. Design and coordinate a study visit in France

Coordinate and technically design a 3–5 day study visit in France for the selected BSO representatives (up to 10–12 participants), in order to connect them with leading AI innovation hubs, incubators, accelerators, research institutions, investors and corporate stakeholders.

This shall include engagement with key AI ecosystem actors and institutions relevant to the programme’s objectives. The service provider shall identify and facilitate meetings with selected stakeholders, ensuring full alignment with the capacity-building objectives and the AI support professionalisation framework developed under this assignment.

The service provider shall prepare and provide supporting pedagogical and methodological materials for participants, including clear learning objectives, structured visit logic and tools for knowledge capture.

Deliverables:

- Study visit agenda and Technical dossier;

- Pre-visit briefing kit and post-visit learning report.

(Note: Logistics and travel arrangements will be managed by Expertise France.)

### 9. Support integration of AI into BSO internal processes

Based on the needs assessment findings, the programme shall include practical guidance on:

- AI-assisted startup screening and evaluation workflows.

- AI-based monitoring dashboards.

- Mentor matching optimisation tools.

- Automated reporting support.

- Knowledge management improvement.

- Responsible and frugal AI adoption internally.

Each BSO shall produce a short internal AI adoption roadmap.

  - Anticipated results

- Five comprehensive diagnostic reports will have been produced, providing a structured assessment of each BSO’s AI maturity, technical gaps, operational weaknesses and priority capacity-building areas.

- A validated and operational AI Diagnostic Toolkit will have been developed and adopted by the five selected BSOs, enabling them to: assess AI technical maturity (data pipelines orchestration, model monitoring, MLOps, infrastructure, local adaptation); assess AI team and organizational capacity; assess AI-specific business dimensions (compute costs, barriers to replication); identify AI-related risks (bias, compliance, cybersecurity); conduct AI due diligence; reduce AI-washing through structured scoring.

- A structured AI Support Playbook will have been finalised and operationalised within each selected BSO, providing: AI-specific modules; mentoring pathways (technical and business AI-specific); best practices for AI economic evaluation (compute costs, pricing); AI team capacity guidance; responsible AI and compliance guidance; programme structuring templates; comprehensive KPI framework for AI startup monitoring and impact measurement ; AI-readiness scoring methodology.

- A formalised AI expert network roster will be operational, with clear referral and engagement mechanisms enabling BSOs to access technical reviews, due diligence support and specialised mentoring.

- A functioning regional community of practice will be established, including: Regular peer-learning sessions; Thematic exchanges on AI evaluation, compute, regulation and investor dialogue; A shared repository of tools, templates and resources; Documented case studies and session materials.

- A structured knowledge-sharing mechanism will be in place and accessible to all selected BSOs.

- A technically designed and fully prepared study visit to France, including a validated visit agenda, identified and confirmed meetings with relevant AI ecosystem stakeholders, a comprehensive technical dossier, a pre-visit briefing kit and a structured post-visit learning report template.

- Each BSO will produce a short internal AI adoption roadmap, identifying priority AI integration actions for their own operational processes.

- Description of the assignment

  - Planned activities

The proposed service provider (individual entity or consortium) shall specify in its technical offer a detailed proposal for the AI-focused capacity-building and peer-learning programme.

This shall include, but not be limited to:

- The number and format of online sessions (collective and individual);

- The thematic areas covered (technical AI evaluation, incubation design, responsible and frugal AI, investor dialogue, etc.);

- The number of hours for live sessions and possible asynchronous modules;

- The structure and content of the AI Diagnostic Toolkit and AI Support Playbook;

- The organisation of the expert network and referral mechanisms;

- The animation modalities of the community of practice;

- The design and structure of the study visit to France.

The service provider is expected to ensure strong availability and responsiveness throughout the implementation period.

All support activities shall be planned in coordination with the FEF+ AI Mediterranean Project Leader at Expertise France and validated with participating BSOs.

The programme will be primarily delivered remotely.

Logistics and travel arrangements for the study visit in France will be managed by Expertise France.

The programme shall be implemented over a 6-month period (June–December) and structured into distinct service packages as follows:

(Note: the service provider’ candidate may propose adjustments and recommendations on its technical approach, methodology, the specific added value of its proposed service packages, training formats, themes and tools. Any such amendments should be clearly justified in the offer).

Planned Activities/Service Packages:

Phase 1 – Diagnostic and Planning (Month 1)

Service Package 1: AI Maturity Assessment and Programme Design

The service provider shall:

- Conduct structured diagnostic assessments for each of the five selected BSOs;

- Assess AI support maturity (methodologies, tools, internal expertise, governance, partnerships);

- Analyse startup selection processes and identify risks of AI-washing or technical mis-evaluation;

- Evaluate capacity to assess AI technical maturity (data preparation and pipeline orchestration, model robustness and monitoring, MLOps maturity, infrastructure scalability adapted to local constraints, AI-related risks);

- Evaluate capacity to assess AI-specific business dimensions (compute infrastructure costs and scalability, unique datasets and barriers to replication, investor expectations);

- Evaluate capacity to assess AI team and organizational capacity (AI-specific roles and competencies, skill gaps, ownership for data quality and model maintenance);

- Identify gaps in expert access, compute access, regulatory awareness and investor dialogue;

- Define priority intervention areas per BSO;

- Identify 2–4 key participants per BSO forming the core group for the programme.

During this phase, Expertise France will facilitate alignment with national stakeholders and provide relevant background information.

### Deliverables:

- Diagnostic report per BSO (5 reports);

- Consolidated capacity-building work plan validated by Expertise France.

## Phase 2 – Tool Development and Expert Mobilisation (Month 2)

### Service Package 2: AI Toolkit, Playbook and Expert Network

The service provider shall:

- Finalise and adapt the AI Diagnostic Toolkit, including:

  - Data quality, preparation, pipelines orchestration and governance assessment;

  - model evaluation template (performance, robustness, scalability, monitoring, drift detection)

  - MLOps and infrastructure assessment

  - AI team and organizational capacity assessment

  - AI risk assessment framework;

  - AI due diligence template covering technical and AI-specific business dimensions

  - AI-readiness scoring system.

- Develop and operationalise the AI Support Playbook, including:

  - AI-focused incubation modules,

  - mentoring pathways (technical and AI-specific business);

  - Best practices for AI-specific economic evaluation (compute costs, pricing…);

  - AI team and organizational capacity guidance;

  - responsible AI and compliance guidance,

  - programme structuring templates,

  - Comprehensive KPI framework (technical and AI-specific business metrics)

- Identify, formalise and confirm an AI Expert Network roster, covering technical AI, MLOps, data governance, AI-specific business economics, AI team and organizational structuring, cybersecurity, responsible and frugal AI, as well as AI productisation (particular attention will be paid to inclusiveness and diversity in the composition of the expert roster.);

- Define referral and engagement mechanisms (office hours, technical review sessions, due diligence support);

- Prepare training materials and digital resources;

- Set up the structure of the regional knowledge-sharing platform.

### Deliverables:

- AI Diagnostic Toolkit (final version);

- AI Support Playbook (final version);

- AI Expert Network roster and access framework;

- Detailed programme roadmap.

## Phase 3 – Capacity Building and Community of Practice (Months 3–6)

## Service Package 3: Training, Coaching and Peer Learning

The service provider shall:

- Deliver a structured series of virtual live sessions and workshops covering:

  - AI startup evaluation methodologies;

  - Data preparation, governance and pipelines orchestration

  - MLOps fundamentals;

  - AI-specific business economics (compute infrastructure costs, pricing sustainability)

  - AI team and organizational capacity assessment

  - Responsible and frugal AI, as well as regulatory awareness;

  - Investor dialogue and AI due diligence (technical maturity + AI-specific business dimensions);

  - Infrastructure adaptation to local constraints (bandwidth, compute access);

  - AI integration into incubation programmes;

  - Impact measurement and monitoring tools (technical and business)

- Provide individual coaching to each BSO to operationalise toolkit and playbook;

- Facilitate regular peer-learning sessions across the five BSOs;

- Document lessons learned and emerging good practices;

- Promote progressive harmonisation of AI incubation standards across countries.

The training calendar may vary over the implementation period depending on pedagogical sequencing and BSO availability, but shall remain balanced and aligned with the validated roadmap.

### Deliverables:

- Session reports per workshop;

- Attendance lists, activity tracker and feedback summaries;

- Coaching follow-up notes and action tracking sheets.

## Phase 4 – Internal AI Integration and Strategic Consolidation (Months 4–6)

### Service Package 4: AI Adoption within BSO Operations

The service provider shall guide each BSO in:

- Integrating AI-assisted startup screening workflows;

- Developing AI-based monitoring dashboards;

- Optimising mentor matching systems;

- Structuring automated reporting mechanisms;

- Improving knowledge management systems;

- Ensuring responsible AI adoption internally.

Each BSO shall produce a short Internal AI Adoption Roadmap, identifying priority integration actions and timelines.

### Deliverable:

- Individual AI Internal Adoption Roadmap per BSO.

## Phase 5 – Regional Networking and Study Visit in France

### Service Package 5: Community Strengthening and International Exposure

The service provider shall:

- Organise online networking sessions and matchmaking activities with AI ecosystem actors;

- Facilitate structured exchanges linked to regional AI events and forums;

- Coordinate and technically design a 3–5 day study visit in France for up to 10 BSO representatives.

This shall include:

- Identification and facilitation of meetings with AI innovation hubs, incubators, accelerators, research institutions, investors and corporates;

- Alignment of meetings with programme objectives;

- Preparation of pedagogical materials and knowledge capture tools.

### Deliverables:

- Study visit agenda and technical dossier;

- Pre-visit briefing kit;

- Post-visit learning report template.

(Logistics and travel managed by Expertise France.)

## Phase 6 – Monitoring, Evaluation and Final Reporting (Throughout – Final Month)

### Service Package 6: M&E and Consolidation

The service provider shall:

- Apply monitoring tools to track activities, participation and knowledge acquisition;

- Collect feedback periodically, course-correct program content and activities, and assess institutional progress;

- Consolidate lessons learned and good practices;

- Produce final evaluation report including recommendations for sustainability and scale-up;

- Provide all supporting documentation required for validation;

- Collaborate with the project’s M&E expert to develop and operationalize a comprehensive M&E framework and required data collection tools. This will include periodic feedback surveys for BSOs, activity and attendance tracking mechanisms, and end-of-programme surveys to assess outcomes, inform adaptive management, and support learning.

### Deliverables:

- Intermediate progress notes including activity and attendance trackers;

- Final evaluation and implementation report;

- Comprehensive documentation package (tools, materials, session reports, evidence).

  - Coordination

The service provider shall be a (individual entity or consortium) bringing together complementary expertise required for the implementation of this assignment (AI technical expertise, BSO capacity building, incubation programme design, peer-learning facilitation, regional ecosystem knowledge).

The individual entity or consortium shall designate:

- One lead entity acting as the contractual interlocutor with Expertise France;

- One overall Project Coordinator responsible for operational implementation and reporting;

- Clear country focal points (if applicable), ensuring contextual adaptation in each target country.

The Project Leader of the FEF+ AI Mediterranean project (Sustainable and Inclusive Economy Department, Expertise France) will be the sole contractual contact person for the individual entity or consortium. Contact details will be specified in the contract.

A kick-off meeting shall be organised within one week following contract notification.

Close collaboration must take place between:

- The Project Coordinator,

- The FEF+ AI Mediterranean Project Leader,

- The Expertise France Project Officer and M&E expert

Regular coordination meetings shall be organised to:

- Monitor implementation progress,

- Validate intermediate deliverables,

- Ensure consistency across countries,

- Address operational challenges.

The proposed service provider (individual entity or consortium) must ensure:

- Smooth coordination across all partners;

- Clear internal governance and division of responsibilities;

- Effective mobilisation of required expertise throughout the programme;

- Provision of digital materials and tools to beneficiaries;

- Proper documentation of all sessions and activities.

Logistics and travel arrangements for the study visit in France will be managed by Expertise France.

- Place, duration and terms of performance

Implementation period: 6 months (June–December).

Estimated start date: Upon contract notification (indicatively June).
Estimated end date: Six months after contract signature.

Primary modality: Remote implementation. One in-person study visit in France

## Performance Evaluation

The contractor will be evaluated based on the following criteria upon submission of required reports and deliverables:

- Compliance with the Terms of Reference and agreed work plan;

- Quality and relevance of tools delivered (AI Diagnostic Toolkit, AI Support Playbook);

- Effective mobilisation and coordination of AI expert network;

- Delivery of outputs within the agreed timeframe;

- Quality and pedagogical relevance of training and peer-learning sessions;

- Level of participation and engagement of selected BSOs;

- Quality of reporting and documentation provided.

### Minimum Requirements

To be considered technically compliant, the proposed service provider (individual entity or consortium) must meet the following minimum requirements:

- Demonstrate proven experience in designing and delivering structured capacity-building programmes, including training, coaching and peer-learning mechanisms for innovation intermediaries (incubators, accelerators, technology transfer offices or similar structures).

- Mobilise a core team of at least three senior experts collectively covering the following areas:

  - AI technical evaluation;

  - AI-specific business evaluation and startup scaling dynamics;

  - incubation or acceleration programme design and BSO capacity building.

- Demonstrate knowledge of innovation ecosystems in Europe and/or the Southern Mediterranean region.

- Ensure operational capacity to deliver services in English and/or French, with the availability of Arabic-speaking expertise considered an asset.

Failure to demonstrate compliance with these minimum requirements may result in the rejection of the proposal as technically non-compliant.

- Required expertise and profile

- TECHNICAL EVALUATION CRITERIA (70 points)

- Relevance and Quality of the proposed methodology (30 points)

- Clear understanding of the Terms of Reference and AI ecosystem challenges in the Southern Mediterranean;

- Coherent and structured phased approach (diagnostic → tool development → capacity building → peer learning → consolidation);

- Capacity to adapt tools and training materials to country-specific contexts;

- Strong integration of AI technical evaluation methodologies (data pipelines orchestration, model monitoring, MLOps, infrastructure), AI-specific business economics (compute costs, pricing…), AI team and organizational capacity assessment, and responsible AI principles;

- Clear deliverables with defined format, timeline and measurable outcomes;

- Ability to structure and animate a regional community of practice.

- Composition and Competence of the proposed Team (40 points)

The proposed team (preferably consortium-based) must demonstrate strong and complementary expertise in:

- Capacity building for Business Support Organizations (BSOs);

- AI venture evaluation methodologies (AI maturity, model robustness, data governance, AI due diligence);

- AI technical evaluation (data preparation, pipelines orchestration and governance, model robustness, monitoring and drift detection, MLOps and infrastructure scalability, adaptation to local infrastructure constraints, AI due diligence);

- AI-specific business economics (compute infrastructure cost analysis, pricing models for AI services, identification of competitive advantages, barriers to replication assessment);

- Responsible and frugal AI, regulatory awareness (including local and AI Act implications), and cybersecurity risks;

- AI team and organizational capacity assessment (AI-specific roles and competencies, skill gap identification, organizational structuring for AI ventures);

- Programme design for incubation/acceleration;

- Facilitation of peer-learning communities;

- Mediterranean ecosystem knowledge.

The team should include senior experts (minimum 4–5 key experts) with:

- Proven experience in similar assignments over the past five years;

- Experience working with innovation ecosystems in Europe and/or the Mediterranean;

- Capacity to deliver services in English and/or French (Arabic appreciated);

- Demonstrated experience in remote capacity building delivery.

We are committed to promoting diversity, equity, and inclusion, and to supporting the meaningful participation of experts from the Global South. We strongly encourage applications from women, local and regional experts, and individuals from underrepresented groups. Diverse teams and partnerships that reflect the contexts in which we operate are particularly valued.

- Financial Evaluation Criteria (30 points)

The financial proposal will be assessed based on:

- Clarity and transparency of budget breakdown per service package;

- Coherence between methodology and financial allocation;

- Cost-effectiveness within the maximum ceiling of EUR 100,000 incl. VAT;

- Appropriate allocation of resources between diagnostic, tool development, training, peer learning and study visit design.

- Composition of the offer to be provided:

The tenderer shall submit:

### 1. Technical Proposal

Including:

- Understanding of the assignment and ecosystem context;

- Detailed methodology and phased implementation plan;

- Description of AI Diagnostic Toolkit and AI Support Playbook structure;

- Organisation of expert network and community of practice;

- Study visit design approach;

- Monitoring and evaluation framework.

Maximum recommended length: 7–10 pages.

### 2. CVs of Proposed Experts

Including:

- Relevant experience;

- Similar references (at least three comparable assignments over the past five years);

- Clear indication of role and time allocation.

### 3. Financial Proposal

- Detailed pricing per service package;

- Breakdown of expert fees and other costs;

- Total amount in EUR (incl. VAT);

- Confirmation that logistics for France visit are excluded.