# Terms of reference 
and technical Specifications

- General information

| # Assignment name | # Study tour in Europe |
| --- | --- |
| # Beneficiary | # National institutions (sectoral ministries) |
| # Country | France and Belgium |
| # Total number of days “Event “ | # 5 working days |

- Context and justification of the need

Expertise France is the French public international cooperation agency. It designs and implements projects that aim to contribute to the balanced development of partner countries, in line with the Sustainable Development Goals (SDGs) of the 2030 Agenda.

The Green Forward project, implemented by Expertise France and funded by the European Union, aims to accelerate the transition to green and circular economies in the Southern Neighbourhood. As part of this initiative, a high-level study tour will be organized in Paris, France, and Brussels, Belgium, from May 15 to May 30 (TBD), 2026, bringing together approximately 20 senior decision-makers from Algeria, Egypt, Jordan, Lebanon, Libya, Morocco, Palestine, and Tunisia.

- Objectives and desired results

  - General objective

The objective of the assignment is to provide event management services ensuring a professional and seamless delivery of all logistical arrangements for the study tour, allowing participants to focus on policy learning and exchange.

  - Specific objectives

- Ensure efficient and timely organisation of all travel and accommodation arrangements for participants, in line with the approved agenda and Expertise France procedures.

- Provide end-to-end logistical coordination before and during the study tour, including internal transfers, catering, on-site support, and event set-up.

- Ensure compliant financial and administrative management, including documentation, and reporting in accordance with Expertise France and donor requirements.

- Guarantee visibility and communication requirements, ensuring all materials comply with Expertise France and EU visibility guidelines.

- Support Expertise France teams on-site, facilitating smooth coordination and rapid resolution of any logistical or administrative issues.

  - Anticipated results

- All travel, accommodation, transfers, and catering arrangements are confirmed and implemented on time, with no disruption to the study tour agenda.

- Participants are well informed, supported, and able to fully engage in study tour activities.

- On-site logistics are efficiently coordinated, ensuring the smooth running of meetings and visits.

- DSA is distributed and documented in full compliance with Expertise France procedures.

- Communication and visibility materials are produced and deployed in line with EU requirements.

- Final technical and financial reports are submitted on time, complete, and audit-ready.

- Description of the assignment

  - Planned activities

The service provider must support the logistic of the study tour in order to perform the following activities:

International Travel arrangements

- Manage the flights booking for delegation of 20 persons from the 8 countries (Morocco, Jordan, Palestine, Egypt, Tunisia, Lebanon, Libya, Algeria), as well as 3 Expertise France staffs members from Jordan.

- Handle all travel arrangements on behalf of participants, including direct communication by email and telephone.

- Provide participants with pre-paid flight tickets and all relevant travel and transfer information in a timely manner.

Rail transportation within Europe

- Book rail tickets in line with the approved agenda (Thalys premium from Paris to Brussels if available for all high-level participants).

- Manage all related logistics and participant communications, and provide pre-paid tickets and transfer details.

Accommodation

- Book the hotels for participants, according to the agenda (4 nights in Paris and 1 or 2 nights in Brussels, depending of flight schedules)

- Book the hotels for Palestinian Delegation in Amman for 2 nights, near Queen Alia International Airport (QAIA), includes dinner and breakfast.

Internal transfers

- Provide appropriate ground transportation between the different locations, according to the agenda, including :

- Airports transfers in Paris (vans or taxis for individual or small group arrivals)

- Transportation for meetings in Paris (Buses for 20-25 people)

- Transfers between the train station and hotel in Brussels (taxi or van)

- Transportation for meetings in Brussels (buses or taxi)

Catering/Meals

- Manage the restaurant reservations or lunch boxes, according to the agenda and dietary requirements.

- Arrange :

- One networking dinner in a restaurant for around 25 people in Paris

- One networking dinner in a restaurant for around 25 people in Brussels

- For the remaining dinners, participants will be free to dine at their convenience. Meals will be managed directly by the hotels, with participants receiving meal vouchers allowing flexible access to a variety of food options.

- In total, Expertise France will cover five (5) lunches and five (5) dinners.

Meetings & Interpretation

- Book meeting room in Paris and Brussels, with projector and microphone, and set up in round-table format for up to 25 participants, in line with the agenda

- Organise coffee breaks during meeting (coffee, tea, water, pastries, ect.)

- Provide simultaneous interpretation services (French, English and Arabic), including the rental of all necessary interpretation equipment

Event management and logistics

- Provide one Event Coordinator on-site throughout the study, who will be in charge of:

  - welcoming participants at the hotel upon arrival and accompanying them upon departure;

  - coordinating transportation logistics;

  - act as a contact person for the participants;

  - supporting EF staff regarding logistical and administrative issues during the event;

  - Gather necessary attendance confirmation and signatures to verify the eligibility of costs.

  - Ensure the smooth running of the event, in all its aspects, from the arrival of participants to the closing;

  - Distribute participant kits with project branding;

  - Set up the places: projection of videos and presentation,

  - Management of material requirements (notebooks, post-its, ballpoint pens, etc.);

Communication materials

- Proposal of materials for participant, including a detailed agenda and logistical notes.

- All materials must comply with Expertise France and EU visibility guidelines.

- Welcome signs for airport arrival.

- Draft of press kit

Other services

- Laptop rental for presentations

Post-assignment follow-up

- Submit the technical and financial report, at the latest 10 working days after the event.

- The final financial report will be presented as a spreadsheet, and will include a concise and clear description of all expenses incurred and specified in the contract. All prices will be expressed in EUROS.

- The following documents will be annexed to the financial report:

- The final participants list, including cancellations or replacement participants, dates and times of arrivals and departures, number of nights’ accommodation, DSA amount, signatures;

- Originals or certified copies of all invoices;

- If requested, any other supporting document.

Sustainability considerations
The service provider is expected to integrate environmentally responsible and sustainable practices throughout the implementation of the assignment. This may include, where feasible, measures to reduce the environmental footprint of travel and events (e.g. efficient transport solutions, waste reduction, limited use of printed materials and plastics, and sustainable catering options). Bidders are invited to briefly describe the sustainability practices they intend to apply in the delivery of the services.

  - Anticipated deliverables

| Deliverables | Description | End date |
| --- | --- | --- |
| - Kick-off meeting with Expertise France |  | T0 + 1-2 days |
| - Communication materials | Draft and final versions of all communication materials, including agenda, logistical notes, participant information pack, airport welcome signs, and press kit. Options to be proposed, in line with Expertise France and EU visibility guidelines. | T0 + 10 days |
| - Detailed logistical plan | Comprehensive logistical plan covering travel arrangements (flights and rail), accommodation, internal transfers, catering, on-site coordination, and contingency measures, aligned with the approved agenda. | T0 + 7 days |
| - Participants’ travel dossiers | Individual travel files per participant (flight/train tickets, hotel confirmations, transfers, emergency contacts). | At the latest 15 working days before the event |
| - Confirmation of all bookings | Written confirmation of all bookings and arrangements, including international flights, rail tickets, hotel reservations, internal transfers, catering reservations, and on-site event logistics. Final participant travel itineraries to be shared individually. | At the latest 20 working days before the event |
| - On-site coordination note / daily logistics brief | Short daily coordination notes or running order for the event (transport timings, contact points, responsibilities). | Before the start of the event |
| - Final technical and financial reports | Submission of the final technical and financial report, including a detailed breakdown of all expenses in EUR, annexed with participant lists and signatures, boarding passes, and original or certified invoices, in line with Expertise France procedures. | T0 + 10 working days after the event |

  - Coordination

The service provider shall designate a single contact person for project implementation purposes.

The project Manager will be the service provider’s sole contact person for Expertise France.

A launch meeting shall be held two days after the contract award has been notified.

Close collaboration must take place with Expertise France team from assignment preparation right up to completion. Furthermore, regular exchanges must take place with the project team on assignment progress and any difficulties that may be encountered.

- Place, duration and terms of performance

Schedule/programme: Study Tour Agenda -TBD

The provisional programme for assignment implementation is as follows:

Day 0 — Paris: Arrivals

| Time | Activity | Location | Notes |
| --- | --- | --- | --- |
| All day | Participant arrivals | Charles de Gaulle Airport (CDG) | Grouped airport pickups arranged |
| Afternoon | Hotel check-in & registration | Paris Hotel | Welcome packs distributed |
| 19:00 | Optional welcome briefing | Hotel meeting room | Informal introduction to the week |
| 20 :00 | Dinner at the hotel | Paris Hotel | Opening ceremony |

Day 1 Paris: Policy & National Frameworks

| Time | Activity | Location | Speaker / Host |
| --- | --- | --- | --- |
| 09:00–09:30 | Welcome briefing | Hotel / EF HQ | EF Jordan team |
| 09:30–10:30 | Overview of EU Green Deal & legislative pillars | Plenary room | Invited EU expert |
| 10:30–11:00 | Coffee break | On site | — |
| 11:00–12:30 | ADEME – National policy frameworks, MRV, CBAM readiness | ADEME HQ | ADEME officials |
| 12:30–14:00 | Lunch | Nearby restaurant | — |
| 14:00–16:00 | Refashion HQ – Textile EPR & sectoral decarbonisation | Refashion HQ | Refashion experts |
| 16:15–17:15 | Wrap-up reflections | Hotel | EF Jordan team |
| 19:00–21:00 | Networking dinner | Central Paris | — |

Day 2— Paris Region: Field Visits & Industry

| Time | Activity | Location | Speaker / Host |
| --- | --- | --- | --- |
| 08:30–12:00 | Site visit: CBAM compliance & decarbonisation | Paris Region | Corporate sustainability team |
| 12:00–13:15 | Lunch | On site / nearby | — |
| 13:30–15:30 | Site visit: Syctom Ivry / Paris XIII – Waste valorisation | Ivry-sur-Seine | Syctom team |
| 15:45–17:00 | Reflection & Q&A – Industrial transition | On site | EF moderator |

Day 3 — Paris: Governance Deep-Dive

| Time | Activity | Location | Speaker / Host |
| --- | --- | --- | --- |
| 09:00–10:30 | City of Paris – Urban waste & circular strategy | City of Paris offices | City officials |
| 10:45–12:00 | DREAL Île-de-France – PRPGD & coherence tools | DREAL HQ | DREAL representatives |
| 12:00–13:15 | Lunch | Nearby | — |
| 13:30–15:30 | Citeo – EPR operations & eco-modulation | Citeo HQ | Citeo team |
| 15:45–17:00 | AFD / Bpifrance – Green finance & industrial modernization | AFD / Bpifrance offices | Finance experts |
| 17:15–17:45 | Wrap-up & Brussels briefing | Hotel | EF Jordan team |

Day 4 — Brussels: EU Institutions & Stakeholders

| Time | Activity | Location | Speaker / Host |
| --- | --- | --- | --- |
| Morning | Travel Paris → Brussels |  | — |
| 10:30–12:00 | Exchanges with DG ENV, DG NEAR, DG TAXUD & DG CLIMA – CBAM & EU ETS | Brussels | EC representatives |
| 12:00–13:15 | Lunch | EU district | — |
| 13:30–15:00 | EU CEAP & stakeholder platforms – Circular Economy Action Plan | EU offices | Platform experts |
| 15:15–16:45 | Peer dialogue & cooperation lab – CBAM readiness | EU offices | EF moderator |
| Afternoon | Hotel check-in | Brussels Hotel | — |
| 19:30–21:30 | Networking dinner | Brussels centre | — |

Day 5 — Brussels: Wrap-Up & Departures

| Time | Activity | Location | Speaker / Host |
| --- | --- | --- | --- |
| 09:00–10:30 | Final wrap-up – Lessons learned & actions | Hotel / EU Delegation | EF moderator + country leads |
| 10:30–11:00 | Hotel check-out | Brussels Hotel | — |
| 11:00–12:00 | Transfer to Brussels-Midi station | Train |  |
| All day | Departures | CDG Airport or Brussels airports |  |

- Required expertise

The service provider should propose an experienced multidisciplinary team and appropriate technical.

Qualifications/Competences

- Event Management Experience: A proven experience in managing high-

profile events, including logistics coordination, venue setup, and on-site management,

particularly for international organizations or development projects.

- Communication Strategy Expertise: Demonstrated ability to design and implement effective communication strategies, including media outreach, public relations, and social media engagement, with a strong focus on promoting sustainability.

- Experience with International Organizations: Prior experience working with or for international organizations, preferably within the context of development projects, ensuring familiarity with global standards, reporting requirements, and cross-cultural communication.

- Team Leadership and Coordination: The ability to lead and coordinate a diverse team, ensuring efficient workflow, timely delivery of tasks, and seamless integration of all event components.

Technical Resources

The co-contractor must have access to the following equipment, tools, and software to ensure the

successful execution of the mission:

- Professional Photography and Videography Equipment: High-resolution cameras, video recording devices, and associated accessories to capture high-quality visuals for post-event communication and documentation.

- Video Editing Software: Access to industry-standard video editing software for creating promotional videos, event recaps, and other multimedia content.

- Graphic Design Tools: Proficiency in using graphic design software to develop visually appealing event materials, such as banners, brochures, and social media content.

- Sound and Lighting Equipment: High-quality audio-visual equipment, including microphones, speakers, and lighting systems, to ensure clear communication and an engaging event atmosphere.

Sustainability practices

In alignment with the project's focus on urban resilience and green development, the event will

adhere to the following sustainability practices:

- Waste Minimisation: Implement strategies to reduce waste generation, including the use of reusable materials, digital invitations, and electronic distribution of event materials to minimise paper usage.

- Sustainable Catering: Source catering services that offer locally produced, organic, and seasonal food options, with a focus on minimising single-use plastics and packaging.

- Digital Materials: Encourage the use of digital formats for all presentations, reports, and handouts, reducing the need for printed documents.

Response Format

To facilitate the analysis of responses, all interested parties are required to prepare their response in

accordance with the instructions outlined in this section. All proposals should be electronically

generated. The vendor will be hired on an Expertise France contract.

Applicants are required to submit the following:

- A Technical Proposal: Letter of Interest, stating why you consider your service suitable for the

assignment and a brief methodology on the approach and implementation of the assignment.

- Evidence and examples of similar projects that have been successfully completed,

- Personal CVs highlighting qualifications and experience in similar projects

- Work references – minimum of three references -contact details (e-mail addresses) of referees (organisation for whom you have produced similar assignments)

- All-inclusive (fix cost bid) financial proposal detailing the price before and after tax indicating consultancy fee and a breakdown of expenses (unit price together with any other expenses) related to the assignment.

- Assignment reports

A report following the model provided must be forwarded by e-mail on conclusion of the assignment: it must correspond with the deliverable summary analytical report …

- Monitoring-evaluation

| Deliverables | Immediate effects | Intermediate effects | Verification sources |
| --- | --- | --- | --- |
| Communication and visibility materials | Participants receive clear, timely and compliant information ahead of the study tour | Improved participant preparedness and visibility of the action in line with EU requirements | Final communication materials, visibility checklist, participant information packs |
| Detailed logistical plan | Logistical arrangements are clearly planned and validated in advance | Reduced operational risks and smoother implementation of the study tour | Approved logistical plan, email validation from Expertise France |
| Confirmation of all bookings | All travel, accommodation and transfers secured before the event | Participants arrive on time and follow the agenda without disruption | Booking confirmations, travel itineraries, hotel and transport vouchers |
| On-site event coordination | Efficient day-to-day coordination during the study tour | Smooth execution of activities and high participant satisfaction | Attendance sheets, daily coordination notes, EF validation |  |
| Final technical and financial reports | Clear and complete reporting of activities and expenses | Financial transparency and accountability towards EF and donors | Approved technical report, financial spreadsheet, annexed invoices and supporting documents |  |