|  | PROCUREMENT CONTRACT |
| --- | --- |
|  | ☒Service – ☐Supplies |
|  | Number: |
|  | Object of the contract: Development of an Implementation Handbook, MEAL system structuring, and Stakeholder Engagement for “Africa -Europe Partnerships for Culture: Audio-Visual” |
|  | MAXIMUM AMOUNT OF THE CONTRACT: |
| Award date:. This contract is subject to the French Public Procurement Code in its latest version in force as enacted by Order No. 2018-1074 issued on 26 November 2018 and its Implementation Decree No. 2018-1075 issued on 3 December 2018 constituting the regulatory aspects of the Public Procurement Code (“CCP”). It is awarded by means of: adapted procedure in application of Articles L. 2123-1 and R. 2123-1 to R. 2123-7 of CCP. |

TABLE OF CONTENTS

special conditions – commitment procedure	4

ARTICLE 1:	Object of the contract	5

ARTICLE 2:	Contractual documents	5

ARTICLE 3:	General characteristics of the Contract	6

Form of the Contract	6

Term of the Contract	6

Commencement and deadline of service provision	6

Procedure for the issuance of purchase orders	6

ARTICLE 4:	Financial provisions	7

Amount of the Contract	7

Form of prices	7

Advance	7

Payment procedure	8

Payment terms and late payment interest	8

Presentation of payment demands	8

Bank transfer	9

Value added tax (VAT)	9

Taxes and duties	10

ARTICLE 5:	inspection and acceptance activities	10

Inspection activities	10

Acceptance of services and supplies	10

ARTICLE 6:	Specific terms of execution	10

Deliverables table	10

Expert in charge of the assignment	11

Place of execution	11

Export control	11

Language of the Contract	11

Commitments of the Contractor	11

Confidentiality	12

Insurance	12

Contact person and communication	12

Understaking against deforestation	13

ARTICLE 7:	Re-examination clause	13

ARTICLE 8:	Similar services	14

ARTICLE 9:	penalties	14

Penalties for periodic documentary deliverables	14

Penalties applicable to submission of final deliverables	14

ARTICLE 10:	intellectual property	14

Definitions	14

Ownership of results	14

Exploitation of results	15

Licensing of pre-existing rights	15

Guarantees	15

Image rights	16

ARTICLE 11:	Termination of the contract	16

General terms of performance	16

Termination of the Contract due to the non-availability of a designated expert	16

Procedure	16

ARTICLE 12:	safety and security measures and responsabilities	16

ARTICLE 13:	ethics	17

ARTICLE 14:	Administration of personal data	17

ARTICLE 15:	Dispute resolution - applicable law	18

ARTICLE 16:	Derogation from the CCAG	18

ARTICLE 17:	AUDIT	18

ARTICLE 18:	Final provisions	19

Declaration	19

Annex 1: Specifications	22

Annex 2: PURCHASE ORDER	31

# special conditions – commitment procedure

Between:

EXPERTISE FRANCE SAS 40, boulevard de Port Royal - 75005 PARIS, France A simplified joint-stock company with share capital of €828,933 registered under the following numbers: - SIRET no.: 808 734 792 00035 - Intra-community VAT number: FR36 808734792 Represented by Mr Jérémie PELLET, Managing Director, of the first part,

and:

co-contracting party’s name (Hereafter the “Contractor”) - Registered office address: - Registration number at the trade and companies registry: - Intra-community VAT no. (as applicable): Represented by: of the second part,

(Hereafter referred to collectively as the “Parties“)

Whereas:

In the context of the cooperation project, hereafter the “Main Contract” (donor contract) signed on December 18th 2025 between  Expertise France, Deutsche Gesellschaft für InternationaleZzusammenarbeit  and European Union, covering “Africa-Europe Partnerships for Culture : Audio-Visual “, Expertise France asks the Contractor, which accepts the same, to perform the services and deliver the services under the Contract as set out in the attached technical annex entitled “Specifications”.

In the light of the foregoing, the following is agreed:

- Object of the contract

The object of this contract (hereafter the “Contract) is to provide information, implementation modalities and networks required to shape “Africa-Europe Partnerships for Culture: Audio-visual” during its inception phase.

- Contractual documents

The Contract is composed of the contractual documents set out below in decreasing order of priority:

- This document and its annexes:

- Annex 1 attached: Specifications;

- The Code of Conduct of Expertise France (available at https://www.expertisefrance.fr/documents/20182/426622/Expertise+France+%E2%80%93+Code+of+conduct/82cf6060-4768-4b25-8817-ccba1d86e568);

- The purchase orders placed under the Contract (see Annex 2, attached: purchase order model);

- Contractual annex (DAJ_M050 : Contractual annex personnal data process (GDRP subcontracting) form and DAJ_F062 : GDRP compliance verification form) covering the processing of personal data in the event of GDPR data processing (collection of personal data on behalf of Expertise France).

- CCAG - General administrative clauses applicable to public procurement for intellectual services approved under the Order of 30/03/2021.

- The Contractor’s bid dated XX/XX/XXXX

These documents constitute the entirety of the agreement between the Parties with regard to the Contract. They supersede all verbal and written communications, procedures, agreements, commitments, guarantees and settlements referring to its object and facts that may have been made by or on behalf of a Party to the other Party before the notification date. These documents are acknowledged by the Parties to represent the sole and complete expression of the terms of their agreement.

Without prejudice to the general rules applicable to administrative contracts, any modification to the Contract or the waiver of any right resulting from the Contract must be covered by an amendment signed by a duly authorised representative of each Party.

- General characteristics of the Contract

## Form of the Contract

The Contract is a mixed public framework agreement contract: it contains one fixed price  element and an order-based element defined as follows:

| Fixed-price element | Initial Scoping Stakeholder Consultation & Co-Design Analysis and Planning Data Collection & Interim Implementation Handbook The Finalization and Co-Construction |
| --- | --- |
| Purchase-rder-based element | Pool of expert days, to be mobilised if needed |

“Purchase order” items are defined by Articles R. 2162-13 and R.2162-14 of the CCP and are executed as and when said purchase orders are issued.]

## Term of the Contract

The term of the Contract is 5 months from its award to the Contractor by Expertise France.

The Contract shall expire after all services have been delivered by the Contractor and all rights and obligations of the Parties resulting from the Contract have been extinguished. If all or some of the services remain outstanding by the specified period, the Contractor must immediately take all necessary steps to complete delivery without being able to claim any remuneration in this regard.

## Commencement and deadline of service provision

The service provision deadline under this Contract is 4 months from the award date of this Contract.

If all or some of the services remain outstanding within the specified deadline, the Contractor must immediately take all necessary steps to complete delivery without being able to claim any remuneration in this regard.

## Procedure for the issuance of purchase orders

Purchase orders will be issued by Expertise France as and when the need arises:

Each purchase order will be issued by e-mail to the Contractor in the format specified in annex to the Contract and will clearly state:

- The reference number of the Contract and of the Main Contract;

- A description of the service ordered;

- The amount of the purchase order and its breakdown (quantity ordered x unit price);

- The place of execution;

- The duration of execution.

Purchase orders will be issued by e-mail to the Contractor.

After its expiry, the FWC shall remain in force with regard to purchase orders and specific contracts. They must be executed within two months of its expiry.

- Financial provisions

## Amount of the Contract

| ITEM | AMOUNT |  |
| --- | --- | --- |
| Fixed-price element | € exc. VAT. |  |
| Maximal amount of the order-based element | 12 000€ exc. VAT. |  |
| MAXIMUM AMOUNT OF THE CONTRACT (FIXED-PRICE ELEMENT + ORDER-BASED ELEMENT) | € exc. VAT. |  |

The maximum amount of the Contract corresponds to the sum of the prices of all fixed-price items and of the minimum amount of the purchase order element.

The lump sum part corresponds to the amount that Expertise France undertakes to pay, after validation, without reserve of all the supplies and/or services expected (excluding the purchase orders). As the price is fixed, it includes all the costs linked to the execution of the services and/or the delivery of the corresponding supplies.

The purchase order-based element of the Contract does not include any minimum amounts. Expertise France is therefore not committed to any minimum order level under the Contract for purchase order items.

The amount of each purchase order corresponds to the amount Expertise France undertakes to pay after all services due under the Contract have been accepted without reservation. This amount is calculated on the basis of the unit prices stated in the unit pricing schedule below, applied to the quantities ordered. It includes all costs relating to the corresponding service provision and/or delivery of supplies.

| Expenditure categories of the purchase order item X | Unit prices € exc. VAT |
| --- | --- |
| Daily rate per expert | € exc. VAT |

## Form of prices

Prices are firm and non-modifiable.

## Advance

An advance of 20% of the fixed-price element of the contract amount is granted to the Contractor from the award date of the Contract.

Any renewal of the Contract execution period will not establish entitlement to any additional advance.

The advance must be repaid in full once the aggregate amount of payments reaches 60% of the price of the item.

## Payment procedure

- Interim payment

Periodic quarterly advances may be paid to the Contractor. The amount of such advances may not exceed the value of the services delivered by the Contractor and duly accepted by Expertise France.

The frequency of advance payments may be reduced to 1 month at the request of the Contractor.

The cumulative amount of advances paid shall not exceed 90% of the amount of the CONTRACT.

Payment of an advance does not constitute proof of acceptance, even partially, nor does it release the Contractor from its obligations under the Contract or with regard to the item in question.

- Partial definitive payments/balance

Each item and purchase order gives rise to a partial definitive payment corresponding to the balance, to be carried out after receipt and final acceptance of all corresponding services and supplies.

## Payment terms and late payment interest

Payment is always made out in the name of the issuer of the invoice or of the expense reimbursement request.

Overall payment terms for monies due under the Contract are thirty (30) days maximum from the date of receipt of the complete invoice, including all supporting documentation, or the date of service/supply acceptance if this date is later. Any missing document will prevent payment.

If these payment terms are not respected, Expertise France will pay late payment interest to the Contractor pursuant to Article R. 2192-10 et seq. of the CCP on the fight against late payment in public procurement contracts. The rate applied shall be the interest rate of the European Central Bank for its main and most recent refinancing operations, as applicable on the first day of the semester of the calendar year during which late payment interest started to accrue, plus eight percentage points.

The amount of the fixed indemnity to cover collection costs is set at forty (40) euros and will be systematically paid in addition to late payment interest. Interest below €40 shall not be mandated.

## Presentation of payment demands

In addition to the legal notices (intracommunity VAT no.), invoices relating to the Contract must contain the following information:

- Company name, address and registered office of the Contractor;

- Registration number of the Contractor (SIRET or equivalent);

- Bank account details;

- The code of the department acting as specifying department (stated in the article entitled Contact person and communication);

- Reference number of the Contract;

- The reference and title of the cooperation project concerned (if applicable);

- Clear and accurate description of the equipment/supplies sold and/or services performed;

- If the Contractor’s bank details are not stated on invoices, it must provide a statement or certificate of bank or post office account details, with the third-party form duly completed in all cases.

Invoices are to be forwarded via the Chorus Pro system, and must state the department code provided above corresponding to the department of Expertise France on behalf of which the Contract has been placed.

If the Contractor is not obliged to forward invoices via Chorus, it may submit its invoices to the contact person stated in the article entitled Contact person and communication.

Invoices for advances must be accompanied by the corresponding supporting documentation validated by Expertise France.

Invoices for balances (partial definitive payments) must be accompanied by a copy of the acceptance decision for the corresponding services and/or supplies.

Any missing document will prevent payment.

## Bank transfer

Payment for invoiced services/supplies will be made to the bank account identified in the third-party sheet.

Payment is always made out in the name of the issuer of the invoice or of the expense reimbursement request.

## Value added tax (VAT)

The Contractor must state the VAT rate applicable to the transaction or, as applicable, its VAT exemption by stating on the invoice the relevant provisions of the French General Tax Code or those of Directive 2006/112/EC of 28 November 2006.

Any Contractor benefitting from exemption must state “VAT exempt” in accordance with the rules that apply to it.

## Taxes and duties

The Contractor shall be directly responsible for all taxes and duties that may be levied against it under the Contract, both in the country of its registered office and in those of project implementation.

- inspection and acceptance activities

## Inspection activities

Inspection activities will be carried out for services and supplies as set out in Chapter 5 of the CCAG-FCS. By way of derogation from Article 23 of the CCAG-FCS, inspection activities will be carried out by:

- the Project Manager, Débora LESEL

- the Project Officer, Julie CAYEUX

## Acceptance of services and supplies

By way of derogation from Article 25 of the CCAG-FCS, acceptance activities will be carried out by:

- the Project Manager, Débora LESEL

- the Project Officer, Julie CAYEUX

Any lack of response from Expertise France shall not equate to tacit acceptance of services or supplies.

- Specific terms of execution

## Deliverables table

| Periodic deliverables |  |  |
| --- | --- | --- |
| Item | Deliverable | Submission frequency |
| Initial scoping phase | Initial scoping note | 1 week after the signature of the contract |
| Stakeholder Consultation Phase & Co-Design | Consultation toolkit | 3 months after the signature of the contract |
| Data Collection Phase & Interim Implementation Handbook | Interim Implementation Handbook | 3 months after the signature of the contract |
| Final deliverables |  |  |
| Item | Deliverable | Deliverable submission deadline |
| The Finalization and Co-Construction Phase | Final Implementation Handbook | 3,5 months after the signature of the contract |

## Expert in charge of the assignment

The assignment must be performed by one or more designated experts whose CV must be appended to the Contract.

The Contractor may therefore not replace any designated expert for the delivery of the services attributed to said expert, unless with prior written approval from Expertise France.

## Place of execution

The services will be performed  remotly The contractor can state in their offer whether missions in Sub-Saharan Africa would be needed.

## Export control

The goods covered by this contract may be subject to export authorisation. The contractor undertakes to comply in all circumstances with the applicable export control regulations. The contractor shall submit to us the Export Control Classification Form (ECCF) duly completed and signed for each item. The Contractor shall inform the Buyer of any regulatory changes (classification/embargo) affecting the goods sold.

The execution of any export of classified military goods and their relates materiel, and/or dual-use goods, by the contractor (exporter) is conditional upon obtaining export authorisation and compliance with the associated conditions.

## Language of the Contract

This document is written in English, which shall be the reference language for any dispute that may arise regarding the meaning or interpretation of the Contract, to the exclusion of any other language.

## Commitments of the Contractor

The Contractor is subject to a performance obligation and therefore undertakes to:

- comply with the Specifications;

- immediately notify Expertise France in writing of any communication or instruction relating to the services/supplies that it may receive from the Client (beneficiary country or public entity) or from a third party, and not to comply with any such communication or instruction until having discussed the matter with Expertise France and after receiving the latter’s written authorisation;

- notify any difficulty it may encounter with the performance of its obligations under the Contract;

- comply with all applicable laws and regulations of the country of delivery of the services/supplies and adopt an attitude and act vis-à-vis third parties in the interests of Expertise France, such that Expertise France cannot be reproached in this regard by the Client, or by any person the latter may have designated;

- protect the interests of Expertise France vis-à-vis the Client;

- act as a loyal advisor vis-à-vis Expertise France;

- present itself vis-à-vis the Client, partners and local authorities as a Contractor engaged by Expertise France;

- apply the undertakings of Expertise France as expressed in its Code of Ethics, provided in Annex 5 of the Contract.

In the context of Contract execution, the Contractor undertakes to:

- perform the services/supplies in a diligent, effective and economic manner, in accordance with generally accepted techniques and practices;

- employ appropriate modern techniques and safe and affective processes.

## Confidentiality

The Contractor shall treat as private and maintain the confidentiality of all documents and information received or which it becomes aware of in the context of the Project. It shall maintain the secrecy thereof and not use them for any purpose other than execution of the Contract.

In this regard, the Contractor undertakes:

- To protect and maintain the confidentiality of information considered or presented as such;

- To handle confidential information it receives with the same degree of care and protection as it applies to its own confidential information;

- only to reveal confidential information to its personnel and third parties involved in performance of the Contract after having received prior written and express approval from Expertise France;

- to take all necessary steps such that its personnel and third parties involved in execution of the Contract, who become aware of confidential information, undertake to treat such information with the same level of confidentiality as set out in this clause;

- As and when required, to reiterate the confidential nature of such information to its personnel and third parties involved in the execution of the Contract, as soon as said confidential information is communicated to the aforementioned persons;

- to reiterate the confidential nature of confidential information prior to any meeting during which confidential information is communicated.

Apart from where necessary for the purposes of service delivery, the Contractor may not disclose any element of the Contract without prior written consent from the other party.

## Insurance

The Contractor shall take out, and maintain at is own expense, third-party and professional liability insurance policies covering the physical injury and material and consequential damage that may arise from delivery of the services/supplies.

The Contractor shall also take out, and maintain at its own expense, insurance policies covering its working accident and occupational illness liability with regard to its agents assigned to delivery of the services/supplies.

The Contractor must be able to produce on request by Expertise France all certificates demonstrating its possession of the aforementioned policies.

## Contact person and communication

All communication and notifications between the Parties under the Contract shall take place in written form, either through the exchange of e-mails or via registered letter with acknowledgement of receipt, where the latter form is prohibited in certain cases under the Contract, and shall be deemed to have been validly served from its receipt by the addressee.

All correspondence shall be forwarded, all carriage costs paid, to the following addresses:

| For Expertise France : | Expertise France Débora Lésel Project Manager Inclusive and Sutainable Economy Department 40, boulevard de Port Royal F-75005 PARIS |
| --- | --- |
| For the Contractor: | To be completed by the Contractor |

Each Party may modify its address at any time subject to notifying the other Party thereof in writing.

## Understaking against deforestation

Within the framework of the policy to combat imported deforestation and in the hypothesis of the use of raw materials or processed products, the Contractor undertakes to evaluate precisely the quantities really necessary and to study alternatives to the products at risk listed below:

- Meat;

- Eggs ;

- Dairy products ;

- Ready-made meals, margarine, spreads;

- Leather shoes ;

- Automotive upholstery ;

- Household and cleaning products ;

- Agrofuels ;

- Lumber ;

- Solid wood or particle;

- Fuels ;

- Paper ;

- Cardboard ;

- Textiles ;

- Coffee, chocolate ;

- Exotic fruits ;

- Electronics.

For more information, the guide Engaging in Zero Deforestation Public Procurement is available at the following email address : https://www.ecologie.gouv.fr/sites/default/files/Guide_politique_achat_public_zero_deforestation.pdf

- Re-examination clause

Under Article R.2194-1 et seq. of the Public Procurement Code, Expertise France may amend the provisions of the Contract subject to the following conditions:

- Example 1: Substitution with a new pricing schedule if deletions, modifications or additions are made to the items in the initial pricing schedule, subject to approval by Expertise France;

- Example 2: Revision of technical elements (clarification of deliverables, producer technical definitions, equipment technical documents, updated instructions, etc.).

Such modifications shall be notified to the Contractor by concluding an amendment.

- Similar services

Under Article R.2122-7 of the French Public Procurement Code, the Contractor may be awarded a contract for similar services to those of the initial contract without advertising or competitive bidding.

- penalties

The amount of penalties will be applied within the calculation of the balance due under the relevant item or purchase order.

## Penalties for periodic documentary deliverables

By way of derogation from Article 14 of the CCAG, penalties are set at the fixed rate of €50 net per day of delay in the delivery of the periodic deliverables specified in Article 6 “Deliverables table” of the Contract.

## Penalties applicable to submission of final deliverables

By way of derogation from Article 14 of the CCAG, penalties are set at the fixed rate of €100 net per day of delay in the delivery of the final deliverables specified in Article 6 “Deliverables table” of the Contract.

- intellectual property

## Definitions

The Assignment provided for by this article requires definition of the following terms:

- “Result” means any intended outcome of the performance of the Contract which is delivered and definitively accepted by Expertise France;

- “Creator” means any natural person who contributed to the production of the result;

- “Pre-existing right” means any intellectual property right, including pre-existing technologies owned by Expertise France, the Contractor or any third party with a prior interest in the order to be executed under the Contract.

## Ownership of results

The ownership of results, and the title to related intellectual and industrial property rights, including the solutions and technical information they contain, are entirely and irrevocably transferred to Expertise France under the Contract. This Assignment only covers the economic rights of creators under the conditions set out in Article 8.3 of the Contract. The moral rights of creators are excluded. Such moral rights cover the disclosure, paternity and respect for the integrity of the results treated as a work within the meaning of the French Intellectual Property Code.

The aforementioned elements shall be deemed to be effectively transferred to Expertise France after acceptance of the results delivered to it by the Contractor.

The payment of the price to the Contractor is deemed to include any fees payable to the Contractor in relation to the acquisition of rights by Expertise France, notably all forms of exploitation of the results. The acquisition of such covers all territories worldwide.

## Exploitation of results

By acquiring title to the results developed by the Contractor, Expertise France becomes the holder of all economic copyright relating to such rights. In this regard, yet without the list being exhaustive, Expertise France may exploit the results for the following purposes:

- internal exploitation:

  - disclosure to its personnel;

  - communication disclosure to persons and entities working for Expertise France or cooperating with it, including contractors, subcontractors (whether legal or natural persons), EU institutions, agencies and bodies and member states' institutions;

  - installing, uploading, processing, arranging, compiling, combining, retrieving, copying, reproducing in whole or in part and in unlimited number of copies.

- distribution to the public:

  - in paper, electronic or digital format;

  - on the internet as a downloadable/non-downloadable file;

  - via display, radio or television broadcasting or any other transmission technique;

  - otherwise in any form and by any method.

- modifications:

  - modification of content, form or technique;

  - addition of new elements of content and form;

  - adaptation using new media;

  - translation into any language;

  - digitisation and computer processing.

## Licensing of pre-existing rights

Expertise France shall not acquire ownership of pre-existing rights. The Contractor shall license the pre-existing rights on a royalty-free, non-exclusive and irrevocable basis to Expertise France, which may use the pre-existing rights as set out in Article 8.3. Such licences shall become effective from the moment the results are delivered by the Contractor and accepted by Expertise France. On delivery of the results, the Contractor may, as required, provide Expertise France with a list of pre-existing rights and third parties' rights, including those of its personnel, of creators and of other right holders. The licensing of pre-existing rights to Expertise France under the Contract covers all territories worldwide and is valid for the whole duration of intellectual property rights protection.

## Guarantees

When delivering the results, the Contractor shall warrant that they are free of rights or claims from creators and third parties, including in relation to pre-existing rights, for any use envisaged by Expertise France.

On request from Expertise France, the Contractor shall provide evidence of ownership or rights to use all the listed pre-existing rights and rights of third parties, except for the rights owned by Expertise France.

## Image rights

If natural, recognisable persons appear in a result or their voice is recorded, on request from Expertise France the Contractor shall submit a declaration in which such persons (or of the persons exercising parental authority in case of minors) give their permission for the described use of their image or voice. This does not apply to persons whose permission is not required in line with the law of the country where photographs were taken, films shot or audio records made.

- Termination of the contract

## General terms of performance

The Contract is subject to the termination clauses as defined in Articles 29 to 36 of the CCAG.

By way of derogation from Article 42 of the CCAG FCS, termination for reasons of general interest is not applicable to this contract. However, the parties agree on the possibility of terminating the contract by mutual consent.

In the event of early termination, the Contractor shall immediately return to Expertise France all documents it may have received for the purposes of execution of the Contract.

## Termination of the Contract due to the non-availability of a designated expert

In the event of the non-availability of a designated expert, the Contractor shall notify Expertise France thereof within 3 days and, within 14 days at the latest, propose the CV of a replacement expert of at least the same level or expertise. If these replacement conditions are not respected, Expertise France may terminate the Contract due to fault on the part of the Contractor.

Regardless of the circumstances, should an expert remain unavailable for a cumulative duration of XX weeks without a satisfactory replacement having been found, Expertise France may automatically terminate the Contract.

Termination for the non-availability of a designated expert shall not establish any entitlement to any form of compensation for the Contractor.

## Procedure

Any termination decision shall be notified by Expertise France to the Contractor by registered letter with acknowledgement of receipt. It shall state the effective date of termination.

- safety and security measures and responsabilities

The Contractor is the only one who is responsible for the safety of the people and property that he mobilizes for the execution of the present Contract and in this respect, takes all necessary measures. He undertakes to ensure that all of his employees and subcontractors comply with the safety instructions that he issues.

In the event of an incident and/or direct or indirect attack on the safety of people directly or indirectly mobilised by the contractor or its equipment, Expertise France cannot be held responsible in any way whatsoever.

- ethics

The Contractor also undertakes to take note of the  Expertise France Code of Conduct and to comply strictly with it (the Expertise France code of conduct is available on the agency’s website: www.expertisefrance.fr).

Any breach to comply with the code of conduct may result in the termination of the Contract and incur the liability of the Contractor.

- Administration of personal data

The Contract may require the processing of personal data. The parties undertake to comply with regulations on the processing of personal data in accordance with amended law no. 78-17 of 6 January 1978 relating to data processing, files and liberties and regulation (EU) 2016/679, known as the General Data Protection Regulation (GDPR).

The Contractor notably undertakes to:

- Process personal data solely for the purposes of the Contract, as defined in annex hereto covering the collection of personal data (GDPR data processor);

- Ensure that persons authorised to process personal data undertake to maintain its confidentiality or are bound by an appropriate legal obligation of confidentiality;

- Implement appropriate technical and organisational measures to guarantee a level of security commensurate with the risks resulting from the Contract, notably with regard to data encryption, confidentiality and integrity;

- Notify Expertise France, via any means, of any personal data breach within 24 hours of becoming aware of any such event;

- Assist Expertise France in its obligation to respond to requests it may receive from data subjects;

- Delete all personal data or return it to Expertise France on conclusion of the services covered by the Contract, as specified by the latter, unless EU law or that of the member state requires such data to be retained;

- Make available to Expertise France all information it may require to demonstrate compliance with the obligations set out in this article and to enable audits to be conducted by the latter or by any other person of its choice.

Where the Contractor uses a data processor to process personal data during execution of the Contract, it must obtain prior written authorisation from Expertise France. Similarly, the Contractor shall notify Expertise France of any planned change concerning the addition or replacement of processors, thereby enabling Expertise France to issue any objections it may have in this regard.

The same obligations concerning data protection as those set out in the Contract are mandatory for processors, notably regarding the provision of adequate guarantees for the implementation of appropriate technical and organisational measures ensuring the protection of personal data. Should any processor fail to meet its obligations, the Contractor shall remain fully responsible vis-à-vis Expertise France for the fulfillment of the processor’s obligations.

In the event of non-compliance with the aforementioned provisions, the Contractor is reminded that its liability may be invoked. In the event of any breach of professional secrecy or non-compliance with the aforementioned provisions, Expertise France may immediately terminate the Contract without compensation for the Contractor.]

- Dispute resolution - applicable law

Any dispute between the Parties relating to the existence, validity, interpretation, execution, and termination of the Contract (or any of its clauses) that the Parties cannot resolve amicably within 30 days of the notification of the dispute by the requesting Party to the other Party, shall be submitted to the competent court.

The applicable law for this Contract is French law, to the exclusion of any other law.

- Derogation from the CCAG

The following articles of this document derogate from the CCAG-FCS:

- article 5 derogates from article 28 and 15 of the CCAG ;

- article 9 derogates from article 14 of the CCAG

- AUDIT

The Contractor may be submitted to an audit concerning compliance with the regulations and contractual obligations applicable to the performance of the present Contract. This audit may be carried out by Expertise France or by a third party appointed by Expertise France and may not be refused by the Contractor. If the audit is carried out by a third party, the appointed third party must not be a direct competitor of the Contractor. Scheduled audits may be carried out periodically or spontaneously at the request of Expertise France or a third party. In all cases, the contractor will be informed at least 5 working days in advance.

The Contractor therefore undertakes to:

- Allow Expertise France or the appointed entity, and facilitate their access to the information required to carry out the audits, including interviews with the people involved and on-site visits;

- Submit documents relating to the performance of the present Contract as well as any documents required by the auditors;

- Demonstrate transparency and respond to auditors’ requests;

- Implement any corrective measures that may be necessary.

Expertise France will notify the Contractor of the identity of the audit structure selected in the case of an external firm, the purpose of the assignment, the planned duration of the assignment and the names of the experts assigned.

The Contractor also undertakes to allow Expertise France, or any other third party mandated by Expertise France, to carry out an investigation in the case of an allegation of a prohibited practice relating to the present Contract, under the conditions set out above.

The conclusions of the audit report will be sent to each of the Parties by any means deemed appropriate by Expertise France.

The conclusions may prescribe the implementation of actions and a deadline for completion.

Any refusal by the Contractor to comply with the audit exercises and/or their conclusions gives as of right to Expertise France the possibility to terminate the present contract without compensation.

- Final provisions

## Declaration

The Contractor, its affiliates, suppliers, service providers, consultants and subcontractors (including directors, employees and agents of such entities) hereby declares:

- that no natural or legal person on whose behalf the Contractor is acting is subject to the prohibitions set out in Articles L. 2141-1 to L. 2141-6 and L. 2141-7 to L. 2141-11 of the French Public Procurement Code or any equivalent prohibition issued in another country;

- that the commitments made by the Contractor within the scope of the Contract do not create a situation of conflict of interest that may affect the execution of the Contract;

- that the Contractor have not committed any act that may influence the process of Project implementation to the detriment of the Beneficiary, and notably that no Understanding has been, or will be, entered into;

- that the negotiation, award and execution of the Contract has not given rise to, nor will do so in the future, any act of corruption as defined in the United Nations Convention Against Corruption dated 31 October 2003;

- accepts that the Contract will be awarded in accordance with standard practices and in electronic format.

Furthermore,

The Contractor, its affiliates, suppliers, service providers, consultants and subcontractors (including directors, employees and agents of such entities) certify that:

- they do not acquire and don't supply/will not acquire or supply equipment and do not intervene/will not intervene in sectors under embargo by the United Nations, the European Union or France. For information, the list can be found at: https://www.sanctionsmap.eu ;

- they are not included in the lists of financial sanctions adopted by the United Nations, the European Union, France and/or the United States, notably in the fight against the financing of terrorism and against attacks on national peace and security. For information, the lists can be consulted at the references below:

- for the United Nations, the United Nations Security Council sanctions lists: https://www.un.org/securitycouncil/content/un-sc-consolidated-list;

- for the European Union, the lists can be consulted at the following address: https://www.sanctionsmap.eu;

- for France, see: https://gels-avoirs.dgtresor.gouv.fr/List;

- for the United States, see: https://home.treasury.gov/policy-issues/financial-sanctions/sanctions-programs-and-country-information;

- they are not subject to a World Bank exclusion order and are not on the list published by the World Bank. For information, the list can be consulted at the following address:

https://www.worldbank.org/en/projects-operations/procurement/debarred-firms

In the hypothesis of such a decision of exclusion, we can join to the present declaration on honor the additional information which would allow to consider that this decision of exclusion is not relevant within the framework of the market).

Finally, the Contractor, its affiliates, suppliers, contractors, consultants and subcontractors (including directors, employees and agents of such entities) acknowledge and accept that the above-mentioned situations may lead to the automatic termination of the contract.

They undertake to inform Expertise France without delay of any change in our situation during the execution of the contract with regard to the present declaration.

FOR THE CONTRACTOR:

In.....………....….., on...…….....20....

Preceded by the handwritten words “Read and approved":

Signature:

Name:
First name:

Role:

FOR EXPERTISE FRANCE:

This offer is accepted as an undertaking.

In.....………....….., on...…….....20....

Signature:

Name:
First name:

Role:

Done in one original copy retained by Expertise France.

# Annex 1: Specifications

Terms of reference 
and technical Specifications

- General information

| Assignment name | Development of an Implementation Handbook, MEAL system structuring, and Stakeholder Engagement for “Africa -Europe Partnerships for Culture: Audio-Visual” |
| --- | --- |
| Beneficiary | EF & GIZ |
| Country | Sub-Saharan Africa & Europe |
| Total estimated number of days | 5 Months |

- Context and justification of the need

Africa-Europe Partnerships for Culture: Audio-visual is an initiative cofinanced by the European Union, the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH and the French Ministry for Europe and Foreign Affairs, implemented by GIZ and Expertise France (EF). The duration of this initiative, hereinafter referred to as “the Action”, is scheduled from 1 March 2026 to 30 November 2029.

The Action’s objective is to strengthen the socio-economic relations between Africa and the EU and foster intercultural dialogue among their citizens through structured support to the value chains of the audiovisual industry. It will cover 5 specific audio-visual (AV) value chains: film, series, animation, video games, and immersive content.

The Action is structured around three interconnected specific objectives. These three specific objectives form a coherent and mutually reinforcing ecosystem:

- Specific Objective 1 establishes the enabling environment and supports co-creation;

- Specific Objective 2 develops human capital and drives innovation;

- Specific Objective 3 ensures that creative products reach audiences and generate market demand and engagement.

This integrated approach aims to strengthen African–European cooperation in the AV sector in terms of co-created content/product development as well as institutional/business partnerships, to support sustainable industry growth as well as investment promotion, and to enhance intercultural dialogue through engaging and inclusive marketing and distribution of audio-visual narratives. The Action is strongly in line with the priority areas of the Global Gateway strategy.

Specific Objective 1: Enabling Environment and Project/Product Development

SO1 aims to strengthen collaboration between Sub-Saharan Africa (SSA) and EU member states in the AV sector by improving data availability, policy frameworks, project/product development, and investment linkages.

The Action will improve access to reliable market and industry information. Data on audience behaviour, market size, trends, and value chains is currently fragmented or missing, which limits strategic business and policy decisions. Through partnerships with research institutions, industry bodies and public agencies, the Action will support collection, harmonisation and accessibility market data and reports. These insights will support companies, investors and policymakers in planning investments, designing policies and identifying collaboration opportunities between Africa and Europe.

Based on this, the Action will support respective institutions to develop better policies and regulations for the AV sector. This can include support on investment incentives, intellectual property, anti-piracy, AI guidelines, infrastructure or connectivity, co-production frameworks, and financing mechanisms. Dialogue formats, peer learning and legal advisory will help align policies between African and European partner countries and address regulatory barriers such as taxation, platform fees and content classification systems.

In addition, the Action will stimulate joint African–European project/products development. It will promote a culture of equitable co-creation through dialogue and guidance on inclusive co-productions and partnerships. Incubation approaches will bring together mixed SSA–EU teams (e.g. creatives, producers, tech developers and entrepreneurs) to develop new products and business models. Selected teams will receive mentoring, networking opportunities and seed funding to develop prototypes and prepare projects for the market.

Finally, the Action will strengthen investment in the sector by strengthening Africa–Europe investors networking structures and implementing an advocacy strategy promoting cross-continental investment, alongside the organization of matchmaking and pitching events. Mature businesses will receive tailored support, including investor-readiness coaching, business development, pitching support and IP protection guidance to strengthen their investment capacity. In parallel, advisory support will be provided to mature co-production projects involving African and European partners.

Specific Objective 2: Skills Development, Mobility, and Institutional Strengthening

SO2 aims to strengthen skills development training ecosystems, and professional networks in the African and European audio-visual sectors, with a strong focus on young professionals and women.

The Action will support professional training and skills development through a series of calls for projects fostering partnerships between Sub-Saharan African and European educational institutions, incubators, mentoring programmes, and training organisations. Supported initiatives will address selected AV value chains while facilitating access to European markets.

Furthermore, the Action will support clusters of African organisations and studios delivering in-house professional training programmes. Selected projects will receive grants combined with capacity-building support to strengthen organisational capacities, improve training delivery, and better align skills development with industry needs across both regions.

A mobility grant scheme will enable African and European professionals to participate in training programmes, industry events, residencies and collaborative projects. Participants will attend major festivals, markets and tech/creative events in Europe and Africa, combined with structured professional visits, meetings and training. These exchanges aim to build long-term partnerships, increase visibility of talents, and connect them with industry players and investors.

Specific Objective 3: Marketplaces, Distribution, and Audience Engagement

SO3 aims to improve how Africa–Europe co-created and co-produced AV content reaches audiences and markets, and how audiences/users discover, access and engage with this content.

The Action will simplify legal and rights-related processes, strengthen partnerships between distributors, broadcasters and platforms, and improve market transparency. Model contracts and rights-management tools will be developed, and alliances between African and European industry actors will be supported to reduce cross-border barriers and accelerate content circulation. To boost commercial success, the Action will focus on matchmaking, deal facilitation and market-readiness support, working with selected markets and platforms to increase transactions and licensing deals.

Accessibility and localisation will be prioritised through multilingual solutions such as subtitling, dubbing, audio description, inclusive game design and assistive technologies. Emerging AI-based localisation tools and support for creative localisation professionals will help reach diverse linguistic communities and people with disabilities, while ensuring African perspectives are reflected in technology development.

The Action will also strengthen audience development by supporting data-driven marketing and content adaptation for different regions, languages, age groups and connectivity contexts. Innovative distribution channels such as mobile cinemas, community screenings, gaming hubs, pop-up VR/AR spaces, schools and youth centres will be tested, alongside partnerships with influencers, creatives, platforms and broadcasters to increase visibility and uptake.

Finally, the Action will foster audience engagement and cultural dialogue through online communities, media partnerships, interactive events and immersive formats. Audience feedback and impact data will inform future marketing, education and policy strategies.

To ensure relevance and partner-orientation of the Action, GIZ and EF will conduct a 6-month inception phase. This phase will be structured as follows:

Phase 1 - Project Set-up: Recruitment and onboarding of the project team; securing office space and equipment; setting up governance and coordination mechanisms between EF and GIZ; formal notification of institutional stakeholders of the project launch.

Phase 2 - Field Missions & Co-design: Deepening research through field missions, mapping exercises, consultations and ecosystem-building with stakeholders, as well as conducting strategic framing studies:

- An internal study or “Implementation Handbook & MEAL system structuring” to help fine-tune and operationalise the Action’s activities. It will focus on all required information GIZ and EF will need to effectively implement the Action.

- An external study that will be available to the public. It will provide an overview of African–European partnerships in the audiovisual sector and provide a status-quo analysis combined with a joint call for action. The timeline for conducting and publishing this study will go beyond the inception phase.

Phase 3 – Validation & Structuring: Validation of activities and logical framework; presentation and validation of the revised workplan; set-up of Monitoring, Evaluation and Learning (MEL); development of the outreach and visibility plan.

The present Terms of Reference have been drafted to allow for the procurement of a service provider to deliver an Implementation Handbook & MEAL system structuring for the project.

- Objectives and desired results

- General objective

The objective of the assignment is to provide information, implementation modalities and networks required to shape “Africa-Europe Partnerships for Culture: Audio-visual” during its inception phase. The focus of the assignment shall only be in the following AV sectors in SSA and EU member states: Film, Series, Animation, Gaming and Immersive Content (VR/AR).

- Specific objectives & anticipated results

The service provider will develop an Implementation Handbook (to be delivered by mid- August 2026), which covers the following areas:

- Project implementation recommendations:

- Map & assess cooperation potential with related projects, initiatives and networks (private, public, civil society, support programmes & intermediaries) across all relevant sectors, outputs and countries in Sub-Saharan Africa and EU.

- Based on a short-listt provided by EF and GIZ, analyse potential priority countries (in Sub-Saharan Africa & EU) for partnerships with government entities to promote enabling legal frameworks for African-European collaboration, as well as countries with strong intermediary structures that can conduct or support with regionally scaled project activities.

- Analyse the Description of Action in light of research and stakeholder feedback and provide actionable recommendations for regional implementation, efficiency, coordination, and operational planning.

- Provide recommendations on partnership models under which the project engages with different stakeholder groups (taking into consideration that the Action wants to champion the topic of partnerships, and lead with good examples within the ecosystem) and potential grant schemes, including proposals for  themes, innovation challenges, volume, target, and contract details with potential fund managing organizations as well as beneficiaries.

- Stakeholders' consultation program

- Design and facilitate a stakeholder consultation program in close collaboration with GIZ & EF teams to collect insights and recommendations: develop a methodology for stakeholder identification and participant selection, plan and (co-)facilitate consultations, synthetize key findings and recommendations to EF and GIZ.

- Present the project logframe and activities and challenge it through stakeholder feedback.

- Identify and engage key experts for the establishment of an Advisory Board consistent of stakeholders from SSA and Europe, (design of a flexible participation framework, rotation of Advisory Board members to ensure diversity, continuity, and sustained engagement).

- Monitoring, Evaluation, Accountability & Learning:

- Contribute to a coherent, inclusive, and replicable MEAL plan, to be further developed and implemented by MEAL focal points in EF & GIZ teams.

- Revise the logical framework to improve clarity and coherence between objectives, outcomes, outputs, and indicators.

- Collect, analyse, and document baseline values for the indicators of the Action (logframe), specifying methods, timing, and responsible entities.

- Identify barriers, enablers, and opportunities related to diversity, gender and disability inclusion, and propose potential activities to address them.

- Propose an internal safeguards system for risk management that includes risk categories, governance and oversight structure, compliance guidelines, code of conduct and ethics, financial and anti-corruption controls, cultural safeguards, and operational risk management.

- Description of the assignment

- Planned activities

The service provider must achieve the above outlined objectives and result in line with the following methodology and activities:

- Initial Scoping (1st week): This phase will include a kick-off meeting with GIZ and EF teams to clarify expectations and refine the methodological approach, a review of project documents including the Description of Action, as well as an initial mapping of potential partners, intermediaries, priority countries and similar projects in the AV sector across outputs. This phase will conclude with the validation of an Initial Scoping Note detailing the methodology and planned activities for the rest of the assignment. This note will be presented to EF and GIZ at a meeting to discuss the preliminary findings.

- Stakeholder Consultation & Co-Design (Until 3rd month): This phase will include the design and implementation of a stakeholder consultation program in close collaboration with GIZ and EF teams to gather inputs that will inform operational recommendations, baseline data collection, and MEL planning, as well as the identification of key stakeholders for co-construction workshops.

- Analysis and Planning (Until 3rd month): This phase will include a review of the logical framework and project activities by the service provider to identify gaps or adjustments prior to baseline data collection, the development of a Monitoring, Evaluation, and Learning (MEL) plan, and a Diversity, Gender and Disability Inclusion Plan.

- Data Collection & Interim Implementation Handbook (Until 3th month): This phase will include collecting baseline and contextual data for project indicators, including gender- and disability-sensitive information, using a mix of methods adapted to national contexts, such as surveys, interviews, and focus groups, informed by previous analysis and stakeholder consultations, and producing an interim Implementation Handbook summarizing findings and preliminary recommendations.

- The Finalization and Co-Construction (Until mid-August): This phase will include co-construction workshops with GIZ & EF project teams and stakeholders to validate recommendations, finalization of the Implementation Handbook (MEL plan, Gender and Disability Inclusion Plan, and stakeholder consultation outcomes), and presentation and dissemination of the final study results to the project teams.

b) Deliverables

1.   Initial scoping note, validated by Expertise France & GIZ

2. Consultation toolkit: package of materials developed to support and document stakeholder consultations (stakeholder mapping & selection, agenda, discussion framework & consultation notes)

3. Interim Implementation Handbook: summarizing preliminary findings, operational recommendations, stakeholder consultation outcomes, and proposed adjustments to project implementation, partnership models, and grant schemes.

4. Final Implementation Handbook: Integrating all findings, recommendations, and lessons learned, ready for operational use. Including:

  - Revised Logical Framework: with improved clarity and coherence between objectives, outcomes, outputs, and indicators and baseline values for the indicators.

  - Monitoring, Evaluation & Learning (MEL) Plan: outlining indicators, baseline data methods, responsibilities, and timelines.

  - Gender and Disability Inclusion Plan: The project will adopt a cross-cutting approach to gender equality and disability inclusion across all activities and in the Monitoring, Evaluation Accountability and Learning (MEAL) framework. Specific recommendations will be developed to ensure the meaningful participation of women and persons with disabilities and to address potential barriers to access and engagement. A follow-up mechanism will be established to monitor the implementation of these recommendations and ensure that inclusion considerations are systematically integrated throughout project implementation.

  - Internal Safeguard / Risk Mechanism: defining procedures for risk identification, mitigation, monitoring, and management throughout project implementation.

- Place, duration and terms of performance

- Implementation period: April to end of August 2026

- Schedule/programme:

The provisional programme for assignment implementation is as follows:

| Activity | Deliverables | Place | Period |
| --- | --- | --- | --- |
| Initial Scoping Phase | Initial scoping note | Remote | 1st week |
| Stakeholder Consultation Phase & Co-Design | Consultation toolkit | Hybrid | Until 3rd month |
| Analysis and Planning Phase | NA | Remote | Until 3rd month |
| Data Collection Phase & Interim Implementation Handbook | Interim Implementation Handbook | Remote | Until 3th month |
| The Finalization and Co-Construction Phase | Final Implementation Handbook | Remote | Until mid-August |

- Number of working days:

An estimated number of of 40 expert days is expected to be distributed between the two experts forming the proposed team.

As an option, additional up to 15 optional expert days may be mobilised from the expert pool, if needed. These additional experts shall be subject to prior approval based on their CVs by EF .

- Required expertise and profile

The service provider should ideally propose a team composed of a pair of SSA-European experts: one monitoring and evaluation (M&E) expert and one inclusivity expert.

The service provider is encouraged to propose a team that reflects a diversity of perspectives and experiences, in particular by combining expertise from Sub-Saharan Africa and Europe. Ideally, the core team would include two key experts: one monitoring and evaluation (M&E) specialist and one inclusivity expert.

In line with the objectives of the action, particular attention will be paid to the team’s ability to demonstrate a collaborative and co-construction approach between professionals from Sub-Saharan Africa and Europe.

Service providers may consider forming a consortium or partnership arrangement to bring together complementary expertise and regional experience.

Given the tight timeline of the assignment, a high level of availability and the ability to mobilize quickly during the implementation period are expected from the experts.

- Qualifications and skills of the Monitoring and Evaluation & Project Management Expert:

- Education:

- A postgraduate university degree in monitoring and evaluation, social sciences, development economics, public policy, or equivalent experience;

- General Professional Experience:

- 10 years of professional experience in Monitoring, Evaluation, Accountability and Learning (MEAL) for international development cooperation projects/programmes.

- Experience in the design and structuring of multi-country or regional programmes.

- Specific Professional Experience:

- 8 years’ experience in designing and implementing baseline studies, indicators, and analysing MEAL (Monitoring, Evaluation, Accountability and Learning) systems;

- 8 years’ experience in facilitating multi-stakeholder consultations, validation workshops and participatory assessments,

- 8 years’ experience mixed methods i.e. quantitative (surveys and data analysis) and qualitative (key informant interviews, focus groups and document review);

- 10 years’ experience using data analysis tools and M&E platforms;

- 5 years’ MEAL experience in creative industry value chains.

- Regional experience:

- 5 years' experience working in Sub-Saharan African contexts;

- 5 years of experience in European contexts.

- Language:

- High proficiency in written and spoken English (C1 according to the proficiency level defined in the CEFR);

- Working knowledge of French (B2 according to the proficiency level defined in the CEFR).

B. Qualifications and skills of the Audio-Visual Inclusivity Expert:

- Education:

  - A postgraduate university degree in social sciences, development studies, gender studies, public policy, cultural & creative industries, or a related field.

- General professional working experience:

  - 8 years of professional experience in gender mainstreaming within development projects;

  - 8 years of experience in conducting sectoral or programmatic gender analyses, gender-sensitive diagnostics, and/or operational gender action plans.

  - Experience in the design and structuring of multi-country or regional programmes.

- Specific professional experience:

  - 4 years of experience in the audio-visual sector, including film, animation, series, video games, or immersive content ecosystems;4 years of experience analysing gender dynamics in cultural and creative industries, media sectors, or entrepreneurship ecosystems would be a strong asset.

- Regional experience:

  - 5 years of working experience in the Sub-Saharan African contexts;

  - 5 years of working experience in European contexts.

- Language:

  - High proficiency in written and spoken English (C1 according to the proficiency level defined in the CEFR);

  - Working knowledge of French (B2 according to the proficiency level defined in the CEFR).

In addition to the two main experts, the service provider will offer a flexible pool of up to 3 short-term experts (up to 15 expert days in total) to support on specific research topics, data collection etc. The selection of each expert in the curse of the assignment requires the prior confirmation of EF.

- Monitoring-evaluation

Applicants shall submit:

- A technical proposal detailing their understanding of the assignment and the proposed methodology.  This entails a proposed timeline and allocation of working days. The technical proposal shall not exceed 25 pages. If the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

- A detailed financial proposal.

- The CVs of the experts to be mobilized. The CVs shall not exceed 4 pages each. They must clearly show the position and the job the proposed person held in the reference project and for how long. The CVs can be submitted in English and French. If the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

# Annex 2: PURCHASE ORDER

PURCHASE ORDER

Date of notification :

| Overview of contract identification |  |  |
| --- | --- | --- |
| Subject of the contract |  |
| Identification number |  |
| Contractor |  |
| Date of notification |  |
| Purchase order |  |
| Purchase order number |  |
| Subject of the purchase order |  |
| Interim deliverables |  |
| Final deliverables |  |
| Time limit for completion or delivery time |  |
| Special conditions of performance |  |

| Signatory empowered to enter into legally binding commitments on behalf of Expertise France: |  |  |
| --- | --- | --- |
| Name and position | Date and place | Signature |

+

Prohibited practices as defined by the Agence Française de Développement group are defined below: https://www.afd.fr/en/ressources/afd-groups-policy-prevent-and-combat-prohibited-practices-2020

Date and original signatures

Date and original signatures

Tentative:  Benin, Kenya, Nigeria, Senegal, Ethiopia, Côte d’Ivoire, Mozambique, South Africa, Rwanda, Botswana, Ghana, Zambia. Confirmed list will be provided before contract signature.