Terms of Reference (ToR)

-

Diagnostic and Feasibility Assessment of Climate Risk Transfer Solutions for FEPCMAC and the CMAC System in Peru

IDRIMA Scoping Phase - March 2026

- Context

The Federación Peruana de Cajas Municipales de Ahorro y Crédito (FEPCMAC) oversees a network of ten (10) Cajas Municipales de Ahorro y Crédito (CMACs), which collectively serve more than three million micro and small enterprises and agricultural clients across Peru. Through their decentralized branch networks, CMACs provide credit and financial services to clients that are often underserved by commercial banks, particularly in secondary cities and regional markets.

CMACs play a key role in promoting financial inclusion and supporting local economic activity. Their lending portfolios are closely linked to the performance of the real economy at local level, including agriculture, small-scale commerce and services. As a result, shocks affecting local production and income generation can have direct implications for clients’ repayment capacity and, in turn, for CMAC portfolio performance.

CMACs and their clients are exposed to a range of climate-related shocks, including El Niño Costero, droughts, floods and landslides. These events can disrupt economic activity, reduce household and enterprise income and increase credit risk. When such shocks affect large numbers of clients simultaneously, they may also generate systemic effects at institutional level, including increased non-performing loans and liquidity pressure.

During consultations held in October 2025 with the Agence Française de Développement (AFD), FEPCMAC highlighted several structural challenges and needs:

- The absence of sufficiently structured and decision-relevant climate risk data to support the assessment of insurance and risk transfer solutions;

- The need for impact studies and portfolio-level analysis to better understand and quantify climate-related risk exposure affecting CMAC clients;

- A strong interest in exploring climate risk transfer solutions at two complementary levels: Client-level protection, with a particular focus on agricultural insurance for smallholder clients; Institutional-level protection for CMACs, aimed at supporting liquidity and financial stability in the event of systemic climate shocks.

In this context, IDRIMA, a joint initiative of the Agence Française de Développement (AFD) and the Insurance Development Forum (IDF), will engage with FEPCMAC to support a structured scoping and diagnostic process. The objective of this assignment is to clarify needs and priorities, identify data and knowledge gaps, and explore feasible climate risk transfer mechanisms adapted to a limited number of selected (through the diagnostic and prioritization phase) CMACs in Peru.

- Objectives of the assignment

The overall objective of this assignment is to support FEPCMAC and Cajas Municipales de Ahorro y Crédito (CMACs) in developing a structured and data-driven understanding of their exposure to climate-related risks, and to identify and assess physical climate risk, with a specific focus on how these risks affect their clients, and to identify and assess for a limited number of CMACs (approximately three) climate risk transfer solutions that could enhance both institutional resilience of CMACs and direct protection for their clients.

Specific objectives:

Specifically, the assignment aims to:

- Conduct a system-level diagnostic of climate risk exposure: Analyse climate-related hazards, exposure and vulnerability affecting CMAC clients and CMAC credit portfolios, and assess how climate shocks translate into financial impacts at both client and institutional level.

- Assess the climate risk data and information environment: Map available climate, hazard and portfolio data relevant to insurance and risk transfer solutions (including data from SENAMHI, IGP, UNI and CMAC portfolios), and identify key data gaps and constraints affecting feasibility.

- Propose the prioritization of a limited number of CMACs (approximately three) for deeper analytical engagement: Based on diagnostic findings, propose and justify the prioritization of a limited number of CMACs to be more closely engaged during the remainder of the assignment, in order to ensure analytical depth and operational realism.

- Deepen the analysis with selected CMACs: Work more closely with the prioritized CMACs to refine portfolio diagnostics, assess operational and data readiness, and inform the feasibility assessment of potential risk transfer solutions.

- Review existing risk management and insurance mechanisms: Review existing risk management practices and insurance mechanisms relevant to the CMAC system (including public schemes such as ProAgro and existing insurance arrangements, where applicable), and assess their relevance and limitations in addressing climate-related risks.

- Identify and assess feasible climate risk transfer solutions: Identify and assess potential climate risk transfer mechanisms for:

  - Client-level protection, with particular attention to agriculture and other climate-sensitive client segments;

  - Institutional-level protection for CMACs.

The assessment will focus on technical, operational, regulatory and market feasibility, without entering into detailed product design or pricing.

- Formulate conclusions, recommendations and a high-level roadmap:

Provide FEPCMAC with:

  - A shortlist of feasible climate risk transfer solutions;

  - Clear conclusions on enabling conditions and constraints;

- A high-level roadmap outlining possible next steps for a subsequent phase focused on product development and structuring.

Cross-cutting requirement - GESI (Gender and Social Inclusion): The service provider shall apply a gender and social inclusion lens across all components of the assignment, identifying differential climate vulnerability and insurance access barriers among client segments (including women borrowers and other underserved groups), and reflecting these findings in the diagnostic, feasibility assessment and recommendations.

- Scope of Work

The selected Service Provider(s) will carry out the assignment in close collaboration with FEPCMAC, the selected Cajas Municipales de Ahorro y Crédito (CMACs), the AFD Lima Country Office, and the IDRIMA technical team.

The scope of work will be implemented across three complementary levels:

- System level, coordinated by FEPCMAC

- Operational level, implemented through selected CMACs

- Client level, covering CMAC borrowers and beneficiaries

The assignment will focus on diagnostics, feasibility assessment and solution exploration. It does not yet include detailed product pricing or actuarial modelling.

- Detailed work assignment

4.1. System-level diagnostic of climate risk hazard, exposure and vulnerability

The Consultant is expected to analyse climate-related hazards, exposure and vulnerability affecting CMAC clients and CMAC credit portfolios, and assess how climate shocks translate into financial impacts at both client, institutional and system level.

Among other activities, the Consultant is expected to

- Assess the climate risk data and information environment: Map available climate, hazard and portfolio data relevant for this work (including but not limited to datas from SENAMHI, IGP, MIDAGRI, UNI and CMAC portfolios), and identify key data gaps and constraints affecting feasibility.

- Conduct climate risk profiling and vulnerability analysis of the CMAC system: The assessment will be based on major climatic & weather-related risks, agricultural and crop-related risks, Business and livelihood risks affecting MSMEs and commercial clients, household economic risks linked to climate shocks. The analysis will take into account:

- CMAC portfolio composition and sectoral exposure (e.g. agriculture, climate-sensitive MSMEs),

- Geographic exposure to climate hazards (e.g. droughts, floods, El Niño-related events) across Peru,

- Qualitative insights from CMAC management and operational staff, Review of existing documentation and studies.

A gender and social inclusion lens will be applied, focusing on the identification of client segments potentially facing disproportionate climate impacts or barriers to risk management (e.g. women-led businesses, women farmers, youth, indigenous or remote communities), based on available qualitative and portfolio-level information.

- Analyze institutional risks faced by CMACs in relation to climate events, covering:

- Credit default risk and non-performing loans following major climate shocks

- Liquidity stress and portfolio volatility

- Property and asset risks where relevant to CMAC operations

- Operational and management exposure linked to geographic and sectoral concentration of climate risk

- Portfolio concentration risks and liquidity risks related to correlated climate losses

The analysis will also include a review of existing loss-absorption and provisioning practices related to climate and portfolio risks (and to identify, at a high level, the extent to which external risk transfer mechanisms could complement or interact with regulatory provisioning and capital requirements.), including the use of voluntary or discretionary provisions established by CMACs. This review will clarify (i) whether such provisions exist across CMACs or only in selected institutions, (ii) the extent to which they are governed by regulatory guidance versus internal discretion, and (iii) the types of risks and loss scenarios these provisions are intended to cover. The objective is to assess how current provisioning practices interact with, complement, or potentially substitute future insurance or climate risk transfer solutions.

- Review of existing insurance products (Client level, exploratory)

Review existing insurance products currently accessed by CMAC clients (if any), identifying:

- Existing solutions

- Coverage gaps and unmet protection needs

- Constraints and limitations of existing products including affordability, distribution and operational challenges.

4.2 Prioritization of a limited number of CMACs for deeper analytical engagement:

Based on diagnostic findings and further one-to-one exchanges with CMACs Management teams on the outcomes of Step 1, the Consultant shall propose and justify the prioritization of a limited number of CMACs to be more closely engaged during the remainder of the assignment.

This prioritization will:

- Be informed by the results of the climate risk, portfolio and operational diagnostics, including the distribution of climate exposure across client segments.

- Aim to ensure analytical depth, operational realism and representativeness

The prioritization may consider:

- Geographic exposure to climate hazards

- Concentration of climate-sensitive portfolios (e.g. agriculture, MSMEs)

- Data availability and quality

- Operational and systems readiness

- Institutional willingness to engage in further analytical work

In the context of this assignment, FEPCMAC may leverage existing working relationships with selected CMACs that are already engaged on climate or risk-related topics. In this regard, CMACs such as CMAC Huancayo, CMAC Cusco and CMAC Piura may offer relevant case studies for deeper analytical engagement, as they operate in different geographic regions and climate contexts within Peru.

- CMAC Huancayo operates primarily in the central Andean region, where economic activities include agriculture, commerce and services, and where climate-related risks such as heavy rainfall, floods and landslides can affect both rural and urban livelihoods.

- CMAC Cusco is active in the southern highlands, a region characterised by significant altitude variation and climate sensitivity, where agricultural activities and small enterprises may be exposed to droughts, rainfall variability and extreme weather events.

- CMAC Piura operates in the northern coastal region, which is particularly exposed to climate variability and extreme events associated with El Niño, including intense rainfall and flooding with potential impacts on economic activity and credit portfolios.

The selection and prioritization of CMACs for more in-depth work will nevertheless be informed by the results of the diagnostic phase and validated through objective criteria related to climate exposure, portfolio characteristics, data availability and operational readiness.

This Step will end up with a Workshop, where the consultants will be able to share the diagnostic and its finding, in order to discuss outcomes, validate findings and make sure to capture all relevant information.

Following this discussion, selected CMACs may be more closely engaged in:

- Product-insurance alignment analysis (at client level)

- Operational feasibility assessment (at both institutional and client level)

- Exploration of feasible risk transfer solutions at both institutional (CMAC portfolio-level) and client level, including solutions for CMAC borrowers distributed through CMAC channels.

- Targeted client-level qualitative analysis, including focus group discussions with selected borrower segments, with the objective of deepening the understanding of client-level climate risk exposure, coping mechanisms and insurance access constraints, and informing the subsequent feasibility assessment and potential future product design.

4.3 Deepen the analysis with selected CMACs and propose preliminary product design

The Consultant is expected to work more closely with the prioritized CMACs to refine portfolio diagnostics, assess operational and data readiness, and inform the feasibility assessment of potential risk transfer solutions.

Building on the diagnostic and analytical work conducted under previous components, the assignment will explicitly identify and assess feasible climate risk transfer solutions for the selected CMACs (client and portfolio level).

This assessment will focus on identifying solutions that are technically, operationally, regulatorily and commercially feasible within the Peruvian context, rather than on theoretical or best-case designs.

The analysis will include, but not be limited to:

- Identification of risk transfer mechanisms that could realistically be offered to:

  - CMAC clients (e.g. agricultural and MSME borrowers, including an assessment of differential suitability and access constraints for underserved groups).

  - CMAC institutions (e.g. portfolio-level protection against systemic climate shocks)

- Assessment of feasibility dimensions for each shortlisted solution, including:

  - Technical feasibility (data availability, trigger robustness, basis risk):

    - High-level assessment of basis risk exposure and operational implications, including scenario-based analysis to understand potential mismatch between insurance triggers and actual client or portfolio losses.

    - Indicative assessment of claims settlement timelines ("time-to-payout") and alignment with CMAC credit repayment cycles, to evaluate whether potential payouts could effectively support client repayment capacity and CMAC liquidity needs.

  - Operational feasibility (capacity to bundle insurance with credit, alignment between credit repayment cycles and climate risk windows, client price elasticity and affordability constraints, distribution through CMACs, systems readiness, etc…)

    - Exploration of premium financing modalities and affordability pathways, including options such as bundling premiums within credit products, phased payment structures, or potential public-private support mechanisms, and assessment of operational and regulatory implications.

- IT constrainst: Assess the capability of CMAC core banking and management systems to Integrate insurance-related processes and to Incorporate georeferencing into client profiles, where required for parametric insurance solutions

  - Regulatory and prudential feasibility, including high-level assessment of how risk transfer solutions may interact with provisioning practices, capital treatment, and regulatory requirements applicable to CMACs.

  - Commercial feasibility and market appetite from insurers and reinsurers

  - Inclusion feasibility: ability to reach underserved groups without exclusion (distribution, documentation requirements, product simplicity, claims process)

- Identification of constraints and limiting factors, such as:

  - Data gaps

  - Affordability thresholds

  - Operational complexity

  - Market capacity

- Differentiation between: Solutions that could be considered in the short term and solutions that may require additional enabling conditions (data, capacity, partnerships) in the medium term may be mentioned. The output of this component will be a shortlist of feasible risk transfer solutions, clearly articulated and justified, to inform subsequent decision-making by FEPCMAC and its partners and assessing feasibility, the analysis should explicitly distinguish between risks currently absorbed through internal provisioning practices and residual risks that may require external risk transfer solutions.

This component does not entail detailed product design, detailed pricing or contractual structuring.

4.4 High-level Implementation Roadmap

For the feasible risk transfer solutions identified above, the assignment will propose an indicative implementation roadmap, aimed at supporting informed decision-making rather than committing to implementation.

The roadmap will outline:

- Required institutional capacities at FEPCMAC and CMAC level

- Key partnerships and roles (insurers, reinsurers, data providers, public stakeholders)

- Potential financial support and premium financing structures, including roles of public actors, donors, or blended finance mechanisms where relevant

- Regulatory and policy considerations

- Indicative phasing and sequencing of next steps beyond the scoping phase

Next Steps and Link to Phase 2

Based on the outcomes of this scoping phase, FEPCMAC and IDRIMA may jointly launch a Phase 2 - Product Design and Structuring assignment, aimed at:

- Developing and testing pilot risk transfer solutions.

- Identify an economic model for risk transfer solutions and potential financial support for implementation if needed.

- Capacity building support to FEPCMAC and CMACs.

5. Deliverables and Timeline

The selected Service provider(s) will be expected to produce the following deliverables as part of this assignment.

Deliverable 1 - Inception Report

Description
An inception report confirming the proposed analytical approach and methodology for the assignment, including:

- Refined methodology and scope of work

- Detailed work plan and timeline

- Stakeholder mapping and engagement strategy with CMACs

- Overview of data sources to be mobilised and initial data gaps

- Initial analytical hypotheses regarding climate risk exposure and potential risk transfer pathways

The inception report will serve as a reference document to align expectations between FEPCMAC, AFD, IDRIMA and participating stakeholders.

Deliverable 2 - Climate Risk and Portfolio Diagnostic Report

Description
A diagnostic report presenting the core analytical findings of the assignment. The report will include:

- Assessment of climate-related risks affecting CMAC credit portfolios and, in an indicative manner, CMAC clients, Climate risk profiling and vulnerability analysis across regions and sectors

- Analysis of historical climate events and their financial impacts on CMAC portfolios (e.g. non-performing loans, liquidity stress)

- Mapping and assessment of available climate, hazard and portfolio data relevant for insurance purposes

- Identification of key data gaps, constraints and enabling factors for insurance feasibility

- Gender and social inclusion implications of climate exposure and risk transmission” (1–2 pages max)

Building on the diagnostic analysis and the outcomes of the in-person diagnostic workshop, the report will also:

- Present a structured, transparent and evidence-based prioritization of a limited number of CMACs (approximately three) to be more closely engaged in subsequent analytical and solution-focused work

- Clearly document the criteria used for CMAC prioritization (e.g. climate exposure, portfolio composition, data availability and quality, operational readiness, ability to reach underserved client segments)

Deliverable 3 - In-person Diagnostic Workshop (Focus Group with CMACs)

Description
An in-person workshop bringing together FEPCMAC, AFD, IDRIMA, CMACs and relevant stakeholders, designed as a structured focus group to inform and enrich the diagnostic process.

The objectives of the workshops are to:

- Share and discuss the preliminary findings and hypotheses from the diagnostic analysis

- Collect CMAC-level qualitative insights on:

  - climate risk exposure and transmission mechanisms

  - portfolio sensitivity and client vulnerability

  - operational constraints and data availability

- Validate and refine the analytical assumptions, data interpretation and diagnostic narratives used

- Discuss and refine the criteria for prioritizing CMACs for deeper analytical engagement

- Exchange on preliminary insights regarding feasible climate risk transfer mechanisms at both client and institutional levels;

- Identify key knowledge gaps, data constraints and operational considerations to be addressed in the subsequent feasibility and solution assessment phase;

- Align on analytical priorities and sequencing for the next phase of work, including the scope and focus of targeted post-prioritization client-level analysis

The workshop will directly inform:

- the finalization of the diagnostic findings

- the evidence-based prioritization of CMACs

- the focus of subsequent feasibility and solution assessment work

Deliverable 4 - Feasible Risk Transfer Solutions Assessment

Description

The report will include a structured insurance solution mapping and stocktake, covering both existing and potential client-level and institutional-level insurance and risk transfer mechanisms relevant to the selected CMACs.

The report will provide a structured assessment of climate risk transfer options at both client level and institutional (CMAC portfolio) level, and will include:

- Identification and assessment of client-level and institutional-level risk transfer mechanisms relevant to selected CMACs

- Analysis of technical, operational, regulatory and commercial feasibility for each solution

- Indicative analysis of trigger performance, basis risk considerations and expected payout timelines, and implications for operational usefulness in supporting loan repayment continuity and institutional liquidity

- Product-insurance alignment analysis across CMAC credit products

- Assessment of potential premium financing approaches, including implications for client affordability, credit product integration and CMAC operational processes

- Assessment of CMAC operational and systems readiness (including core banking and georeferencing capacity)

- Targeted international benchmarking of relevant climate and parametric insurance approaches

- Identification of constraints, limiting factors and enabling conditions

- GESI screening of shortlisted solutions

Deliverable 5 - Feasibility, Recommendations and Roadmap Report

Description
A consolidated final report synthesizing the full set of analytical findings generated throughout the assignment, and translating them into clear conclusions, strategic recommendations and an actionable implementation roadmap.

The report will also include a high-level assessment of regulatory and prudential considerations related to the proposed risk transfer solutions, including how potential insurance payouts may interact with CMAC provisioning practices and support financial resilience in the event of climate-related portfolio shocks.

Indicative Deliverable Timeline Summary

| Deliverable | Timeline |
| --- | --- |
| Inception Report | 3 weeks after contract signature |
| Climate Risk & Portfolio Diagnostic Report (incl. CMAC prioritisation and Targeted Client-Level Analysis) | By end August 2026 |
| In-person Diagnostic Workshop (Focus Group with CMACs) | September 2026 |
| Feasible Risk Transfer Solutions Assessment | End October 2026 |
| Feasibility, Recommendations and Final Report | End November 2026 |

6. Qualifications and Experience

The service provider(s) must demonstrate qualifications and experience aligned with the scope of this assignment (diagnostic, feasibility assessment and identification of feasible climate risk transfer solutions for the CMAC system in Peru).

6.1 Core Expertise Requirements

a) Climate Risk Transfer / Insurance Expertise (inclusive focus)

Proven experience in assessing, structuring or advising on climate-related risk transfer solutions (including agricultural insurance and/or parametric/index-based approaches), with demonstrated capacity to translate climate risk into practical insurance mechanisms and feasibility conditions.

Minimum 7- 10 years of relevant experience (depending on role in the consortium).

b) Risk Diagnostics for Financial Institutions (portfolio lens)

Demonstrated experience in conducting diagnostics that link external shocks (including climate shocks) to financial institution performance, including:

- credit portfolio vulnerability analysis

- stress events impact assessment (e.g., NPL spikes, liquidity stress)

- sector and geographic concentration analysis

Experience working with microfinance institutions or retail financial institutions serving vulnerable segments is strongly preferred.

c) Peru / Latin America Context and Regulatory Awareness

Strong understanding of the Peruvian (or Latin American) context relevant to the assignment, including:

- insurance market dynamics and distribution practices

- basic regulatory landscape and stakeholder ecosystem (e.g., SBS and relevant public entities)

- Local presence or demonstrated delivery capacity in Peru is an asset.

d) Data and Analytics for Climate Insurance Feasibility

Demonstrated ability to mobilise and work with climate/hazard and exposure data (e.g. meteorological, geospatial, historical loss proxies) and to assess data readiness for feasibility of insurance solutions (including parametric triggers and basis risk considerations). This includes the ability to conduct a data mapping and gap analysis aligned with insurance feasibility.

6.2 Team Composition Requirements

The proposed team should cover the competencies needed to deliver the ToR deliverables (diagnostic → workshop → feasibility & shortlist of feasible solutions → recommendations and roadmap). The team structure may vary depending on whether the proposal is submitted by a single entity or a consortium; however, the service provider(s) should ensure the availability of the following functions:

a) Team Leader / Project Manager (Risk Transfer & Feasibility Lead)

Senior profile with proven experience in climate risk transfer and feasibility assessments, responsible for overall delivery quality, coherence across deliverables and coordination with FEPCMAC/AFD/IDRIMA.

b) Climate Risk & Data Analytics Specialist

Profile responsible for climate hazard profiling, vulnerability analysis, data mapping and gap analysis (including parametric trigger feasibility, basis risk considerations, and data requirements).

c) Financial Institution / Portfolio Risk Specialist

Profile responsible for CMAC portfolio diagnostics, linking climate events to credit portfolio outcomes (e.g. NPLs, liquidity stress), and supporting CMAC selection/prioritization criteria.

d) Market & Distribution / Insurance Practitioner (optional but recommended)

Profile with practical understanding of insurance market operations, distribution and servicing models relevant for CMAC channels (can be insurer/broker/technical expert).

6.3 Relevant Track Record Requirements

a) The service provider(s) should present evidence of at least three (3) comparable assignments completed within the last five (5) years in one or more of the following areas:

- climate risk transfer solutions and feasibility assessments

- agricultural insurance and/or parametric insurance feasibility

- diagnostics linking external shocks to credit portfolio performance

- insurance distribution through financial institutions / bancassurance / embedded insurance

- data readiness assessments for climate insurance solutions

b) Experience delivering assignments in Peru (preferred) or Latin America (strong advantage).

c) Demonstrated ability to mobilise an appropriate team and to conduct field-based or stakeholder-based work across relevant regions (as required by the diagnostic and CMAC prioritisation component).

d) Ability to provide references from previous clients for similar assignments.