## 230 días
Budget - USD Name of the contract
CONSULTANCY FOR THE DESIGN AND DEVELOPMENT OF A SYSTEM (METHODOLOGICAL AND COMPUTER) FOR THE IDENTIFICATION, MONITORING AND IMPLEMENTATION OF CONAFIPS' GREEN CREDITS FOR BIOECONOMY AND CLIMATE CHANGE | [10 empty] | Expert | Title (ex. Senior Consultant, junior consultant, Project manager…) | Price by day, all costs included (USD Exc. VAT)
Name of the Contractor :
POR DEFINIR |  | To fulfill | [8 empty] | Expert 1 | Coordinador de proyecto
[11 empty] | Expert 2 | Experto indicadores
| Price per deliverable | [9 empty] | Expert 3 | Experto bioeconomía
[8 empty] | Subtotal by days | Costs (USD Exc. VAT) |  | Expert 4 | Experto huella de carbono
| Coordinador de proyecto | Experto indicadores | Experto bioeconomía | Experto huella de carbono | Experto desarrollador senior | Experto Desarrollador | Experto analista de datos |  |  |  | Expert 5 | Experto desarrollador senior
Phase I | [10 empty] | Expert 6 | Experto Desarrollador
Deliverable 1- Conducting the information gathering process, initial diagnosis, and preliminary definition of indicators and eligibility criteria for the green credit modules.. | [7 empty] | 0 | 0 | 40 | Expert 7 | Experto analista de datos
Phase II
Deliverable 2- II. Development of the comprehensive methodology, variable matrix, wireframes, and validation/QA rules for the system.. | [7 empty] | 0 | 0 | 105
Phase III
Deliverable 3- Design of the technical architecture, data model, security framework, and required specifications for integrating the application with CONAFIPS’ infrastructure.. | [7 empty] | 0 | 0 | 195
Phase IV
Deliverable 4- Development of the web/mobile modules and the methodological engine, including the generation of the testing dataset and the preliminary administrative manual. | [7 empty] | 0 | 0 | 230
Phase V
Deliverable 5- Execution of the pilot phase with selected users, implementation of improvements, and methodological updates prior to final deployment.. | [7 empty] | 0 | 0 | 270
Phase VI
Deliverable 6- System go-live with backup and monitoring mechanisms, accompanied by functional and technical training for CONAFIPS and full technology transfer. | [7 empty] | 0 | 0 | 300
Total (days) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Price (USD excluding taxes) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Price - Excluding taxes (USD) | [8 empty] | 0
[8 empty] | Tax (%) | 0%
Total Price - Including taxes (USD) | [8 empty] | 0
Important Note – Financial Offer
Please complete this financial offer in USD, in accordance with the explanations provided in the Terms of Reference. The consultancy budget — including professional fees, administrative costs, logistics, travel, profit, and other associated expenses — is calculated on the basis of person‑days effectively reported. For administrative and contractual purposes, the total number of person‑days assigned to the consultancy corresponds to a maximum of two hundred and thirty (230) working days of consulting effort. In line with this, the financial proposal must be structured strictly on the basis of the 230 person‑days established, and the total amount offered may not exceed the value resulting from this allocation. Prices must be expressed excluding taxes (USD Exc. VAT), with the applicable tax percentage indicated separately. The financial offer must be consistent with the technical proposal, including profiles, phases, and deliverables.