# Specifications

- General information

| # Assignment name | # Execution of a feasibility study for a solicited Public-Private Partnership Project in the Solid Waste Management Sector - (Philippines) |
| --- | --- |
| # Beneficiary | # PPP Center and 3 LGUs |
| # Country | Philippines, Mindanao region |
| # Total estimated duration | # 12 months |

- Context and justification of the need

The Project context

The purpose of the EU-PH Partnership for Green Economy Programme is to support the Philippines’ transition towards a green economy, including circular economy, reducing waste and plastic, as well as to increase energy efficiency and renewable energy deployment to support climate change mitigation.

The action tackles three main levels:

- Establishing a Policy Dialogue Platform at central government level to facilitate policy formulation, improve city to city collaboration through supporting the development of a National Circular Economy Strategy and Roadmap, extend dialogue to promote renewable energy/energy efficiency and to apply the dialogue’s outcomes (linked to Specific Objective 1 of the action);

- Working with Local government units (LGUs) to define and implement circular economy, climate change and energy policies with a human rights and gender - responsive perspective, including outreach and support of local business and civil society (linked to Specific Objective 2 of the action);

- Enhancing engagement of the private and financial sectors into the circular waste economy creating better conditions for private sector investment by supporting business driven waste reduction strategies and circular solutions in the production process (linked to Specific Objective 3 of the action).

Expertise France (EF) is engaged as the implementer of Sustainable Investments related to private sector mobilisation and includes the following two outputs:

- Output: Support for the development of eco-enterprises, through entrepreneurship, innovation, and transformation of MSME’s

- Output: Support for the development of green infrastructure projects which delegate waste management services to the private sector

The output component aims to develop infrastructure and service projects in the solid waste management (SWM) sector towards the promotion of a circular economy. The project will focus on supporting the establishment of public-private partnership (PPP) projects in green infrastructure which delegate waste management services to the private sector. EF will provide expertise and finance feasibility studies in order to accompany these projects from the planning and pipeline development stage, through the transaction phase. In addition, the integration of informal waste workers (IWW) into green infrastructure projects will be taken into account throughout the implementation of project activities.

The implementation of the activities will be implemented in close collaboration with the Public-Private Partnership (PPP) Center of the Philippines. The PPP Center serves as the central coordinating and monitoring agency for all PPP projects in the Philippines. In accordance with the PPP Code and its implementing rules and regulations (IRR), the PPP Center is mandated to facilitate the implementation of the country’s PPP Program and Projects. It champions the country’s PPP Program by enabling implementing agencies in all aspects of project preparation, managing the Project Development and Monitoring Facility (PDMF), providing projects advisory and facilitation services, monitoring and empowering agencies through various capacity building activities.

The Project description // Background

As part of the EU-GEPP funding programme budget, up to 3 projects have been selected to be grant funded under the programme. The intention is to complete the feasibility stage of the projects development process and progress towards the procurement phase of a solicited PPP contract between a private party and the local government unit (LGU).  All of these LGU’s have undergone basic training on the PPP code of the Philippines and will be supported by the PPP center of Philippines and Expertise France as the development partner.

Expertise France is therefore seeking to appoint a professional and suitable joint-venture company or a corporation internationally or nationally registered with a pool of experts with the relevant competencies and expertise to conduct one to three detailed feasibility studies for the establishment of solid waste management for 3 local government units (LGUs) in order to provide solutions to manage waste disposal and diversion challenges that are currently faced by the 3 municipalities. These Feasibility studies will provide a comprehensive assessment of the project’s viability, covering financial, technical, legal, institutional, environmental and social aspects.

The 3 selected projects are based in Mindanao region and details about the precise location would be

- Objectives and desired results

  - General objective

The objective of the assignment is to support 3 selected pilot local government units (LGUs) in charge of waste services in the structuring and development of the PPP of the solid waste management infrastructure projects; by conducting detailed Feasibility studies and facilitating the establishment of commercially viable projects in solid waste management PPP, which may also serve as reference for other LGU’s in the country

  - Specific objectives

The technical support will be carried out via knowledge sharing, seminars, trainings, technical studies and LGU’s ’ team mentoring on the operationalizations of the projects.

Specific objectives are:

- Technical support to pilot projects: Determine the technical feasibility of establishing municipal solid waste management projects including waste composition, processing technologies and site suitability

- Financial viability: Assess the financial viability, including cost estimates, revenue models and funding mechanisms

- Legal, Institutional and regulatory compliance: Evaluate legal and regulatory compliance, taking into account PPP framework, environmental authorizations as well as municipal regulatory frameworks and requirements

- Risks analysis: Analyze the potential environmental and social impacts and risks, ensuring sustainable and inclusive project design, as well as key risks (technical, financial, political, environmental) and propose mitigation strategies

- Stakeholder engagement: To ensure alignment with local needs

- PPP Structure recommendation: Analyse and assess optimum PPP structure by assessing risks using the Generic Preferred Risks Allocation Matrix (GPRAM) and ensuring GEDSI integration in project implementation that are accessible, inclusive, and responsive to the needs of all individuals, regardless of gender, disability, or social status.

- Procurement: Develop the necessary documentation for procurement of the project.

  - Anticipated results

The following results are anticipated to be achieved through the present assignment:

- The technical, financial, marketing, legal and environmental requirements to support the project design and implementation of the SWM PPP project have been assessed

- An optimal, bankable PPP project structure and governance model signaled by market acceptability), taking into account risk and mitigation measures has been shared with stakeholders

- The procurement plan is produced and outlined timelines, budget and procurement strategies to support the next implementation phase of the project with procurement-ready project documents,

- Phases and deliverables mentioned in these technical specifications (TORs) are validated by stakeholders and additional deliverables to achieve the required feasibility study are identified,

- The assignment result in a clear assessment of how the SWM project will contribute to the local economy, including green growth and job creation whilst considering GEDSI inclusion

- Description of the assignment

  - Planned activities

The service provider must support the implementation of Output 2 interventions in line with the overall work plan and defined methodology in order to perform the following activities:

Part I: Inception report

The service provider must prepare an Inception report containing, among others, a detailed plan of approach, methodology and work plan covering a two-months initial period and taking into consideration key findings (e.g. critical issues to be addressed) from a first review of all existing documentation including project concept notes, solid waste management plans among others and covering the first field mission.

- Activity 1: Field mission and inception report

A first field mission as well as Inception Report should be produced with the following information:

- Review of LGU’s Project concept Notes, Site Mission reports and checklist, and other LGU supporting documentation and data gap analysis,

- General Project Information and Objectives

- Performing a regulatory mapping exercise as per RA11966

- Key observations and recommendations for the implementation of the Feasibility Study schedule and Activities

- Set up of the Document Control and Database management system

The Document Control System shall ensure systematic creation, review, approval, version control, storage, retrieval, archiving, and disposal of Project Documents; provide a single source of truth for all Project Documents; maintain a complete and auditable record of document revisions, approvals, and access history.

The Database Management System shall: support role-based access rights and permissions; allow controlled data sharing and collaboration between Project Participants; be compatible with commonly used industry platforms and file formats; enable data export in non-proprietary formats upon request by the Authority.

- Full project management and organization information (organizational chart)

- Inception mission key findings, including confirmation of Plan of Approach, Methodology and Feasibility Study Project Schedule with clear Critical Path Milestones outlined. A separate Log for Issues and Recommendations is to be included.

- Draft Monitoring and Evaluation Framework including data collection and alignment with LGUs from inception meetings

- Cost Breakdown/Payment Milestones and detailed reporting in the next 12 months

Part II: Feasibility study

The scope of the feasibility study will take into account the pre-feasibility Project Concept Notes that have been produced by the LGU’s including the Technical Checklists, Site Mission Reports and other supporting documentation provided by the LGU. The consultant is to update the information, incorporate into the Feasibility Study Document Control and Database System and fill the necessary gaps in alignment with the Philippines PPP Code and Guidelines (Republic Act No. 11966) including the following phases:

- Activity 2: Situational analysis

The service provider will conduct an in-depth analysis/study into the current state of waste management across the selected municipalities including the description of available infrastructure, and socio-economic conditions and producing a mapping of the study area.

The analysis must quantify the waste generation, recycling, and disposal while assessing the capacity of existing municipalities and barangays. This includes an assessment of quantities and types of waste that are generated in the areas accounting for seasonality and a wholly representative sample from within the waste generation and collection areas. The assessment of the existing facilities (both municipal and private) and a description of the services that are provided for the collection, minimization, reuse, recycling and recovery treatment and disposal of waste is developed. Financial and human capital including waste infrastructure and equipment will also be listed and analyzed.

Furthermore, the service provider will benchmark these findings against national and international best practices to establish a clear baseline.

The service provider must analyse and recommend optimum PPP Structure by assessing risks using the Generic Preferred Risks Allocation Matrix (GPRAM) and ensuring GEDSI integration in project implementation that are accessible, inclusive, and responsive to the needs of all individuals, regardless of gender, disability, or social status.

- Activity 3: Needs analysis

Building on the situational analysis, the service provider will perform a Needs Analysis to define the project's scope and ensure it aligns with local and national policies.

This activity includes:

- Projecting future waste generation rates based on population growth and industrial activity, existing and future planned waste policies such as EPR legislation (The EPR Law in the Philippines, Republic Act No. 11898)

- Assessing existing financial resources, including historical, present and forecasted budgets for the full value chain of waste collection and management, including capital and operational costs for landfill operations, logistics and human resources,

- Identifying all current sources of revenue received by the LGU from waste operations, including, amongst others, National Government budget allowances, waste collection fees from residential and commercial tariffs, recyclable material recovered,

- Identifying service delivery gaps,

- Conducting a Cost-Benefit Analysis and test if the solution has Value for Money to society in socio-economic terms,

- Reviewing the institutional arrangements in the municipality, including human resources and capacities to develop and implement the project, review of related asset registry and third party service providers, based on the results of consultation of key stakeholders for the project, including informal waste workers and other community service organisations and non-governmental organisations. (The IA’s commitment and capacity must be outlined by establishing the numbers and cost of existing institutional staff that will be affected in each solution option, conducting a skills and experience audit, and establishing the key human resources requirements for the development and implementation of the project)

The result is a comprehensive SWOT analysis that identifies the requirements the solid waste management project must meet to serve the community effectively.

- Activity 4: Project Due Diligence (Legal, Environmental, Health and Safety)

The Service provider performs a rigorous due diligence process to uncover any legal, financial, or technical issues that could impede project closure.

This includes verifying:

- Legal requirements for the project including necessary licensing/permitting requirements,

- Review procurement legislation and outline necessary approvals for PPP processes

- Land tenure review (land ownership and site acquisition risk)

- Environmental compliance

- Socio-economic issues.

- Activity 5: Technical feasibly assessment

This critical phase involves several technical studies.

- First, the service provider performs a waste characterization study to determine the composition, calorific value, and seasonal variations of the waste stream.

- Simultaneously, a site selection exercise is conducted to identify potential locations based on proximity to waste sources, landing availability, zoning regulations and geological stability, accessibility to utilities and environmental sensitivity. A preliminary geotechnical and hydrological assessment on the preferred site will be conducted.

- The service provider will deliver a technology assessment which evaluates and benchmarks various waste processing technologies (such as Material Recovery Facilities, Composting, or Waste-to-Energy, Landfilling) to recommend the most suitable mix in terms of efficiency, costs and environmental impact based on waste composition and local conditions, whilst always applying the principles of adoption of a Circular Economy and the waste hierarchy.

- Finally, a conceptual engineering design for the project is developed, including layout, utility and human resource requirements, and pollution control measures, amongst others. This will include a functional and reference basic design with key design requirements and cost estimated data that will feed into the financial model including asset maintenance and operation of the project concession term.

- Activity 6: Solutions options analysis

The service provider will identify and weigh various technical and financial options for delivering the project. This involves assessing each option’s advantages, risks, and financial impacts through a matrix approach including:

- Alignment of each solution with the concerned LGU,

- Preliminary view of financial impacts, affordability, payment mechanism and funding models,

- Previous discussions with the LGU and other key stakeholders, and solutions analysis for the impact of each option on the socio-economic aspects,

- Possible technology services and advanced technologies and their potential,

- Compliances with all local and national relevant legislation and regulations, whilst also aligning to global best practices and regulations,

- Number and estimation of existing institutional staff and estimate of the number of new jobs opportunities

- Private-sector value drivers and main financial and operational constraints companies might face in participating to this project,

The analysis must consider how different technologies might stimulate economic productivity and ensure the project remains commercially viable and attractive to the market, focusing on PPP method to deliver value for money compared with a conventional procurement choice.

It should examine other spin-off effects and development benefits derived from the project, such as reduced air pollution, improved safety, and energy efficiency attributable to the installation of the project.

- Activity 7: Service delivery analysis

This deliverable focuses on how the project should be managed. The service provider evaluates both internal and external service delivery mechanisms, reviewing options previously considered by the municipalities to recommend the most efficient model for the execution of the SWM project.

- Activity 8: Market and stakeholder analysis

To ensure the project is bankable, the Service provider conducts market sounding exercises through meetings with private sector players including local communities, junk shops and buy back centers, community service organisations and non-governmental units active in the sector, and industry benchmarks to capture the potential investor’s perspectives of the project.

This task should also analyze the demand for recycled materials or energy in the LGU, and identify potential off-takers and competitors.

- Activity 9: Value and risk assessment

A core component of the feasibility study is the comparative assessment of procurement choices. The TA constructs a Public Sector Comparator (PSC) and a PPP reference model to determine which approach offers better Value for Money.

This involves developing a detailed financial model, including CAPEX and OPEX estimations, revenue stream projections (gate fees, sale of recovered materials, energy sales or carbon credits) and land acquisition costs, operations and maintenance as well as tariff modeling.

A comprehensive risk matrix to allocate costs and responsibilities between the public and private sectors. The cost estimates shall be based on the outcome of the previous deliverables, based on historical data and quotations received from suppliers and similar projects and international suppliers.

The construction of the PPP reference model will be done by:

- Confirming the type of PPP and contractual arrangement options (or assess the proposed contractual arrangement)

- Describing the processed PPP project structure and funding sources, closely linked to the project type including aspects of whether the project is most suitable for project or corporate finance funding and likelihood of raising debt and equity, and testing market appetite specific project risks,

- Developing the core components of the payment mechanism,

- Incorporating full project life cycle costing, maintenance and operating costs,

- Calculating and consolidate all costs,

- Constructing the PPP reference model and explaining all assumptions and indicators.

An initial Value-for-money test, conducted with the prescriptions of Republic Act (RA) No. 11966 or the PPP Code of the Philippines, should:

- -Define in terms of cost, price, quality, quantities and risk transfer or a combination thereof by comparing conventional procurement with a PPP reference model,

  - Conduct an analysis and estimate the projects NPV, IRR and weight average cost of capital (WACC) which shall be computed on an after-tax-basis in real terms using constant prices,

  - Convert the cost estimates and financial projections from nominal to real terms,

- -Prepare a Financial Model (Sponsor and Lender case), including Income Statement, Balance Sheet and cash flow Forecasts, highlighting clearly all assumptions made

- -Recommend the procurement choice

- -Verify the information used and sign off in the feasibility study

- Activity 10: Economic and socio-economic impact analysis

The service provider evaluates the project’s broader impact on the local economy using a social accounting matrix. Key tasks include assessing:

- The project’s contribution to GDP, estimation of the economic internal rate of return (EIRR), and the economic valuation of environmental impacts. The assessment of EIRR shall be guided by generally accepted benchmarks for economic viability of public investments, consistent with the principles under the PPP Code and its IRR and relevant national appraisal guidelines, recognizing that acceptable thresholds may vary depending on sectoral context and the project’s social and environmental benefits.

- A sensitivity analysis to assess the effects of changes in project costs, energy quantities, recyclable sales and how implementation delays affect the economic outcome.

The study must focus on several key developmental pillars:

- Prioritizing skills transfer, talent development, and human capacity building, aligned to GEDSI inclusion

- Assessing the project's role in local manufacturing, industrialization, and the transformation of spatial land-use.

- Specifically measuring contributions to job creation, poverty alleviation, and the empowerment of vulnerable groups.

- Providing decision-makers with a view of the project's potential to drive technology transfer and productivity improvements

Activity 11: Stakeholder engagement analysis with project structuring – Stakeholder Engagement Plan

The service provider must develop a Procurement plan demonstrates that the implementing agency has the capacity, resources, and governance mechanisms to carry out the PPP procurement process. At minimum, it should include:

- Project Timeline & Milestones: Clear schedule from project preparation to approval and contract implementation

- Budget Confirmation: Proof of sufficient funds allocated to support the project through procurement and implementation.

- Risk Management: Identification of potential challenges with strategies for mitigation.

- Procurement Approach: Best practices and procedures tailored to the project’s type and structure.

- Governance & Decision-Making: Defined processes for institutional oversight and approvals.

- Stakeholder Engagement: Identification of stakeholders and their role in the PPP process.

- Project Team: Clear assignment of functions and responsibilities.

- Information Disclosure: Categories of data to be shared with bidders and how these will be prepared.

- Approvals: List of required internal and external authorizations.

- Detailed Schedule (e.g., GANTT Chart): Covering procurement documentation, land acquisition, environmental studies, and related approvals.

- Contingency Planning: Measures for deviations in budget or timeline.

- Bid Evaluation: Defined process and evaluation teams.

- Quality Assurance: Systems for reviewing procurement documentation.

- Audit Trail: Mechanisms to ensure transparency and accountability.

- Integrity Safeguards: Security, confidentiality agreements, anti-corruption measures, and conflict-of-interest declarations.

In addition, the service provider shall provide a Stakeholder Engagement plan and perform an in-depth analysis of each of participating organisations involvement in the project (Stakeholder Engagement Study), including the public and private sectors and formulate an appropriate project structure based on the participating LGU, including regulatory requirements, funding and operating model. It shall assess the following:

- Job creation opportunities vs potential displacement of informal waste workers,

- Opportunities for youth, women and disabilities in waste management,

- Waste and salaries;

- Community benefit-sharing

- Activity 12: Draft Procurement and Project Implementation plan

The service provider develops a detailed roadmap for the project’s rollout, including a Procurement Plan that sets out timelines and strategies for the SWM projects. The service provider is tasked with developing a plan that demonstrates the municipality have the necessary budget and capacity to undertake the procurement. This plan must explicitly set out the timelines, processes, and strategies for the bidding phase.

An Implementation Plan will outline every step from financing and civil works to equipment procurement and synchronization, providing a tentative schedule of milestones including:

- Outlining the steps for financing, facilities management, civil works, construction, and the procurement and synchronization of equipment and furniture’s

- Establishing a tentative timeline for when key milestones should be achieved.

  - Providing a detailed methodology explaining how the requirements of the Scope of Work will be achieved systematically. This includes an activity plan that specifies:

  - The approach (how tasks will be done and by whom).

  - The specific project resources required.

  - An itemized budget breakdown directly linked to the expected deliverables,

Activity 12: Final Procurement Strategy and Procurement Plan

The service provider should incorporate the outcomes of stakeholders consultations, which are to be carried out in line with PPP Center guidelines. The identified stakeholders may include facility users. The team are responsible for :

  - Identify consultation needs and prepare data collection tools

  - Conduct consultations with stakeholders

  - Synthetize their feedback and propose recommended revisions,

  - Review and present the existing draft of the Porcurement strategy and plan

Activity 13: Draft Bid Documents and Concession Agreement

Based on previous results and recommendations, the consultant will draft a complete set of bid documents and the concession agreement in line with the applicable national PPP Code. The bid documents will define the procurement structure, eligibility criteria, evaluation methodology, risk allocation, and key contractual obligations. The concession agreement will translate the agreed structure and risk distribution into a binding contractual framework between the LGU and potential private partners.

The expert will :

  - define the procurement approach,

  - prepare draft bidding documents, including instructions to bidders, evaluation criterai, draft technical schedules, and transation timelines,

  - develop the draft concession agreement, including key schedules and annexes

  - Ensure consistency between the bid documents and the concession agreement.

- Activity 14: Draft of Feasibility Study

All findings are compiled into a high-quality, comprehensive Draft Feasibility Study Report. This report must be accompanied by an executive summary and a PowerPoint presentation for the project decision-makers and Steering Committee members.

- Activity 15: Final feasibility study

After an initial period of review and consideration of comments from the project's technical team and the Project Steering Committee provided within 45 days, the completion of the study will be managed by the service provider and conclude with a close-out meeting with the submission a Final Feasibility Study Report, summarizing the assignment's outcomes and handing over all project property.

  - Anticipated deliverables

Please refer to the table below as an indicative timeframe for the assignment.

| Deliverables | End date |
| --- | --- |
| - Deliverable 1 (for Activity 1): Inception report Review of submitted concept notes and develop a detailed plan of approach, methodology and work plan covering a two-months initial period and taking into consideration key findings | T0 + 1 month |
| - Deliverable 2 (Activity 2 - 5): Technical feasibility assessment & Due Diligence This critical phase involves situational analysis and needs analysis, comprehensive technical analysis and design | T0 + 3 months |
| - Deliverable 3 (Activity 5-13): Procurement and implementation plan Develop a plan that demonstrates the LGU have the necessary budget and capacity to undertake the procurement, including solution option analysis, service delivery options analysis, market analysis, due diligences, value assessment, risk assessment, economic and socio-economic impact analysis | T0 + 9 months |
| 4. Deliverable 4 (Activity 14): Draft Feasibility Study Report with an executive summary and a PowerPoint presentation for the project decision-makers and Steering Committee members. | T0 + 10 months |
| - Deliverable 5 (Activity 15): Final feasibility study Review of comments and completion of the study, including transfer of the project property | T0 + 12 months |

  - Coordination

In addition to the above scope of works, the Consultant shall: work closely with the Expertise France and the Philippines PPP Center, through their respective Project Managers or designated representative, provide comments on presentation materials and proposed responses to stakeholders’ queries, prepare highlights and/or minutes of all major meetings. The Consultant, for the duration of its contract, shall make its team available to receive comments or queries and provide responses thereto, and entertain consultations from concerned stakeholders. This may entail holding meetings through video/ teleconference, except in activities where the physical presence of the expert/s is required.

The service provider shall designate a single contact person for project implementation purposes. The Output Leader will be the service provider’s primary contact person for Expertise France. The designated Project Steering Team will also include representatives from the PPP center and the LGU.

A launch meeting shall be held approximately 2 – 5 days after the contract award has been notified. Close collaboration must take place with the project team based in Manila, the support team from EF headquarters in Paris, the Philippines PPP Center personnel and the designated LGU representative, from assignment preparation right up to completion.

- Place, duration and terms of performance

  - Implementation period			: 12 months

  - Start date				: 01 August 2026

  - End date				: 31 July 2027

    - Effective duration per assignment	:  Please refer to the table below for the indicative duration per assignment

  - Schedule/programme:

The provisional programme for assignment implementation is as follows:

| Activity | Place | Period | Duration (man/days) Indicative |
| --- | --- | --- | --- |
| Activity 1: Review of submitted concept notes and develop a detailed plan of approach, methodology and work plan covering a two-months initial period and taking into consideration key findings | Remote + Field Mission to the LGU | August-September 2026 | 60 |
| Activity 2: A situational analysis will deep-dive into the current stage of SWM and describe available infrastructure and socio-economic conditions. | Remote | September 2026 | 60 |
| Activity 3: A needs analysis is performed to define the project scope and ensure it aligns with municipal policies | Remote | October 2026 | 60 |
| Activity 5: Technical feasibility assessment phase involves a waste characterisation study, a site selection exercise and recommend the most suitable mix | Remote + Field Mission to the LGU | September 2026– July 2027 | 80 |
| Activity 6: Assess each option’s advantages, risks, and financial impacts through a matrix approach | Remote | December 2026 | 60 |
| Activity 7: Evaluate both internal and external service delivery mechanisms, reviewing options previously considered by the municipalities to recommend the most efficient model | Remote | December 2026 | 20 |
| Activity 8: Conduct market sounding exercises through meetings with private sector players | Remote + field missions to Philippines | December 2026- January 2027 | 40 |
| Activity 9: Project due diligences process is lead to uncover any legal, financial, or technical issues that could impede project closure including land use and zoning | Remote | January –February 2027 | 60 |
| Activity 10: Core component of the feasibility study including comparative assessment of procurement (PPP reference model) choices including detailed financial modeling, CAPEX and OPEX estimations, revenue stream projections and a comprehensive risk matrix | Remote | January- March 2027 | 120 |
| Activity 11-13: Develop a plan that demonstrates the municipality have the necessary budget and capacity to undertake the procurement, including solution option analysis, service delivery options analysis, market analysis, due diligences, value assessment, risk assessment, economic and socio-economic impact analysis | Remote + Field Mission to the LGU | May – June 2027 | 90 |
| Activity 14: Draft Feasibility Study Report with an executive summary and a PowerPoint presentation for the project decision-makers and Steering Committee members. | Remote + Field Mission to the LGU | January - June 2027 | 220 |
| Activity 15: Final Feasibility Study Report including recommendations and feedbacks from the Steering committee members, developing annexing and delivering all the required documentation | Remote + Field Mission to the LGU | January - June 2027 | 60 |
| Total | Remote + Field Missions | 01 August 2026 – 31July 2027 | 930 |

- Required expertise and profile

The selected service provider must possess strong expertise in solid waste management (SWM), circular economy, and Public-Private Partnerships (PPP), particularly in the context of infrastructure project development, feasibility studies, and capacity building for local governments. The expert(s) must also demonstrate experience in working with international development projects, private sector engagement, and public-sector institutions, ideally in the European and Southeast Asian region, with a focus on the Philippines.

  - Profile of the Corporation responsible for contract execution

Number of experts per assignment: Min 9 experts

Qualifications and skills

- Strong knowledge of PPP models, public procurement mechanisms, and waste management infrastructure projects

- Have conducted feasibility assessments and financial/economic analyses of infrastructure projects,

- Strong communication and facilitation experiences in delivering trainings, workshops, and technical assistance.

- Demonstrated ability to coordinate multi-stakeholder processes, including public authorities, private sector actors, and development partners.

- Proficiency in English (written and spoken) is required and local Philippines languages preferred – (required for the social engagement expertise)

General professional experience

- At least ten (10) years of experience in providing consulting services for large infrastructure projectsnd/or building construction.

- Proven experience in advising local government units (LGUs) or public agencies on waste management strategies, PPP project structuring, and policy development.

- Experience in technical capacity building, including the design and facilitation of workshops, seminars, and peer-learning events.

- Experience in working with international donors and public-sector institutions on infrastructure or waste management projects.

Specific professional experience

- At least 5 years of direct experience in solid waste management infrastructure projects, including experience with projects with a CAPEX worth over €10 million

- Previous experience in similar or infrastructure projects in the past 5 years   with preference for projects undertaken and aligned with the Philippines PPP Code at least

- Experience in supporting or advising national or local PPP Implementing Agents municipal authorities, or public institutions on PPP project identification, design, or implementation.

- Demonstrated experience in the integration of informal waste workers (IWW) into municipal solid waste management systems is an asset.

- Experience working in the Philippines, Europe or Southeast Asia is strongly preferred.

  - Profile of the designated expert(s) responsible for contract execution

| No | Position | Requirements |
| --- | --- | --- |
| 1 | PPP Expert (Team leader – option 1) | -University Master’s degree in Law, Finance, Management, Economics, Engineering or any other relevant field. - A minimum of 10 years’ demonstrated experience in providing PPP transaction advisory services/development of large infrastructure projects on PPP basis -Successful preparation of PPP projects with projects worth over €10 million in the last 5 years -Experience as team lead in a solid waste management project. Relevant qualifications and experience in the entire solid waste management value chain, particularly in collection, transportation, treatment, disposal, operation and maintenance projects. Good English communication and report writing skills are essential |
| 2 | Financial expert | - University Bachelor’s degree in Finance, Accounting, Economics or any other relevant professional qualification -At least 10 years of professional experience in PPPs and project finance, with a proven track record in financial evaluation and financial modelling of PPP projects including value for money, Public Sector Comparator analysis, affordability and fiscal impact assessment. -Demonstrated experience in dealing with project finance structures and products and experience in capital raising having financially closed to €10 million. Experience in the solid waste sector is preferred. Good English communication and report writing skills are essential. |
| 3 | PPP Legal expert | -University degree in Law and postgraduate qualification in Law -A minimum of 5-7 years demonstrated experience in drafting PPP contractual agreements (such as PPP Concession Agreement, Shareholders Agreements, and other related documents/agreements), managing bidding process, and resolving legal issues, policy and institutional assessment; and successful preparation of PPP projects with financially closed to €10 million -Demonstrated knowledge and experience of the legal, regulatory and institutional framework for PPPs in Philippines, relevant experience of public procurement/ transaction management. Experience of working in the Solid Waste and Environmental sector will be an added merit. Good English communication and report writing skills are essential. |
| 4 | Solid waste management expert (Team leader – option 2) | -Advanced university degree (Master’s or higher) in Environmental Engineering, Civil Engineering, Environmental Science, Waste Management, or a related discipline. Additional specialization in solid waste management systems, environmental infrastructure planning, or circular economy will be considered an advantage. - General Professional Experience - Minimum 10 years of professional experience in the planning, design, or technical assessment of municipal solid waste management systems. - Demonstrated experience in integrated solid waste management planning, including waste collection, treatment, and disposal systems. - Experience working on large-scale infrastructure or environmental projects funded by multilateral or bilateral development partners is desirable. -Specific Professional Experience The consultant must demonstrate experience in at least several of the following areas: - Technical Planning and System Design - Planning and technical design of municipal solid waste management systems. - Preparation or review of waste characterization studies and waste generation forecasts. - Experience with facility design or evaluation, including: - Sanitary landfills - Material Recovery Facilities (MRFs) - Composting or anaerobic digestion systems - Waste-to-Energy (WtE) or refuse-derived fuel (RDF) facilities - Waste transfer and logistics infrastructure - PPP and Project Preparation - Experience supporting PPP project preparation, feasibility studies, or transaction advisory in the waste sector. - Experience defining technical service standards, performance indicators, and infrastructure requirements for PPP projects. - Experience contributing to technical inputs for financial models, including CAPEX and OPEX estimates. - Regulatory and Environmental Compliance - Familiarity with environmental regulations and standards applicable to waste management infrastructure. - Experience incorporating environmental safeguards, climate considerations, and circular economy principles into project design. -Experience working in Europe or the Philippines is highly desirable. -Familiarity with the policy and regulatory framework governing municipal solid waste management, including relevant national legislation and standards. -Skills and Competencies - Strong analytical skills in waste system planning and infrastructure evaluation. - Ability to translate technical assessments into bankable project inputs for PPP structures. - Excellent technical writing and reporting skills. - Proven ability to work with government agencies, municipal authorities, and development partners. - Fluency in English (written and spoken) is required. |
| 5 | Land use planner | Advanced degree in physical planning (urban/land-use, environmental planner) with 7 -10 years’ experience in on land use planning for large infrastructure or environmental facilities (landfills, treatment plants, industrial zones, etc.). The expert will be responsible for site identification and suitability analysis, consistency with master plans and zoning, waste collection and logistics mapping from waste generation to waste disposal sites, interface with communities and other land uses, and stakeholder consultations. Good English communication and writing skills, especially in report writing, are essential. |
| 7 | Geotechnical Specialist-National | Advanced degree in Geology, Civil engineering or Geotechnical engineering. At least 5 years of professional experience in geotechnical engineering, including soil investigations and foundation design for infrastructure projects; experience with landfill or environmental infrastructure is preferred. Experience in Philippines is required. |
| 8 | Environmental specialist-National | Advanced degree in Natural sciences, Environmental sciences, with experience in EIA scoping for waste management, green or circular economy, environmental or geographical science, sustainability or biodiversity, conservation or industrial ecology, land use planning, integrated or organic waste systems or environmental impact systems with over 7 years of demonstrated experience in environmental impact assessment and preparation of environmental management plans/programs for PPP projects in accordance with the specific requirements and legislation in the Philippines. Experience in Philippines is required. |
| 9 | Socio-economic and gender specialist-National | University degree in Social Studies, Business Management or Administration, Public Administration, Public policy or Administration or Finance or Public Governance with 5 years demonstrated experience in assessment of social impacts including gender analysis and preparation of mitigation measures for PPP projects in accordance with the specific requirements in the Philippines. Should have thorough knowledge of the Philippine labor laws and other related laws/provisions and experience with resettlement/social safeguards planning. Local Philippines languages required. |
| 10 | Development Communication Specialist-National | University degree in Public Relations, Marketing and Communications, or similar. 5 years of demonstrated experience in public relations and preparation of public communications plan for development projects, with development projects successfully implemented. Local Philippines languages required. |

- Assignment reports

Reports developed for each specific deliverable will be reviewed by EF team for final approval of satisfactory quality of results achieved. The service provider must ensure all input, comments, and suggested revisions from EF team are incorporated in the final reports.

A final report following the model provided must be forwarded by e-mail on conclusion of the assignment. The final report must include a comprehensive narrative and reporting of all reports developed during the assignment for all deliverables.

- Monitoring-evaluation

Performance indicators

| Deliverables | Immediate effects | Verification sources |
| --- | --- | --- |
| - Deliverable 1 (for Activity 1): Inception report | The project management team is introduced. The project plan based on the inception meetings and discussions is updated. Stakeholders, main challenges of the assessment and project milestones are identified. | - Organizational chart - Project Plan - Inception report - List of attendees and minutes of inception meetings - Database and Document Control System established |
| - Deliverable 2 (Activity 2 - 5): Technical assessment analysis | Baseline data on current status of MSWM in target LGUs are analyzed. A set of potential waste treatment technologies applicable is proposed for PPP interventions in SWM for target LGUS, depending on the local context and including cost-benefits analysis. Acceptance of the deliverable. | - Situation analysis report - Needs and cost-benefits analysis Report - Waste characterization study - Comparison tools and waste processing technology list - Site selection study report |
| - Deliverable 3 (Activity 5-11): Procurement and implementation plan | Demonstrate that the LGUs have the necessary capacity and budget to undertake the project’s procurement and set out timelines. Stakeholder (private and public) engagement is clear, the procurement process is structured and accepted. | - Solution option analysis, - Service delivery options analysis, market analysis, - Procurement Plan - Implementation Plan - Value assessment, Risk assessment, Economic and Socio-economic impact analysis |
| 4. Deliverable 4 (Activity 12): Draft Feasibility Study Report | Acceptance of intermediary deliverables and/or annexes. Risks (legal, technical, financial and economic) and solution option analysis, service delivery, market analysis, due diligences, value assessment. The SC approve the draft report based on provided comparative tools and propose improvements. | - Draft Feasibility Final Report - PowerPoint Presentation for dissemination of recommendations - Minutes of Meeting of Presentation of Report to the PSC. |
| - Deliverable 5 (Activity 13): Final feasibility study | Acceptance of the final report by all stakeholders and all annexes are distributed among partners. | - Final Feasibility Report with all annexures and detailed studies - Handover of Database Management System to PSC. - Close Out Report |

- Practical information

The service provider must ensure regular and effective coordination with EF team in Manila, under the overall supervision of the Output leader and the Project Lead.

The service provider shall be responsible for its own space while in the country, and all necessary facilities and logistical support for its staff, including transportation, office equipment (computers, printers, telephone, and internet services), survey and investigation equipment, communications, utilities, office supplies, and other miscellaneous costs for carrying out the services as per the requirements under the TOR.

Field missions to the Philippines, including international and domestic travel arrangements, will be included under these TOR. Therefore, the service providers should include travel-related costs (flights, accommodation, per diem) in their financial proposal, as well as Expertise France security recommendations and requirements.

Further, the Consultant will need to provide all the administrative and support staff needed to carry out their services.

The contractor may elect to bid for each of the projects on an individual basis, or any combination thereof, fully taking into account the availability of its own resources and capabilities to execute the deliverables within the anticipated 12 months schedule.

- X Confidentiality

The Contractor shall protect all Confidential Information against unauthorised access, disclosure, alteration, or loss and shall ensure that access is limited strictly to authorised users. Any data breach or suspected compromise of security shall be notified to the Authority promptly and, in any event, within 12 hours, together with details of remedial actions taken.

Expertise France shall have the right, upon reasonable notice, to audit or require independent verification of the Contractor’s compliance with this Clause, including the effectiveness of the Database and Document Control System and security controls. Failure to establish or maintain the Document Control System in accordance with this Agreement shall constitute a material breach and may be subject to service failure deductions, step-in rights, or other remedies available to the Authority

VfM and PSC should follow Philippines PPP Code methodology that will be provided to selected bidders