Annex II.III – Expert-days Allocation Table

| Deliverable No | Timeline | Outputs for payment | Please indicate how many days the relevant expert will use for this task. |
| --- | --- | --- | --- |
| 1st Cycle |  |  |  |
| D1 | July 2026 | - Inception report and implementation plan covering roughly all activities but more specifically the October 2026 Forum (digital format submitted by e-mail) | Senior Expert: Expert(s): |
| D2 | September 2026 | - Forum’s final programme, list and details of materials and contents needed for each session of the forum including the panel and the panellists. (digital format submitted by e-mail) | Senior Expert: Expert(s): |
| D3 | November 2026 | - Forum report including the visual outputs of the forum and the planning document for the upcoming checkpoints at schools. | Senior Expert: Expert(s): |
| D4 | November 2026 | - School projects follow-up plan (more specific and concrete than D3 and broken down to tasks) | Senior Expert: Expert(s): |
| D5 | March 2027 | - Meeting and field visit reports based on the planning document D4. (digital format submitted by e-mail) | Senior Expert: Expert(s): |
| D6 | April 2027 | - End of project development phase report | Senior Expert: Expert(s): |
| D7 | April 2027 | - Vocational solidarity event’s final programme, list and details of materials and contents needed for each session (digital format submitted by e-mail) | Senior Expert: Expert(s): |
| D8 | May 2027 | - Activity report including a visual summary of the process from the forum to the completion of the solidarity activity | Senior Expert: Expert(s): |
| 2nd Cycle |  |  |  |
| D1 | July 2027 | - Implementation plan of the 2nd forum based on 1st cycle outputs | Senior Expert: Expert(s): |
| D2 | September 2027 | - Forum’s final programme, list and details of materials and contents needed for each session of the forum including the panel and the panellists. (digital format submitted by e-mail) | Senior Expert: Expert(s): |
| D3 | November 2027 | - Forum report including the visual outputs of the forum and the planning document for the upcoming checkpoints at schools. | Senior Expert: Expert(s): |
| D4 | November 2027 | - School projects follow-up plan (more specific and concrete than D3 and broken down to tasks) | Senior Expert: Expert(s): |
| D5 | March 2028 | - Meeting and field visit reports based on the planning document D4. (digital format submitted by e-mail) | Senior Expert: Expert(s): |
| D6 | April 2028 | - End of project development phase report | Senior Expert: Expert(s): |
| D7 | April 2028 | - Vocational solidarity event’s final programme, list and details of materials and contents needed for each session (digital format submitted by e-mail) | Senior Expert: Expert(s): |
| D8 | May 2028 | - Activity report including a visual summary of the process from the forum to the completion of the solidarity activity | Senior Expert: Expert(s): |
|  | TOTAL |  | Senior Expert: Expert(s): |

The indicative total number of experts*days for completion of all deliverables is approximately 220 days. The number of days of service should not exceed this number of days.