TERMS OF REFERENCE

TECHNICAL AND LOGISTICAL SUPPORT TO TRAINING PROCESSES, AS WELL AS COMPREHENSIVE SUPPORT TO THE BENEFICIARY POPULATION OF THE LAMARR PROJECT .

Table des matières

I.	Introduction	2

II.	Background and justification	3

III.	Objectives	3

1.	General objective	3

IV.	Scope of the mission	4

1.	Overall scope of the consultancy	4

2.	Initial consultancy activities (first quarter)	4

V.	Methodology	6

VI.	Duration of the consultancy	7

VII.	Profile of the consultant	7

VIII.	Offer	7

1.	Technical offer:	8

2.	Economic offer:	8

# Introduction

Expertise France designs and implements projects that sustainably strengthen policies in developing and emerging countries. Through the implementation of its project, 'LAMARR'', a digital skills and services project for young people in vulnerable situations in El Salvador, Expertise France seeks to contribute to the integral and sustainable development of El Salvador.

The project is developed in El Salvador for a period of 5 years and is financed by the European Union.

The project beneficiaries are young people aged 16-29 with one or more of the following characteristics:

- Young people in socio-economic vulnerability.

- Young people in conflict with the law.

- Young people with disabilities.

- Young people returned from irregular migration.

The project is important in addressing the various challenges faced by young people in El Salvador, with regard to limited training and vocational integration opportunities in the digital transformation sector.

First, the project aims to provide training opportunities for vulnerable young people. To achieve this, it is important to ensure that the training provision meets the needs of the professional world. This implies strengthening the partnership between training institutions and the actors of the professional world, which contributes to the economic sustainability of training efforts at national level. Creating and harnessing economic opportunities for young people are the catalysts of change for this population and the domestic productive sectors.

To achieve a strong partnership and trust between the actors, training institutions should improve the quality of their training and broaden the content of their training offer in accordance with the needs of the private sector by strengthening their links with the world of work. The training approach must include the development and certification of individual skills, positive work experiences and an effective interface between training and the occupational sector.

In addition, the project beneficiaries require support to strengthen their soft skills and prepare them for employability, develop a life plan that includes a training route to facilitate their integration into the working environment, and participate in mentoring processes and internships when necessary.

# Background and justification

The LAMARR project has consolidated strategic alliances with various public and private institutions in the country, companies from multiple economic sectors (construction, textiles-clothing, commerce, etc.), as well as civil society organizations, Who are involved in the implementation of the project. These partnerships have been key in the implementation of activities focused on technical training for young people, with emphasis on vulnerable populations.

The project has made significant progress since the initial stage of diagnosis on training and employment in the digital sector, as well as having extended its scope and coverage at national level through work with training centres, technical institutes and universities with a nationwide presence. To date, more than 2,500 young people in vulnerable situations have been trained in various areas of digital and applied digital skills training, including office automation, cybersecurity, programming languages, computer networks, digital marketing, English and French languages for teleoperators, port logistics and supply chain, home automation, AI, data analysis, applied digital for the construction and textile-clothing industries, among others.

In order to overcome one of the main challenges of the project, which is to achieve the effective adaptation of young people to work and production, the project has strengthened its employability component, The implementation of a dual training model combining technical training with practical experience in a company, as well as the execution of internship processes and training aimed at developing cross-sector skills and employment skills.

The project is currently in the process of strengthening its follow-up and care mechanisms for young people covered by the project, with a view to providing closer and more effective support; To strengthen and facilitate their transition to continuing training and/or employment.

In this context, Expertise France within the framework of the LAMARR project launches a call for proposals addressed to organizations specialized in the implementation and management of interventions financed by international cooperation, particularly those aimed at strengthening skills, Employability and attention to vulnerable populations in El Salvador, to provide technical and logistical assistance for the project activities with a main focus on personalized follow-up to young beneficiaries and training centers.

# Objectives

## General objective

Carry out a 18-month mission, regarding technical and logistical support for the implementation of activities aimed at training, monitoring, care and job insertion of young people served within the framework of the LAMARR project.

# Scope of the mission

## Overall scope of the consultancy

This consultancy covers technical and logistical support for the actions linked to training, employability, care and follow-up of young people who beneficiated of the LAMARR project. To do this, the organization must carry out the required actions in direct coordination with the project team and the actors involved in the various components.

The organization should act as a transversal support, contributing to the systematization of information for up to 5,000 beneficiaries. Moreover the organization will be in charge of the execution and monitoring of activities and processes as the articulation with each component responsible, ensuring the quality of the interventions, compliance with Expertise France guidelines and the project’s goals.

Within this general scope, the organisation will be responsible for implementing actions aimed at:

- Supervision and technical-operational follow-up of the vocational training centres (CFPs) providing services for the project.

- Support the implementation of monitoring and systematization of activities related to the employability of young people in the project.

- Implementation of training processes in project-defined transversal skills.

- The integral management of monitoring, verification, validation and recording information tools necessary for the correct implementation and technical and financial follow-up of activities.

- The coordination and management of logistics, operations and administration necessary for the implementation of activities related to the project components.

- Implement the PATH system (Human Talent Care Program) of the LAMARR Project, from the process of assessment and selection of young people to the implementation of services defined in the methodology, according to the needs of the project and within the national scope. Including notably soft skills strengthening activities, employability, mentoring, and dual training, among others.

Specific activities, timelines and expected outputs will be defined through purchase order that will be developed in coordination with the project team.

## Initial consultancy activities (first quarter)

The activities described below are an estimate of actions planned for the first quarter of implementation of the consultancy and serve as a basis for the formulation of the technical and economic proposal. Applicants will have to present a budget and a price for this product (1st quarter Deliverable).

In this sense, the organizations offering the services must submit their technical and economic proposal based on the following activities planned for the first quarter, detailing the proposed operational methodology for the implementation of the activities:

- Operational coordination with training centres: permanent coordination with the training centres for the implementation of cohorts, from institutional induction and socialization of the implementation model and project operational guidelines, verification of schedules, The establishment of groups and support for special requests from young people (differentiated travel expenses, risk situations, entry and exit tests).

- Monitoring of performance and quality control of training processes: Monitoring of the performance indicators of the training centres, verification of compliance with deadlines and deliverables, supervision of attendance. The participants remain and participate actively in the training process.

- Cohort closure and certification: management of participation diplomas, organization of regular closures and support for complementary certification processes linked to training.

- Systematization and reporting of training results: Preparation of monthly technical and financial reports, systematization of the results by cohort, training and/or training centre, and documentation of special cases to ensure completion of training processes.

- Management of monitoring and follow-up instruments: administration, implementation and storage of tools and instruments for the collection of data and records of participants, updating of monitoring matrices, attendance lists and control of travel expenses, and the organization and updating of evidence in the corresponding digital files. This activity is transversal to all the training processes and activities carried out by the project.

- Provision of travel expenses to participants: provision of travel expenses to participants in training processes or other project activities, subject to approval by the project team, including the establishment of corresponding travel expenses control lists. In most cases, this activity consists of the management of funds designated by the project for participants' travel expenses, so these resources should not be part of the economic offer.

- Administrative and financial management of the training processes: validation, control and settlement of regular travel expenses, closure and other activities carried out by the project.

- Monitoring the employability of young people in the project: monitoring the progress of beneficiaries in internship processes or work practices derived from training processes of the Project, contact with beneficiaries to update and verify information related to their employment status and progress in the processes of employability, administration and regular updating of the tools designated for monitoring the employability of young people.

- Coordinate and manage the logistics necessary for the implementation of activities related to project components: call for participants, listing and other related requests by the project.

- Implement cross-functional skills training processes: facilitation of cross-functional skills training processes, after coordination with the project team, implementation of registration, assistance and evaluation tools. Monitoring participation and systematization and reporting on training results.

- Implement the youth assessment and selection process: operational coordination of the process with training centres and project teams, implementation of the assessment and selection system (registration in form, calls, review of documents, interviews, psychometric tests and techniques), record, safeguard and protection of the information of the selection process and elaboration of narrative and statistical reports of the processes developed.

- Implementation of the services of the Human Talent Care Program (PATH): execution of the services defined in the methodology (employment simulators, soft skills and employment skills strengthening activities, follow-up to mentoring processes, etc.) In coordination with the project team, management of information relating to these activities, monitoring of young people, systematization and reporting of results of services implemented and youth participation.

For the first quarter, it is estimated that:

- ten (10) technical training groups will be attended to ;

- two (2) cross-functional skills training processes will be carried out ;

- approximately five hundred (500) young people will be evaluated and selected;

- the provider will have to ensure follow-up on the employability of young people placed in employment to date (), as well as those currently in training who will be placed in employment upon completion of their training (up to 100 beneficiaries in the first quarter).

In addition, the services of the Human Talent Support Programme (PATH) are to be progressively implemented, which includes the development of face-to-face activities, the monitoring of young people and support for their integration into the labour market, whose scope includes the care of young people beneficiaries of the project to date (more than 2,500 young people) as well as the young people to benefit during the following months of implementation of the project. Also, in the framework of the implementation of PATH, the organization will be responsible for the follow-up to the mentoring program of the project, which will include the training of mentors and the follow-up to the mentoring processes, the mentor persons and the young mentees. For the first quarter, approximately fifty (50) mentors and one hundred (100) mentees are expected to participate.

The LAMARR project provides technical training for at least two thousand (2,000) new young people during the contract period of the consulting organization, who will be assisted through the processes and activities described.

The geographical coverage of activities and processes to be developed by the organization will have a national scope, in coordination with training centres and territorial actors defined by the LAMARR Project. The number of participants, groups and territories may be adjusted according to operational demand, pace of implementation and project priorities.

Details of implementation, methodology and deliverables for the activities described will be defined in the implementation arrangements to be developed in coordination with the project team.

# Methodology

The consultancy will be implemented through a collaborative approach, aimed at ensuring the proper implementation of the training, employability, care and follow-up actions of the LAMARR Project. The provider will work in permanent coordination with the project team, following their technical, administrative and financial guidelines.

The consultancy will be based on flexible operational planning, defined through activity execution agreements, which will allow actions to be adjusted according to project needs and territorial dynamics. The organization will be responsible for implementing procedures and tools that ensure proper execution, supervision and follow-up of activities related to the various components, including the Human Talent Programme.

It will also manage in an integral way the logistical processes required for the development of activities and ensure the registration, validation and systematization of the information necessary for technical and financial monitoring. The methodology is national in scope, according to the operational requirements of the project. The technical and administrative team of the provider organisation will have to be multidisciplinary with a proven ability to manage training activities and employability of young people in vulnerable situations.

In addition, the organization offering the project must present, as part of its technical proposal, the specific methodology it proposes for the implementation of the operational components of the project (evaluation and selection process of young people, follow-up to employability, mentories). This methodology should describe the approaches, tools, roles, operational flows and implementation assumptions, and will form the basis for the formulation of the economic proposal, The structure of the programme should be based on the activities planned for the first quarter of implementation.

# Duration of the consultancy

The consultancy will start from the signature of the contract, with a maximum duration of eightenn (18) months. The detailed timetable for this period will be specified in the implementation arrangements, to be defined in coordination with the project team.

# Profile of the consultant

- The proposed task force should have at least two years' proven experience in implementing development projects and with cooperation organizations, government entities and training centres, as well as experience in coordinating actions with multiple actors and operating at a national level.

- The proposed work team should be made up of professionals with experience in supervising vocational training processes, youth employability, psycho-emotional support for young people. In addition, he or she must have competence in the systematization of information and administrative and financial management of projects.

- The relationship of the consulting entity with economic sectors or companies in the productive sector will be evaluated, especially those linked to employment opportunities for the young population participating in the project.

- The consulting entity shall present an institutional profile including general information of the entity, institutional presentation, organizational structure, proposed work team (with life sheets and roles), similar work references of the team when applied..

# Offer

## Technical offer:

The technical offer shall focus on the execution of the activities confirmed for the first quarter, as set out in paragraph 4.2 of these Terms of Reference, and shall contain at least the following paragraphs:

- Institutional profile, including general information about the entity, institutional presentation, work team experience (including their life-histories and roles).

- Working methodology proposal for the first quarter, which presents the methodology and operational approach by which it will execute the activities confirmed for the first quarter, detailing the organization of workflows, team responsibilities, implementation times and coordination mechanisms with the project team. It should include the methodology of monitoring, quality control, information management and accompanying young people and training centres, demonstrating ability to operate simultaneously in the different components of the LAMARR Project.

- Organization of the work team for the first quarter, including a description of the team assigned to carry out the activities of the quarter, functions, level of commitment and relationship with the activities to be carried out.

- Proposed mechanism for reporting and monitoring implementation, the organization should describe how it will report technical and financial progress to the LAMARR Project, ensuring the quality of information, the support of verification means and consistency between activities implemented and resources used.

- Identification of operational risks and mitigation measures, including analysis of the main operational risks associated with the first quarter execution and proposed strategies for their mitigation.

## Economic offer:

The economic offer must be presented for the activities confirmed in the first quarter, consistent with the technical offer, in a disaggregated, clear and detailed manner, allowing the costs associated with the execution of the activities to be identified. The organization offering may structure the cost calculation by activity and/or by beneficiary served, according to the methodology proposed.

The economic proposal shall include at least:

- Offer in accordance with the activities described in paragraph 4.2 of these Terms of Reference.

- The offer for the unit price schedule which is detailed below :

| Component | Item | Description | Unit of Measure |
| --- | --- | --- | --- |
| Employability / Care for vulnerable populations | Monthly follow-up to young person / per young person | Technical transfer of the didactic sequences in transversal skills and employability, using virtual reality tools, aimed at staff of Training Centers. The training must last at least 16 hours and may be divided into four 4-hour sessions, for example. | Trained person |
| Care for vulnerable populations | Transversal skill training / Per trained person | Develop in-person training in transversal skills with or without the use of virtual reality lenses aimed at young people in vulnerable situations, including the collection of attendance records and the payment of per diems to young people. The training must last a minimum of 16 hours and may be divided into four 4-hour sessions for groups of 25 people each, for example, as defined by the project. | Trained person |
|  | Attending the start and end events of each training cohort to carry out activities such as verifying participation lists and the delivery of per diems to young people or other items / 2 events per cohort | Monitor and evaluate partners' reporting on the development of special or complementary cohorts (e.g., the Mentor Network). This activity consists of attending the start and end events of each training cohort to carry out activities such as verifying participation lists and the delivery of per diems to young people or other items. The events are in-person with an estimated duration of 4 hours each. | For two events (start and close) per cohort |
| Training | Follow-up and monitoring of vocational training centers and/or educational institutions where technical trainings are carried out. / per training group | Monthly monitoring and follow-up to each training center for each group consisting of 25 to 30 participants. The training varies in duration from 1 to 12 months. The scope of monitoring may include, among other activities, the following: Review the quality of information from weekly CFP reports, according to standards established since the LAMARR project, manage the actual execution schedule, review and follow up on each participant’s individual documentation (registration form, letter of commitment, informed consent, satisfaction survey, pre-test and post-test table, among others), management of funds for the delivery of travel documents for graduation, monitoring of attendance rates for each training group, among others of a similar nature), as well as the weekly report of the group (attendance list and travel schedule) Notes: - It is clarified that the responsibility for managing and delivering each group’s documentation lies with the training center or educational organization. - Communication is carried out virtually 90% of the time, during the training a maximum of two visits are made, mobilization costs are excluded from this process. | Training group |
| Technical support | Young person evaluated in phase 1-2 and deserted from the process / per young person And Young person evaluated from stage 3 to 5 and/or selected / per young person Two different units | Implement the process of evaluation and selection of beneficiaries, in coordination with the project team and training centers, consisting of five phases: 1) verification of the young person’s vulnerability profile, 2) request for CV and video, 3) call for data validation, 4) individual interview and 5) application of psychometric tests), as well as the preparation of individual and group results reports, with their respective endorsements. The process and its phases may be modified according to the needs and profile of the corresponding course. | Young person evaluated in phase 1-2 and deserted from the process |
|  |  |  | Young person evaluated from stage 3 to 5 and/or selected |
|  | Monthly follow-up to young person / per young person | Monthly monitoring of an average of 700 young people involved in the project, using structured instruments provided by the project (to be sent via messaging or applied by short call to young people) aimed at: - Follow-up and/or updating of participants’ education or employment status in order to identify support needs and facilitate subsequent referrals. - Follow-up of youth employed through the project to monitor their employment status and job retention. - Follow-up with youth participating in internships or work placements, including coordination with training centers to verify the implementation of the practical component. Including the collection and recording of information, progress updates, supporting evidence, and the preparation of monitoring reports. | Young person |
|  | Young person assisted in PATH activities / per young person | Implement activities to strengthen young people's soft skills and prepare them for employment, targeting groups of 25 young people each (e.g., job simulators, skills enhancers, or other activities covered by the Project-PATH Human Talent Care Program), including logistical and operational coordination and reporting of required information. Required technical profile: development facilitator or employment technician, with knowledge and experience in employability and youth services. | Young person assisted in PATH activities |
|  | Young beneficiary integrated into employment / Per young person | Implement the process of integrating young people into employment in sectors related to the technical training provided by the project. The intervention may include identifying and liaising with companies, managing vacancies and surveying the profiles required by companies, referring candidates, and supporting the selection processes and monitoring young people who have been integrated into employment for 6 months. | Young beneficiary integrated into employment |
|  | Support for the implementation of project events / Per event | Provide support for the implementation of project events related to training or employment for young people (e.g., job fairs, employability workshops, among others). Support may include managing participant recruitment, monitoring participation, collecting and verifying attendance and records, delivery of per diems to young people and other tasks. | Event |