# Terms of reference

- General information

| # Assignment name | # INTERNATIONAL CLIMATE ADVISORY SERVICES # AS PART OF THE IMPLEMENTATION BY EXPERTISE FRANCE OF THE NATIONAL COMPONENT OF THE EUROPEAN UNION-FUNDED FORESTRY-CLIMATE CHANGE-BIODIVERSITY PROGRAMME FOR PAPUA NEW GUINEA |
| --- | --- |
| # Beneficiary | CCDA – Papua New Guinea’s Climate Change and Development Authority (CCDA) Associated organisations: - CEPA – the Conservation and Environment Protection Authority - DAL – the Department of Agriculture & Livestock - DLPP – the Department of Lands & Physical Planning - DNPM – the Department of National Planning & Monitoring - NEA – the National Energy Authority - PNGFA – the Papua New Guinea Forest Authority |
| # Country | Papua New Guinea |
| # Total estimated number of days | # 400 days of expertise from the contract award date to 6 July 2029: - 100 days of a senior expert - 300 days of a junior expert |

- Context and justification of the need

Expertise France

Expertise France, a subsidiary of the French Development Agency (Agence Française de Développement, AFD) Group, is the French government’s international technical cooperation agency. Its role is to design and manage donor-funded international cooperation projects that aim to sustainably strengthen public policies in developing and emerging countries in fields such as governance, security, health, education and the environment. The European Union (EU), the French Ministries and AFD constitute Expertise France’s main donors.

In 2024, Expertise France was active in 147 countries around the world, with 384 projects under implementation, and a revenue of 447 million euros.  The agency has a workforce of 870 personnel in its headquarters in Paris and about 1,450 personnel internationally.

More information about Expertise France is available on the website: https://www.expertisefrance.fr/.

The implementation by Expertise France of the national component of the European Union-funded Forestry-Climate Change-Biodiversity (EU-FCCB) Programme for Papua New Guinea

The European Union-funded Forestry-Climate Change-Biodiversity (EU-FCCB) Programme for Papua New Guinea is an international cooperation programme funded by the European Union whose general objective (GO) is “to support a development model that reconciles forestry, climate change and biodiversity with sustainable, inclusive and gender-responsive green growth and jobs at national and pilot subnational/community levels”. Its three specific objectives (SOs) are:

- SO1: “Effective implementation of evidence-based FCCB policies, governance and institutional frameworks”

- SO2: “Improved FCCB awareness, knowledge, capacities and mobilisation”

- SO3: “Increased inclusive and gender-responsive green growth”

This Programme consists of several components, including a significant component implemented by Expertise France regarding “support at the national/institutional level with spill-over effects at the local/community level” (the national component).

This project includes interventions across all three specific objectives of the EU-FCCB Programme, including support for a number of PNG-based public sector institutions operating in the FCCB intervention area, support for PNG-based research, education and awareness institutions and support for PNG-based communities, civil society organisations and private sector organisations engaged in conservation, sustainable livelihoods, and sustainable value chain development.

More information about the EU-FCCB Programme and the national component implemented by Expertise France are available at the website: https://fccbpng.eu/.

Needs in terms of INTERNATIONAL CLIMATE ADVISORY SERVICES

The national component of the EU-FCCB Programme implemented by Expertise France includes a series of interrelated interventions in the climate space.

These interventions include various technical assistance measures to PNG’s Climate Change and Development Authority (CCDA), as well as other interventions in the climate space, which can be described as follows:

| The EU-FCCB National Component’s Activities in the Climate Space implemented in partnership with the Climate Change & Development Authority (CCDA) |  |
| --- | --- |
| Technical Assistance to CCDA | - Activities under SO 1 (Effective implementation of evidence-based forestry, climate change, and biodiversity (FCCB) policies, governance, and institutional frameworks) - 1.1 Activities relating to the digital transformation of FCCB agencies and data enhancement - Digitalisation - Support for the development of a new website for CCDA - Provision of IT equipment (Videoconferencing solution + information hub) - Digital workspace enhancement - Support for PNG’s National Carbon Registry (NCR) system - Support for PNG’s REDD+ Safeguards Information System (SIS) - Green Fee revenue collection information system - Data Enhancement - Support for the development and submission of PNG’s first Biennial Transparency Report (BTR) 1 - 1.2 Activities relating to the improvement of coordination between and within FCCB sectors - Support CCDA on organising carbon markets / REDD+ sector awareness / coordination events - Support for technical working committees (TWC) coordinated by CCDA - 1.3 Activities relating to the organisational development of FCCB agencies - Support for the organisational restructure of CCDA - Support for the business planning (change management) process at CCDA - Support for communications & knowledge management strategy & implementation - Provision of communications equipment - 1.4 Activities relating to the implementation of public policies and associated instruments and measures - Support for the consolidation of PNG’s REDD+ safeguards framework - Support for the development of PNG’s third Nationally Determined Contribution (NDC3) - 1.5 Activities relating to the application of public policies and associated instruments and measures at the subnational level - Support for the development of provincial adaptation plans - Activities under SO 2 (“FCCB awareness, knowledge, capacities, and mobilisation improved”) - 2.1 Activities relating to the improvement of knowledge and awareness on FCCB issues among PNG’s population - Support to CCDA for the 2025 national climate summit - 2.2 Activities relating to the enhancement of PNG’s participation in FCCB national, regional and international communications and knowledge exchange networks and platforms - Support for CCDA participation at international events (COP28, COP30) - Activities under SO 3 (“Inclusive and gender-responsive public and private sector investment, sustainable growth, deforestation-free livelihoods and decent jobs in the FCCB space increased”) - 3.2 Activities relating to improved access to finance and increased investments in the FCCB sector - Support for the development of the National Climate Finance Strategy (NCFS) - Support for the registration of PNG’s jurisdictional REDD+ programme under the ART-TREES standard |
| Other interventions in the climate space | - Forest Cover Mapping: - Potential support for updating forest cover maps in 5–6 provinces, contributing to ART-TREES readiness and strengthening baseline data on deforestation and forest degradation. Subject to further coordination with PNGFA, FAO. - Institutional Strengthening – PNGEA: - Continued support to the organisational strengthening of the Papua New Guinea Environment Alliance (PNGEA). Note that the organization is facing donor-related constraints but that PNGEA has a growing interest to engage with government on carbon markets and REDD+ including JREDD+. - Youth and Gender Capacity-Building: - Capacity-building initiatives targeting youth and gender mainstreaming in the FCCB sector. - Support for knowledge-sharing on gender and Free, Prior and Informed Consent (FPIC) processes. - Promotion of youth advocacy and engagement in FCCB policy and action. - Higher Education and Skills Development: - Support for development of tertiary-level courses on emerging FCCB themes, including: - Nature-Based Solutions (NBS) - Carbon Markets and Cooperative Mechanisms under Article 6 - Integrated Green Growth Strategies - Scholarships and Research Grants: - A €3 million master’s scholarship and research grants scheme - Third-Party Grant Facility: - A €6 million grant scheme to support conservation and sustainable livelihood initiatives implemented by third parties, with government entities eligible to participate as, for example, associates (covering travel and per diems, but not salaries). |

These different interventions are at various stages of implementation.

To ensure a strategic and coordinated approach of these interventions, Expertise France is seeking to hire an international consulting firm able to provide international climate advisory services to CCDA, as described in the next section.

- Description of the assignment

To ensure a strategic and coordinated approach to the climate-related interventions of the project, Expertise France is seeking to hire an international consulting firm able to provide international climate advisory services to CCDA. The selected consulting firm would play a key role in providing strategic advice to CCDA and in coordinating the project’s climate-related interventions.

Main tasks:

- Strategic Advice to CCDA and to the Government of PNG in the climate space

In coordination with Expertise France and with other development partners:

- To establish and maintain a strategic dialogue with CCDA and the Government of PNG in regard to the country’s goals, challenges and strategies on a number of emerging topics of interest in the climate space,

- To follow-up with CCDA on all action items arising from these strategic dialogue meetings,

- To prepare briefing / background notes / presentations on issues and options on topics of interest for CCDA or upon request,

- Coordination of the project’s climate-related interventions

- To assist in the preparation, updating and review of the project’s list of interventions in the climate space

- To ensure that this list of interventions is coordinated effectively with the interventions of other development partners

- To identity potential candidates and to prepare terms of reference for individual or national experts who would need to be hired in the climate space

- To guide the selected individual or national experts at key junctures of their assignments

- To review the deliverables (ex: technical inputs; progress reports; mission reports) prepared by these individual or national experts

- To contribute to the effective organisation of the information and documentation arising from the different assignments

- To prepare and host climate-focused project technical coordination meetings with all these individual or national experts, with a few to fostering linkages and synergies between workstreams

- To follow-up with all individual or national experts on the action items arising from these coordination meetings

- To assist with the supervision of two national embedded officers deployed within CCDA to support the roll-out of the project’s climate-related interventions

To this end, the international consulting firm would need to deploy a team of one senior and one junior international expert*, who would be expected to spend significant amounts of time in Port Moresby, Papua New Guinea, to achieve and maintain close collaboration with CCDA and associated government organisations at all levels (technical, management and leadership).

The senior expert would be expected to conduct regular but short missions to Port Moresby (ex: monthly 5-day missions or bimonthly 10-day missions).

The junior expert would be expected to be able to be deployed for longer periods of time (ex: missions of 2-months each) to collaborate closely with CCDA on the day-to-day implementation of activities, for example in the carbon markets & REDD+ space.

Additionally, the international consulting firm will be expected:

- to ensure that design and planning of the work to be carried-out under each scope item is informed by the following:

  - baseline information / assessment,

  - detailed scope description,

  - theory of change (TOC) with assumptions and risks,

  - RACI matrix and/or coordination framework,

  - exit strategy

  - etc.

- under the guidance of Expertise France, to coordinate effectively with other international and national experts hired by Expertise France under other workstreams

- to provide high-quality capacity-building and awareness to all relevant public and non-profit organisations at all levels (technical, management and leadership levels)

Finally, the international consulting firm will be expected to develop and maintain a strong overall strategic focus to help guide decision-making around prioritisation and the use of available resources, including the expertise and time of the international consulting firm, especially in the event of the materialisation of risks or opportunities that call for budget arbitrations between work streams.

A Purchase Order-based framework contract

The contract would be a purchase order-based framework contract based on unit prices for days of expertise (senior / junior) to be provided by the international consulting firm.

Expertise France would issue purchase orders (POs) for days of expertise by the international consulting firm according to the progressive emergence of its needs. Once a need has emerged:

- Expertise France would communicate this need to the international consulting firm and ask the international consulting firm to prepare and submit a proposed work plan to calibrate the exact tasks and the number of days of expertise in response to this need;

- Expertise France would review this workplan and ask the international consulting firm to provide clarifications or make adjustments to the workplan.

- Once Expertise France is satisfied with the workplan, Expertise France would raise a PO and award it to the international consulting firm.

For example, Expertise France could consider proceeding as follows:

- First PO: Following the award of the framework contract to the successful tenderer, Expertise France would contact the selected international consulting firm to request a specific workplan to cover the first month of implementation with a focus on a full scoping assessment including a stocktake of the results to date and the plan for the implementation of the remainder of interventions

- The second PO could cover the period of implementation from the end of the first PO until the end of June 2027.

- The third and last PO could cover the period of implementation from 1 July 2027 to 30 June 2028.

To be noted: the maximum contract value of the framework contract should in no case be seen as a “firm” commitment by Expertise France to raise POs up to the maximum value of this contract. Only the raising of POs is binding on Expertise France.

Arrangements regarding missions to PNG

In order to carry-out the work planned under the different POs, the selected international consulting firm will be expected to conduct missions to PNG.

To conduct missions to PNG, the international consulting firm will be required to prepare missions plans for Expertise France’s review and approval. These mission plans should be prepared at least one month in advance prior to the start of the proposed mission. Once the mission plan is approved, the international experts of the international consulting firm will be required to obtain a Mission Security Clearance (MSC) from the relevant authorities within Expertise France and complete all requirements as per Expertise France procedures.

Expertise France will be making the travel and accommodation arrangements for the international experts in PNG.

A Per Diem of 66.50 EUR per night of stay of the experts will be provided to the Contractor on the basis of an invoice and supporting documentation including a mission expense form.

These mission expenses are not considered part of the contract value.

Deliverables

Expertise France would require the Consulting Firm to submit a Final Deliverable with all supporting documents for each PO.

Coordination

The consultant shall designate a single contact person for project implementation purposes.

The Technical Coordinator of the National Component of the European Union-funded Forestry-Climate Change-Biodiversity (EU-FCCB) Programme will be consultant’s main focal point at Expertise France.

As mentioned, close collaboration must take place with the Expertise France project team and all other relevant international and national consultants right up to completion. In particular, close collaboration is expected with the national experts hired by Expertise France to provide day-to-day support to the organisations in question.

- Place, duration and terms of performance

  - Implementation period: from the contract award date to 31 March 2029

  - Start date: contract award date

  - End date: 31 March 2029

  - Effective duration per assignment: would be determined in the POs.

  - Acceptance, deliverables and timesheets

Acceptance of the deliverables will be carried out by the Project Manager – National Component of the EU-FCCB Programme.

Acceptance of the deliverables will take the form of an acceptance certificate signed by Mr. Vandenberghe, a copy of which will be provided to the Contractor.

Furthermore, timesheets will be prepared by the Contractor using the template specified in the contract and will require approval by Expertise France. Approval of the timesheets will take the form of a countersignature on the timesheet document.

Expertise France does not allow for work to be done on weekends or public holidays; therefore, any timesheets in which the Contractor indicates that work has been done on the weekend or public holidays will be rejected.

- Required expertise and profile

  - Required experience:

- Experienced international consulting firm in the field of climate advisory services, with at least:

  - 5 relevant references

  - 1 relevant reference in Papua New Guinea

  - Number of experts per assignment: at least 2

  - Profile of the designated expert(s) responsible for contract execution

The applicant should provide CVs of all key personnel proposed for this tender.

- Familiarity with the project theme (sustainable development, forestry, climate change, biodiversity…)

- Working experience on matters of climate change in the public sector in developing countries. (At least 10 years of relevant work experience required for the senior expert).

- Working Experience in Papua New Guinea or Pacific

- Familiarity with the implementation of EU-funded projects or alternatively with projects by other development partners.

- Experience working in a consultant role

  - Method Statement

The applicant should provide a method statement.

In particular, the method statement should set out in detail how the consulting firm will be organised to perform the assignment and achieve the desired results. In particular, this method statement should highlight aspects such as:

- overall strategy to ensure the success of the assignment

- planned arrangements to be able to quickly mobilise & deploy the designated experts upon request, and the associated timeframe

- planned arrangements to be able to replace designated experts with experts of comparable qualifications and experience should the need arise, and the associated timeframe

- processes and approach to ensure strong collaboration with the partners;

- processes and procedures to ensure quality control;

- processes and procedures to ensure a timely delivery of deliverables;

- processes and procedures for effective training & capacity building

- exit strategy considerations

- Assignment report

A report following the template provided must be forwarded by e-mail on conclusion of the POs.

Note that though the intention is for most activities to stop by 30 June 2028, the contract enddate would be 31 March 2029 to allow for the possibility that more time would be needed.