# Terms of reference 
and technical Specifications

- General information

| # Assignment name | # CAPACITY-BUILDING INTERVENTION FOR ENTREPRENEURIAL SUPPORT ORGANISATIONS (ESOS) |
| --- | --- |
| # Beneficiary | # ESOs (such as incubators and accelerators) and other providers of business development support for entrepreneurs |
| # Country | Eligible countries in ESA : Angola, Bostwana, Burundi, Ethiopia, Kenya, Malawi, Mozambique, Namibia, Rwanda, South Africa, Tanzania, Uganda, Zambia (with a focus on Angola, Namibia, Burundi and Mozambique) |
| # Available amount for the tender | Best offer |
| # Project duration | # 1 year |

- Context and justification of the need

The SWITCH to Circular Economy in East and Southern Africa (SWITCH-2-CE in ESA) program is a regional initiative co-financed by the European Union and the German Federal Ministry for Economic Cooperation and Development (BMZ), and jointly implemented by the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) and Expertise France (EF) until July 2029.

The program aims to foster an inclusive transition to a circular economy (CE) across East and Southern Africa by supporting policy reform, skills development, and private sector investment. It focuses in particular on two priority value chains and material streams with high environmental, economic, and social relevance: plastics and packaging, and electronics.

The overall objective of SWITCH-2-CE in ESA is pursued through three specific objectives:

- Establish an enabling and inclusive policy framework for circular economy at national and regional levels;

- Enhance the participation of formal and informal workers and SMEs, including women and youth, in circular economy models;

- Improve access to and use of financing and technical assistance by circular economy businesses, with a particular focus on women-owned and women-led enterprises.

Within this context, and in addition to the efforts of enhancing access to financial and technical assistance programs for circular economy enterprises, the program also acknowledges the need for capacity building interventions targeting Entrepreneurial Support Organisations (ESOs) and Business Development Support (BDS) providers. The ultimate goal is to build the capacity of ESOs and BDS providers (including incubators and accelerators) to support local businesses in the field of circular economy, and to integrate circular economy dimensions into existing incubation, acceleration and business development support programs.

More specifically, through this assignment Expertise France is focusing on the following capacity building aspects for ESOs operating in the region:

- Deepening the understanding of circular economy concepts and business models, recognising that circular economy goes well beyond waste management and recycling, and encompasses a broad range of approaches including repair, refurbishment, reuse systems, resource efficiency, and product-as-a-service models;

- Strengthening the capacity of ESOs to identify, assess and support circular economy businesses, including businesses that apply circular principles without explicitly positioning themselves as circular economy enterprises;

- Integrating circular economy dimensions into existing incubation, acceleration and business development support programmes;

- Fostering peer learning and knowledge exchange among ESOs in the region on circular economy topics and best practices in business support.

- Objectives and desired results

  - General objective

The general objective of this assignment is to strengthen the capacity of ESOs and BDS providers in East and Southern Africa to effectively support SMEs and start-ups in circular economy businesses, and to integrate circular economy dimensions into their incubation, acceleration and business development programs.

  - Specific objectives

The following specific objectives are identified:

- Improve the capacity of ESOs to provide tailored business support to circular economy start-ups and MSMEs at different stages of maturity, including in the areas of financial readiness, investment preparation, and business model development;

- Strengthen the circular economy knowledge and expertise of ESOs, enabling them to understand, identify and assess circular economy business models and opportunities across different sectors and value chains;

- Support ESOs in integrating circular economy considerations into their existing support programs and service offerings, ensuring that circular economy principles become a structural component of the assistance they provide to entrepreneurs;

- Build a regional community of practice among ESOs, fostering peer-to-peer knowledge exchange and long-term collaboration on circular economy topics and business support methodologies.

  - Anticipated results

The following anticipated results are identified :

- At least 10 ESOs across the target countries have successfully completed the capacity building program;

- Participating ESOs demonstrate improved knowledge and understanding of circular economy concepts, business models and value chain dynamics;

- Participating ESOs have integrated, or have a concrete plan to integrate, circular economy dimensions into their support programs and service offerings;

- A functional peer learning mechanism is established among participating ESOs, with evidence of active knowledge exchange during and beyond the program.

- Description of the assignment

The service provider is expected to design and implement a comprehensive, blended capacity building program for ESOs in East and Southern Africa, combining in-person and online components in a manner that maximizes learning effectiveness, geographic reach and sustainability of results.

The service provider shall have full responsibility for the design of the program methodology, training content and delivery modalities. Applicants are expected to propose and justify their approach in detail in their technical offer, demonstrating how it responds to the specific objectives and expected results of this assignment. The proposed methodology should reflect the service provider's experience in training professionals and trainers active in the field of business support, incubation and acceleration, and should clearly articulate how circular economy knowledge will be integrated into practical, applicable tools and frameworks for ESOs.

The program shall be structured around four phases described in the following paragraph.

  - Planned activities

Phase I: Assignment inception and preparation (indicative duration: 1 month)

Prior to the launch of the program, the service provider shall undertake the following preparatory activities:

- Identify a list of potential beneficiaries in the target countries;

- Conduct a rapid needs assessment of the selected ESOs to identify their current level of knowledge, existing service offerings, and priority capacity building needs, in order to tailor the program design accordingly;

- Develop a detailed implementation plan, including the training calendar, delivery modalities (which should include both in-person and online delivery) , resource requirements and coordination arrangements with Expertise France;

- Present the inception report and implementation plan to Expertise France for review and approval before proceeding to Phase II.

Phase II: Programme design and training content development (indicative duration: 2 months)

- Design the full capacity building curriculum, including training modules, learning materials, tools and resources, based on the findings of the needs assessment and in line with the specific objectives of this assignment. The curriculum shall cover at minimum the following thematic areas:

  - Circular economy fundamentals: concepts, principles, business models and value chain dynamics, with a focus on plastics/packaging and electronics sectors;

  - Identifying and assessing circular economy businesses and opportunities, including businesses that apply circular principles without explicitly positioning themselves as circular economy enterprises;

  - Tools and methodologies for supporting circular economy start-ups and MSMEs, including business model development, financial readiness, and investment preparation;

  - Integrating circular economy dimensions into incubation, acceleration and business development program;

  - Best practices in business support, mentoring and coaching for MSMEs and start-ups.

- Develop the online learning component of the program, including any digital resources, e-learning materials or collaborative platforms to be used during and after the program;

- Facilitate the establishment of a peer learning community among participating ESOs, including a knowledge sharing platform or equivalent mechanism to support ongoing exchange beyond the program;

- Present the full curriculum and training materials to Expertise France for review and approval before delivery begins.

Phase III: Program and training delivery (indicative duration: 6 months)

- Deliver the capacity building program to the selected ESOs across the target countries, in accordance with the approved curriculum and implementation plan;

- The program shall combine in-person and online delivery modalities. The service provider is expected to propose and justify the specific mix of modalities in their technical offer, demonstrating how the blended approach maximizes learning effectiveness and geographic reach;

- Organize a minimum of 2 in-person workshops bringing together participating ESOs from across the target countries, designed to facilitate hands-on learning, peer exchange and networking;

- Facilitate regular online learning and exchange sessions throughout the program duration;

- Provide individualized follow-up and coaching support to participating ESOs between sessions, to assist them in applying learning to their specific organizational context.

Phase IV: Integration support and community of practice (indicative duration: 2 months)

- Provide targeted support to participating ESOs in integrating circular economy dimensions into their existing support program and service offerings, including through individual advisory sessions and practical tools;

- Support ESOs in the official integration of CE dimension in their services portfolio

- Document best practices, lessons learned and insights emerging from the program, for dissemination within the SWITCH-2-CE network and beyond.

Phase V: Monitoring, evaluation and closure (indicative duration: 1 months)

- Conduct a final evaluation of the program, assessing knowledge gains and integration of circular economy dimensions among participating ESOs;

- Complete the logical framework provided by Expertise France with relevant data, evidence and sources of verification;

- Produce a final report summarizing program implementation, results achieved, lessons learned and recommendations for future interventions.

  - Anticipated deliverables

The service provider shall produce at least the following deliverables in accordance with the implementation schedule. All deliverables must be submitted to Expertise France for review and approval prior to the processing of the corresponding payment installment.

| Deliverables | Description | End date |
| --- | --- | --- |
| - Inception report | Findings of the rapid needs assessment, detailed implementation plan, training calendar and coordination arrangements | End of month 1 |
| - Capacity building curriculum and training materials | Full curriculum including training modules, learning materials, tools and resources, covering all thematic areas specified in “Phase II” | End of month 3 |
| - Online learning component and peer learning platform | - Digital resources, e-learning materials and/or collaborative platform to be used during and after the program, with evidence of functionality - Functional knowledge sharing platform or equivalent mechanism, with documentation of its use and evidence of active participation by ESOs | End of month 3 |
| - Workshop 1 report | Summary of proceedings, attendance records, training materials used, and participant feedback from the first in-person workshop | As defined in implementation plan |
| - Workshop 2 report | Summary of proceedings, attendance records, training materials used, and participant feedback from the second in-person workshop | As defined in implementation plan |
| - Final report with completed logical framework | - Comprehensive report covering program implementation, results achieved against expected outcomes, lessons learned. The final report shall also include: an assessment of knowledge gains and changes in the adoption of CE dimensions among participating ESOs. - Logical framework provided by Expertise France, completed with relevant data, evidence and sources of verification | End of month 12 |

The service provider has the flexibility to add components to this list of key activities and deliverables if considered appropriate for an effective delivery of the assignment

  - Coordination

The service provider shall designate a single contact person for project implementation purposes.

Samy Remtolla and Sheena Millapo will be the service provider’s contact people for Expertise France

A launch meeting shall be held 10 days after the contract award has been notified.

Close collaboration must take place with from assignment preparation right up to completion. Furthermore, regular exchanges must take place every 2 weeks on assignment progress and any difficulties that may be encountered.

- Place, duration and terms of performance

  - Implementation period: 1 Year

  - Start date: September 2026

  - End date: September 2027

  - Effective duration per assignment: 1 Year

  - Schedule/programme:

The provisional programme for assignment implementation is as follows:

| Activity | Place | Period |
| --- | --- | --- |
| Phase I : Assignment inception and preparation | Online | September/October |
| Phase II : Programme design and training content development | Online | October/November |
| Phase III : Program and training delivery | Online and in person | December-May 2027 |
| Phase IV : Integration support and community of practice | Online | May-July 2027 |
| Phase V : Monitoring, evaluation and closure |  | August/September 2027 |
| Total |  | 12 months |

- Required expertise and profile

  - Number of experts per assignment: The service provider shall mobilize a team of at least 2 experts for the implementation of this assignment. The service provider is free to propose additional experts if deemed necessary to ensure the quality and effectiveness of the program delivery, provided this is clearly justified in the technical offer.

  - Profile of the designated expert(s) responsible for contract execution

Expert 1 — Lead Expert: Circular Economy and Business Support Specialist

Qualifications and skills:

- Advanced university degree (Master's level or equivalent) in a relevant field such as sustainable development, environmental management, business administration, economics or equivalent;

- Excellent communication, facilitation and knowledge transfer skills;

- Strong analytical and reporting skills;

- Full professional proficiency in English. Knowledge of Portuguese is an asset, particularly for interventions in Angola and Mozambique.

General professional experience:

- At least 7 years of professional experience in the field of circular economy, sustainable business models or related areas;

- Demonstrated experience in designing and delivering training programs or capacity building initiatives for professionals, with a strong preference for candidates with experience in "training the trainers" methodologies;

- Experience working in Sub-Saharan Africa, preferably in East and Southern Africa.

Specific professional experience:

- Proven experience in circular economy business model analysis, including the ability to identify and assess circular economy opportunities across different sectors and value chains;

- Experience in supporting or advising ESOs, incubators, accelerators or business development service providers in integrating sustainability or circular economy dimensions into their programs;

- Familiarity with the challenges and opportunities facing circular economy start-ups and MSMEs in the East and Southern Africa context.

Expert 2 — Business Support and Incubation/Acceleration Specialist

Qualifications and skills:

- Advanced university degree (Master's level or equivalent) in business administration, entrepreneurship, management or equivalent;

- Excellent facilitation, mentoring and coaching skills;

- Strong experience in curriculum design and adult learning methodologies;

- Full professional proficiency in English. Knowledge of Portuguese is an asset, particularly for interventions in Angola and Mozambique.

General professional experience:

- At least 7 years of professional experience in the design and implementation of incubation, acceleration or structured business support programs for start-ups and MSMEs;

- Demonstrated experience in training professionals working in business support, incubation or acceleration, with a strong preference for candidates with experience in "training the trainers" methodologies;

- Experience working in Sub-Saharan Africa, preferably in East and Southern Africa.

Specific professional experience:

- Proven track record in designing and delivering capacity building programs for ESOs or equivalent business support organisations;

- Experience in applying gender-responsive and inclusive approaches in business support or training programs;

- Knowledge of circular economy concepts and business models is an asset.

- Assignment reports

The service provider shall submit all reports and deliverables listed in the paragraph “Anticipated deliverables” of Section IV,  by email to the Expertise France contact persons designated in paragraph “Coordination” of Section IV. Reports must be written in English and submitted in editable format (Word) accompanied by a PDF version.

Expertise France reserves the right to request revisions to any report or deliverable that does not meet the required standards or does not adequately reflect the work carried out.

- Monitoring-evaluation

Performance indicators

| Deliverables | Immediate effects | Verification sources |
| --- | --- | --- |
| 1. Inception report | - List of beneficiaries are selected and rapid assessment of knowledge and capacity building needs is implemented; - Program implementation plan is defined and tailored the needs of beneficiaries | - List of beficiaries - Needs assessment - Inception and implementation plan |
| 2. Capacity building curriculum and training materials | - Full capacity building curriculum, training modules and learning materials are developed | Full curriculum with tools and methodologies (including clear learning objectives) |
| 3. Online learning component and peer learning platform | - E-learning modules for on-line training delivery are completed - Peer learning platform is established to support ESOs knowledge sharing and collaboration beyond project end | - Functional online platform for e-learning delivery. The e-learning platform shall ensure accessibility and fruition of the training material beyond project completion - Verification of the platform functionality and accessibility |
| 4. Workshop 1 report | - Workshop 1 concept note, agenda and implementation/delivery plan, learning objectives; - ESOs participating in first in-person workshop | - Workshop implementation report - ESOs attendance confirmation list - ESOs post-attendance evaluation questionnaire and knowledge gain assessment |
| 5. Workshop 2 report | - Workshop 2 concept note, agenda and implementation/delivery plan, learning objectives; - ESOs participating in first in-person workshop | - Workshop implementation report - ESOs attendance confirmation list - ESOs post-attendance evaluation questionnaire and knowledge gain assessment |
| 6. Final report with completed logical framework | - Program implementation achievements, lessons learned, knowledge gains and future recommendations are developed - Documentation of changes in the ESOs’ inclusion of CE dimensions in their service offer portfolio to businesses. | - Final report with summary of implemented activities and interventions results, proof of output achievements, knowledge gains, lessons learned and recommendations |

- Practical information & Budget Presentation Guidelines

The candidates are expected to provide a clear budget according to the number of hours spent for each phase, number of lessons delivered online, number of days per workshop, how many workshops, etc...

Applicants are expected to present a clear and comprehensive overview of their proposed approach, activities, and implementation modality for the entire initiative. The budget should reflect the full scope of planned interventions.

For the following logistical costs in their budget:

- International and domestic flights for ESO representatives

- Accommodation costs

- Per diem allowances

- Venue reservations and catering for workshops or events

These costs, upon validation with Expertise France, can be included in the reimbursable costs.

What applicants are required to provide is a clear indication of where and how such costs will arise. Specifically, the budget narrative should include:

- Workshop locations: where each workshop or in-person event is planned to take place

- Expected number of participants: an estimate of attendees for each event

- Travel requirements: planned international flights or domestic trips for participants, including origin and destination where known

- Accommodation needs: estimated number of nights and location, where relevant

This information will allow Expertise France to plan and budget for logistical arrangements accordingly.