Terms of Reference (ToR)

Title of the assignment: National assessment of the space and satellite capabilities of Central Asian countries to meet the needs of the project to promote the satellite connectivity access and use of satellite technologies. Country Analysis to be conducted in Kazakhstan, Uzbekistan, Kyrgyzstan, Tajikistan, and Turkmenistan.

Project: Team Europe Initiative (TEI) on Digital Connectivity in Central Asia, Soft Pillar.

Component: 3 – Digital Innovation.

Location: The assignment is expected to be carried out remotely, with compulsory missions to Kazakhstan, Uzbekistan, Kyrgyzstan, Tajikistan and Turkmenistan.

Implementation Approach: The assignment shall be implemented under a single fixed-price service contract. The selected service provider shall demonstrate the technical expertise, organisational capacity and resources necessary to deliver the full scope of the assignment across all target countries within the required timeframe.

Proposed team composition: The service provider shall propose a multidisciplinary team with the technical expertise, organisational capacity and resources necessary to successfully deliver the full scope of the assignment across all target countries.

The proposed team shall include a Space and Satellite Assessment Coordinator, who will coordinate the technical implementation of the assignment, facilitate collaboration across the expert team, ensure a consistent methodological approach and consolidate the assessment outputs into a regional comparative analysis and strategic recommendations.

The service provider shall remain responsible for the quality and timely delivery of all contractual deliverables.

Depending on the proposed methodology and team structure, the proposed team may include the following key expert profiles:

- Space Policy and Regulatory Expert

- Research, education and innovation space expert

- Technical and Space Infrastructure expert

- Stakeholder Engagement & Workshop Facilitation Expert

Duration: The assignment is expected to be implemented over a period of three (3) months from the contract start date.

Expected Start Date: 01 October  2026

Language Requirements: Proficiency in English is essential. Any Central Asian local languages and/or Russian would be an advantage.

- Background:

The Team Europe Initiative (TEI) on Digital Connectivity in Central Asia project is funded by European Union and aims to bridge the digital connectivity divide in Central Asia, through the development of an enabling, safe and inclusive environment for satellite connectivity use, with the overall objective of increasing equal access to basic public services and socio-economic inclusion. The project activities will be implemented and cover Kazakhstan, Uzbekistan, Kyrgyzstan, Tajikistan and Turkmenistan.

The project is being implemented by the TEI Consortium led by the Expertise France (France), Central Project Management Agency (CPVA, Lithuania), Central Financing and Contracting Agency (CFLA, Latvia), E-Governance Academia (EGA, Estonia) and Finnish Institute for Public Management (HAUS, Finland).

The Action consists of four components:

- To foster the development and use of ICT connectivity through the development of policies and regulations.

- To improve transparent and inclusive access to public and private connectivity services.

- To promote the use of satellite-based technologies to foster local digital innovation and tackle local challenges;

- To build cybersecurity capacity and awareness among stakeholders, and establish comprehensive cybersecurity frameworks.

Expertise France’s activities under Digital Innovation component are aimed to support the development of a dynamic innovation ecosystem in Central Asian countries, by promoting exchange, cooperation, access to capacities and funding to digital innovators. This objective will focus on satellite-based digital solutions, including but not limited geospatial data applications complemented by IoT sensors, which provide relevant solutions to tackle local challenges (climate adaptation, urban planning, natural resources management, economic inclusion, etc.).

Component outputs are focusing on:

- Creation regional innovation network.

- Digital innovation developed and incubated.

- Users’ tools and capacities to use satellite-based innovations are increased.

- Visibility of Central Asian digital innovation actors in Europe has increased.

- Assignment description:

Nowadays space technology and derived services are crucial enablers for national development including economic growth, sovereignty, security abilities, climate resilience, communications, disaster management, scientific advancement, etc.

Therefore, in order to provide a structured and evidence-based understanding of the region’s space and satellite ecosystem both strategic and developmental, Expertise France seeks to recruit a service provider to conduct national assessments in Kazakhstan, Uzbekistan, Kyrgyzstan, Tajikistan and Turkmenistan, as well as a regional comparative analysis. The assessment shall take into account the varying levels of maturity of the space sector across the region, ranging from countries with established infrastructure and operational capabilities to those where regulatory frameworks, institutional arrangements and technical capacities for space activities remain underdeveloped or are still emerging.

The national assessment for each country aims to:

- Map stakeholders and their services. As national assessment is on the space capabilities, the stakeholder mapping implies to recognize all types of stakeholders existing in each country.

- Establish baseline of space and satellite capabilities.

- Evaluate infrastructure and technical capacity.

- Identify technical, institutional, regulatory and commercial strengths, gaps, risks, and opportunities. It is important to cover all segments, including Earth Observation, telecoms, others.

- Assess strategic autonomy and risks.

- Examine international partnerships and compliance with international space law.

- Assess human resource. National assessment has to evaluate country’s ability to regulate, develop, operate, analyze and utilize satellite technologies with identifying relevant human resources: regulatory – space policy and legal experts; space agencies – technical and engineering experts, scientific – astrophysics, space researches, remote sensing specialists, etc. As well as relevant university programs, trainings centers, etc.

- Provide strategic recommendations for national and regional development. Based on the data received during the assessment give recommendations and guidance to strengthen country’s satellite/space sector. Synergies is one of them.

The assessment for each country shall include, but not be limited to, the following components:

Legal and policy framework:

- National space strategy and policies.

- Regulatory regime (licensing, spectrum, orbital slots).

- Compliance with international space laws.

- Innovation & Research support frameworks

Institutional bodies and their services (stakeholders’ activities to regulate, design and operate space communication systems, manufactures, etc.):

- Space agencies or coordinating bodies.

- Relevant ministries.

- Research institutes and universities.

Infrastructure and assets:

- Satellites (communications, EO, navigation, etc.).

- Ground stations and control facilities.

- Launch facilities (if applicable).

- Data processing and storage capacity.

Industrial and commercial ecosystem:

- Local aerospace companies.

- Tech start-ups and innovation clusters.

- Public-private partnerships.

- Access to venture capital and funding.

- Participation in global value chains.

Human capital and R&D:

- University programs in aerospace/space sciences

- Technical workforce capacity.

- Brain drain / retention issues.

- National research funding.

International cooperation:

- Bilateral/multilateral partnerships.

- Cooperation with major space powers.

- Participation in regional initiatives.

- Membership in international organizations.

Security and strategic considerations:

- Cybersecurity of space infrastructure.

- Dependence on foreign systems.

- Strategic autonomy considerations.

Socioeconomic Impact:

- Use of space services in key sectors: eg. agriculture, disaster management, energy, transport, etc.

- Digital inclusion impact.

- Economic contribution of space sector.

Methodology:

The assessment for each country shall use a mixed-methods approach (not exhaustive):

- Key informant interviews (government, private sector, CSOs, international partners).

- Desk research and document review.

- Stakeholder mapping.

- Survey instruments.

- Data collection and statistical analysis.

- SWOT analysis.

Each country assessment should follow a standardized analytical framework to ensure regional comparability.

Overall Assessment  Coordination

The Space and Satellite Assessment Coordinator shall ensure standardized analytical framework, regional comparability and synergies across all national assessments. He/She will:

- Establish coordination for the multidisciplinary expert team across all target countries;

- Coordinate and consolidate the inputs of all experts involved in the assignment;

- Provide guidance on standardized and harmonized approach for national assessments to ensure regional comparability and synergies;

- Organize coordination meetings with the experts and Expertise France;

- Ensure standardized and high quality approach for the proposed methodologies and prepare report on coordinated approach.

- Ensure quality assurance of the methodology and all deliverables;

- Coordinate the preparation and consolidation of national assessment reports;

- Ensure that all national assessments incorporate a regional perspective and identify opportunities for regional cooperation;

- Consolidate country findings into a comparative regional analysis and strategic recommendations for future project activities.

- Expected deliverables :

    - Inception Report:

- Detailed methodology

- Stakeholder engagement plan

- Timeline

- Templates for the national assessment report and the regional comparative analysis

    - Draft Assessment Reports (five national reports and one regional comparative analysis report) :

- Structured according to agreed framework

- Executive summary

- Data annexes

- Stakeholder feedback integration

    - Final Assessment Reports (five national assessment reports and one regional comparative analysis report)

- Incorporating comments

- Strategic roadmap with clear recommendations guidance on how to improve space capabilities in short and medium terms both: 1) for Central Asian stakeholders and 2) for further activities of the component to reach project’s goals, including recommendations regarding the relevance of the activities outlined in the current workplan. Strategic roadmap should have a regional perspective to each national report with a final SWOT comparative analysis.

- Proposed payment terms:

| Contract signature and mobilisation | Contract start | Up to 30% pre-financing (if applicable) |
| --- | --- | --- |
| Final National Assessment Reports (five national reports and one consolidated regional assessment report) | Within 90 days from the contract start | Final payment upon approval of all final deliverables |

Payments shall be made in accordance with the terms of the Service Contract and shall be subject to the satisfactory completion and approval of the corresponding deliverables by Expertise France.

- Proposed experts and qualifications:

- The Space and Satellite Assessment Coordinator

Overall responsibility for technical leadership, methodology oversight, quality assurance, coordination across countries, and liaison with Expertise France and implementing partners.

- Advanced university degree (Master’s or equivalent) in fields relevant to specific expertise area, such as aerospace engineering, space system and telecommunication engineering, international space law, public policy and public administration. In the absence of such a degree, candidates should have at least 10 years of professional experience in the relevant domains such as telecom and space infrastructure, space policy and governance, innovation and ecosystem, EO applications.

- Minimum 7 years of professional experience in the space sector, computing, cybersecurity or aerospace sector.

- Proven experience leading multi-country or complex country-level policy assessments and strategic views, developing space policy, strategy or regulatory frameworks, developing road maps.

- Proven experience working with governmental institutions, regulatory authorities and national space companies.

- Strong knowledge in satellite systems, space infrastructure, resilience of space systems and space industry value chain development.

- Working in international technical assistance projects, especially with EU-funded projects.

- Excellent time management, planning, analytical, stakeholder engagement and communication skills.

- Ability to work independently and deliver high-quality outputs under tight timelines.

- Strong analytical and report writing skills.

- Proficiency in written and spoken English is essential. Knowledge of the Central Asian or Russian languages will be an asset.

- Regional experience in Central Asia is an asset.

- Space Policy and Regulatory Expert

Covers country-specific analysis of legal, regulatory, and institutional frameworks affecting the space sector.

- Advanced university degree in law, public policy, political science, or a related field.

- Minimum eight (8) years of professional experience in regulatory analysis, policy reform, or public sector advisory work.

- Demonstrated experience conducting national-level policy or regulatory assessments in at least three (3) of the target countries or comparable contexts.

- Strong knowledge of regulatory areas relevant to the space sector.

- Ability to translate regulatory analysis into practical, implementable recommendations.

- Experience working with government counterparts and regulators is required.

- National or regional expertise in the target countries is highly desirable.

- Proficiency in written and spoken English is essential. Knowledge of the Central Asian or Russian languages will be an asset.

- Research, education and innovation space expert

Covers country-specific analysis of Human capital, industrial, research and innovation national ecosystems

- University degree in aerospace, ICT innovation management or related fields

- Minimum 7 years of experience working in aerospace

- Strong knowledge on innovation triple helix concepts, EU standards and frameworks on space innovation support for R&D

- Demonstrated experience in assessing innovation space ecosystems, education and training frameworks and research and development support scheme in comparable contexts

- Ability to translate needs and gaps for practical recommendations

- National or regional expertise in the target countries is highly desirable.

- Proficiency in written and spoken English is essential. Knowledge of the Central Asian or Russian languages will be an asset.

- Technical and Space Infrastructure expert

- Covers infrastructure, technical capacity, industrial ecosystem, and security considerations.

- University degree in aerospace engineering, satellite communications, or a related field.

- Minimum 7 years of experience working in the aerospace sector.

- Demonstrated experience with communications satellites, Earth Observation (EO), or navigation systems (e.g., GPS, Galileo).\Proven ability to translate qualitative engineering insights into policy-relevant findings.

- Having participated in at least two (2) similar projects.

- Proficiency in written and spoken English is essential. Knowledge of the Central Asian or Russian languages will be an asset.

- Stakeholder Engagement & Workshop Facilitation Expert

- Design, organise, and facilitate multi-stakeholder consultations and in-country workshops (scoping, consultations, validation).

- University degree in social sciences, public policy, communications, or a related field.

- Minimum 7 years of experience in stakeholder engagement, facilitation, or participatory policy processes.

- Proven experience facilitating multi-stakeholder workshops involving government, private sector, universities, and development partners.

- Strong facilitation, communication, and consensus-building skills.

- Experience conducting workshops in Central Asian contexts is required.

- Ability to manage parallel workshops across multiple countries is an asset.

- Proficiency in written and spoken English is essential. Knowledge of the Central Asian or Russian languages will be an asset.

NOTE: The proposed team may include additional experts beyond the minimum requirements specified in these Terms of Reference. The service provider shall ensure that the team composition is appropriate to cover all required areas of expertise and to deliver the assignment in a timely and high-quality manner.

- Management and Reporting

The service provider shall report directly to the Digital Innovation Component Coordinator and/or Team Lead (Expertise France), based in Astana. All deliverables shall be submitted to, reviewed and approved by the Digital Innovation Component Coordinator and/or Team Lead.

- Contractual Arrangements

Contract Type: Service Contract.

Contract Duration: Three (4) months from the contract start date.

Performance Period: Three (3) months within the Contract Duration.

Payment: Payments shall be made in accordance with the Service Contract and shall be linked to the satisfactory completion and approval of the agreed deliverables. Subject to the contract terms, an advance payment of up to 30% may be made upon contract signature, followed by an interim payment upon approval of the draft deliverables and a final payment upon approval of all final deliverables.

Price Composition: The proposed contract price shall include all costs necessary for the successful implementation of the assignment, including experts' fees, coordination, travel, accommodation, daily subsistence, local transportation, workshops, translation and interpretation (where required), communications, administrative costs and any other expenses related to the delivery of the services.

- Proposal Submission Requirements

Interested service providers shall submit both Technical Proposal and Financial Proposal.

Technical Proposal shall include, at a minimum:

- Proposed methodology and workplan;

- Proposed team composition and CVs of the proposed experts;

- Implementation schedule;

- Relevant experience in similar assignments.

Financial Proposal shall be submitted as a single all-inclusive lump-sum price covering the full scope of the assignment. For evaluation purposes, the financial proposal shall also include a breakdown of the major cost components, including, where applicable:

- Expert fees (daily rate × estimated number of working days for each proposed expert);

- Travel and mission costs;

- Workshops and stakeholder consultation costs;

- Translation and interpretation costs;

- Administrative, coordination costs;

Any other costs necessary for the successful implementation of the assignment.