| FACILITY FROM THE REGIONAL TEACHER INITIATIVE FOR AFRICA |  |
| --- | --- |
| TERMS OF REFERENCE CALL FOR TENDERS TECHNICAL ASSISTANCE – THE GAMBIA Development of a STEAM Policy and a STEAM Teachers’ competency framework |  |
| CAP technical area | TEACHERS’ EDUCATION AND PROFESSIONAL DEVELOPMENT |
| CAP main actions | ACTION 3.1: Development of a STEAM policy ACTION 3.2: Development of a STEAM/ digital teacher competency framework |
| Impacted indicators and objectives of the ESSP 2016-2030 | Result area 2: Quality and relevance: #2: STEM governance framework established and functional #2: STEM education and training programmes developed and implemented (indirectly) |
| Implementation period | September 2026 – August 2027 |
| Total estimated number of days | 95 days |

| Expected key deliverables | ACTION 3.1 - Report highlighting best practices (benchmark) and recommendations for the development of the STEAM policy - Technical note and PP presentation on the proposed methodology and format - STEAM policy - STEAM policy Operationalization plan (OP) - Based on the OP: capacity building modules, communication strategy, monitoring system and tools, annual review tools - Technical memo on the process (for learning purpose) - Advocacy strategy/ note(s) for donors and private sector ACTION 3.2 - Report on existing teacher STEAM/digital competency frameworks in Africa and globally (benchmark) - Technical note and PP presentation on the proposed methodology - STEAM competency framework - Pilot/ consultations concept note - Presentation and report on pilot/ consultations results - Operationalization plan (OP) - Sensitization/ capacity building modules (including ToT module) - ToT report - Technical memo documenting the process |
| --- | --- |
| National implementing partner (Unit in charge of interaction with the experts) | - Science and Technology Education Directorate (STED) – MoBSE (lead) - HR directorate - In-Service Training Unit (INSET) |

# BACKGROUND

THE REGIONAL TEACHER INITIATIVE FOR AFRICA

The Regional Teacher Initiative for Africa (RTIA), a programme funded by the EU/EC via the Education section (G3) of DG INTPA aims to improve learning outcomes and the socio-emotional development of children in Africa, by having a more competent, motivated and inclusive teacher workforce in basic education.

The RTIA will especially seek to achieve the following outcomes over the next 6 years:

- Improve the governance, management, attractiveness, and gender balance of the teaching profession, with a strong focus on increased digitalisation and innovation.

- Enhance the quality, relevance, and effectiveness of initial and continuous teacher professional development, notably through digital education, peer-to-peer learning approaches, and regional collaboration.

Within RTIA, the Facility will support teacher policy and improve teacher education and professional development systems by i) providing capacity building at country level through technical assistance, ii) promoting innovation and scaling of effective teaching solutions; iii) increasing the production and use of data and evidence, and iv) promoting the use of regional frameworks, evidence-based practices, and joint learning at regional level.

The Facility from RTIA will reach the above-mentioned objectives through 3 types of instruments or “windows”: i) a window to deliver technical assistance on teacher governance and teacher education and professional development based on the demand from eligible partner countries, ii) a window on testing and scaling effective programs for teacher education and professional development in the thematic areas of digital skills, gender, green skills, and pedagogical skills, including in the context of refugees and displaced population, iii) a research window to create new evidence and support the integration of evidence in the policy making process and in the design of teacher education and professional development programs.

In addition to these windows the Facility’s knowledge management and communication activities will further contribute to the sharing of knowledge, evidence, and best practices related to the overall Initiative outcomes.

The Facility is funded by the European Union and co-implemented by the Partnership formed by four member-state agencies: Expertise France for France, Enabel for Belgium, EDUFI for Finland and ESTDEV for Estonia. Expertise France has been designated the Coordinating Agency for this Partnership. With the Facility governance scheme serving as the Initiative's governance scheme, it is expected that the Partnership will work closely with UNESCO and UAC, in charge of the other 2 components of the EU Initiative.

The duration of the action is scheduled from 01.02.2024 to 31.01.2030 with a budget of

92.000.000 EUR.

The call for expertise falls within the scope of Window 1 consisting in the provision of technical assistance (TA) aimed at supporting countries in specific thematic areas related to teacher policy and governance, as well as teacher training and professional development.

## WINDOW 1: DEMAND-DRIVEN TECHNICAL ASSISTANCE

The Technical Assistance Window is a mechanism activated at the request of eligible countries in sub-Saharan Africa to mobilize expertise in the design and implementation of public policies and capacity building in two areas: the governance of the teaching profession and the training and professional development of teachers.

The Technical Assistance Window involves mobilizing experts to help countries design and implement national reforms and policies relating to teachers, build capacity and strengthen systems to improve the effectiveness of teaching, by improving social dialogue with teacher representatives and seeking ways to enhance the status of the teaching profession.

Within the framework of this Facility, the term ‘technical assistance’ refers to the mobilization of institutional or individual technical expertise, whether European or African.

In order to ensure the sustainability of the initiative beyond its implementation period, the Facility seeks to encourage the establishment of partnerships between European and African public institutions.

##### COUNTRY ACTION PLAN (CAP)

The technical assistance is provided within the framework of a Country Action Plan (CAP), jointly developed by the technical teams of the requesting Ministry of Education and the Facility. A CAP is a set of coherent technical assistance actions covering a period of between 12 and 24 months, leading to targeted changes in synergy with the country's education sector plan (ESP) and teacher-related policies, if these exist or are being developed.

A CAP is the result of a process that includes:

- An expression of interest and needs from the requesting sub-Saharan African country – submitted by the national authorities (with the Ministry of Education as the focal point channeling the country's needs) with the support of EU delegations and EU Member State agencies in the country, if necessary.

- An analysis of the expression of interests and needs based on teacher policy (where available), teacher sections of the education sector plan and the GPE compact (if available), as starting points for assessing the relevance, feasibility and sustainability of the needs and identifying appropriate technical assistance and capacity building measures.

- A series of consultations and local interactions with the Local Education Group (LEG), the EU delegation, and EU agencies in the country (if they have not been consulted previously), with the aim of prioritizing the most strategic actions of the CAP, ensuring consistency with ongoing national and international programs on teachers, and sustainability by taking into account available or future investment lines in the field of education in the country. The CAP aims to support and complement existing initiatives. High priority will be explicitly given to technical assistance actions that prepare for or are directly linked to teacher policy reform and/or substantial investments in the sector, from national or international resources (e.g. national budget for teacher salaries, national budget for initial and continuing teacher training, multilateral and bilateral investment programs, among others).

##### CAP ACTIVITIES

Each CAP includes a list of specific activities to be carried out by technical experts. The activities are defined in a set of specifications covering one or more activities included in the CAP list. Technical assistance is provided in the short and medium term and aims to achieve precisely defined results.

##### PARTNERS AND FOCAL POINTS

The main partners in the technical assistance window are the ministries of education of eligible partner countries in sub-Saharan Africa. They are the main focal points in the development of CAPs, which means that they identify needs and, in collaboration with the Facility team, design the CAP actions.

CAPs may include technical assistance actions that benefit other institutional actors such as teacher training institutes, universities (when they are responsible for teacher training in particular), inspections, decentralized services, as well as other ministries involved in responding to the needs identified in the CAP (Ministry of Finance, Ministry of Planning, Ministry of Higher Education, etc.). In addition, ministries of education have the option of involving other actors, such as trade unions and teachers' organizations, as beneficiaries of technical assistance and in activities related to teaching policy reforms and the revitalization of the teaching profession.

Where CAPs from different countries have similarities in their programs or activities, the Facility proposes to facilitate collaboration and exchanges between these countries, depending on their interest and availability.

## GAMBIA REQUEST FOR TECHNICAL ASSISTANCE

The request sent by the Gambia Ministry of Basic and Secondary Education (MoBSE) on April 23, 2025, was covering five main areas, namely:

- Gender-Responsive Teacher Policy Implementation

- EdTech and Digital Pedagogy Integration

- Teacher HR Management Systems (TMIS Strengthening)

- Inclusive Education for Displaced/Marginalized Learners and

- Climate Education Curriculum Design.

The first online technical exchanges between MoBSE and RTIA teams allowed to refine the demand around teachers’ governance (human resources management and teacher policy) and teachers’ education and professional development (digital skills, green skills and inclusive education).

The MoBSE request was approved by the Facility on July 30, 2025.  In September 2025, an in-country mission with 2 experts from the Facility led to the co-development of a Country Action Plan (CAP) for The Gambia.

## BACKGROUND INFORMATION – MAJOR EDUCATION POLICY AND REFORMS STATUS IN THE GAMBIA

As of mid-2025, The Gambia's population is estimated at approximately 2.82 million people, with around 45% falling within the school-age bracket of 4 to 18 years. This youthful demographic reflects the country's steady population growth and underscores an urgent need for expanded school infrastructure and a larger, well-trained teaching workforce.

Investing in education is a key pillar of the Gambia’s National Development Plan 2023–2027. The Gambia Ministry of Basic and Secondary Education (MoBSE) has made significant strides in expanding school enrolment. The introduction of the ‘fee-free policy’ and the provision of school grants have improved education coverage, resulting in near-universal access to basic schooling. This progress is largely attributed to the expansion of school infrastructure, improved facilities, and the deployment of newly trained teachers nationwide associated with an increase in public expenditure on education.

The education system is structured in 3-6-3-3: 3 years of early childhood education (ECE), 6 years of lower basic education (LBE), 3 years of upper basic education (UBE) and 3 years of senior secondary education (SSE). MoBSE oversees over 3,300 public, private, and religious schools. According to the Gambian Education Statistics 2024/2025; 148, 299 children are enrolled in ECE; 442,901 children in LBE, 144,964 in UBE and 94,731 in SSE.

However, challenges remain. Enrolment rates for children with special educational needs continue to lag behind (0.46% for ECD, 1.36% at LBE, 0.33% at UBE and1.5% at SSE as extracted from 2024/2025 education statistics) highlighting persistent gaps in inclusive education. Moreover, improving the quality of education—particularly at the foundational level—has proven difficult. The 2023 Early Grade Reading Assessment (EGRA) revealed a deeply rooted learning crisis in foundational literacy showing alarmingly high rates of zero scores and low reading fluency.

Recognizing the key role of teachers in promoting learning in the classroom, MoBSE has tripled the number of qualified teachers from 4,600 in 2000 to 13,300 in 2023. Measures such as hardship allowances intend to support teachers’ deployment in remote areas. However, the lack of HR policy undermines transparency and accountability regarding teachers’ recruitment, deployment and promotion, with a negative impact on teachers’ morale and retention. MoBSE identified the development and implementation of an HR policy as one of their top priorities.

The Education Sector Strategic Plan (2016–2030) outlines a bold vision to professionalize the Gambia’s teaching workforce. Central to this effort is the development of a Teacher Competency Framework, which defines career pathways and expected competencies at each level, alongside a comprehensive teacher policy. However, these initiatives have yet to be fully operationalized.

While The Gambia has made notable progress in increasing the proportion of trained teachers across all education levels, in-service capacity building through Continuous Professional Development (CPD) programs remains heavily dependent on financial support from development partners. Coordination of CPD initiatives and capture of corresponding data are lacking. MoBSE is planning to pilot a teacher portal developed by Owl Technology at the end of 2025, to improve transparency, and enhance the overall effectiveness of teacher training programs. Teachers are expected to be key users of the platform, to apply online for vacant positions and transfer, and to access information on/ apply for capacity building opportunities. The launch of the platform will contribute to the efforts to increasing transparency and accountability in teachers’ governance and continuous professional development.

## LOGIC OF INTERVENTION

The Gambia CAP is articulated around the two main areas of teachers’ governance and professional development, with proposed activities focusing on the education 1 reform priorities, and complementary to existing initiatives.

ACTION 1: teachers’ governance

- HR and teacher policies

Consultations in country both with MoBSE and international partners highlighted the necessity to undertake a policy situational analysis, mainly because of a lack of visibility on existing policy documents, their status, their level of implementation and their relevance in line with the education reform. The main objective of this activity is to nurture the development of the HR policy, but also to identify potential duplications, build on what is already existing and ensure that the different policy documents are aligned and relevant to the education reform implementation.

The key action, identified by MoBSE as their first priority, is the co-development of an HR policy. The process intends to be participatory, and to include the relevant directions, partners, and teachers’ union representatives. The same involvement will take place for co-developing the operationalization plan, which will include roles and responsibilities, sensitization and communication plans, monitoring tools, and, if needed, capacity building modules for implementers.

The second action, in terms of policy development and implementation, will also benefit from policy situational analysis. It aims to review the existing teacher policy against the education reform and international standards. Given that it has been developed in 2022, few updates are expected. As the teacher policy was never implemented, the TA will facilitate the co-development of a realistic operationalization plan, highlighting, as for the HR policy, roles and responsibilities, sensitization and communication plans, and monitoring tools. Gender-responsiveness will be mainstreamed in the operationalization plan, as per the initial ask in the request. A participatory approach similar to that of the HR policy aims to contribute to ownership by all education stakeholders.

ACTION 2: teachers’ governance

- MoBSE teacher portal implementation

The last activity under teachers’ governance will support the launch of MoBSE teacher portal developed by Owl technology. This activity intends to orientate and guide platform users outside HQ (i.e. teachers, headmasters and principals, cluster monitors etc.) through small tutorials, guidelines and/or training contents per user category focusing on their actual use of the platform. It is quite important for teachers to be able to navigate the platform, as, among other uses, this will be the only way to apply for transfer in the future.

ACTION 3: teachers’ education and professional development:

- STEAM policy and competency framework

The demand for TA in “EdTech and Digital Pedagogy Integration” in the request changed quite drastically after discussions, given that the needs for TA in EdTech and digital pedagogy are covered under other initiatives. Two main actions are related to, but not only, digital skills. The first one is the development of a STEAM policy targeting basic to higher secondary education, intended as a political statement of the importance of developing students’ soft skills alongside technical skills to make them more adaptable to a changing world. The proposed activities include a benchmark of best practices to nurture the policy development, the framing of the policy within existing policies, strategies and curricula, an operationalization plan and an advocacy strategy targeting donors and the private sector to get extra financial and material resources for the policy implementation.

The second action is the development of a teacher's STEAM/ digital competency framework. The TA will use the same approach of identifying best practices through a benchmark, co-developing the framework and its operationalization plan, and developing tools and modules based on the operationalization plan. The STEAM/ digital competency framework will be integrated in the teacher’ competency framework.

ACTION 4: teachers’ education and professional development:

- Continuous Professional Development: enhancing teachers’ competencies

As part of MoBSE willingness to strengthen the management of the teaching force, as well as to enhance teaching quality, teacher continuous professional development was discussed extensively. Two actions related to CPD are included in the CAP. The first one is the operationalization of the teacher's competency framework. The TA includes a review of the existing competency framework and assessment of its alignment with the education reform and international standards. Besides the co-development of the operationalization plan, the TA will also co-develop a pathway for career development for teachers to know the required level of competency needed by position, and the steps to reach this level. Based on this pathway and the operationalization plan, the TA will co-develop capacity building modules, targeting clusters’ monitors, for school/ cluster level support to teachers.

MoBSE developed a mentoring program as part of the teacher's pedagogical support system. There is confusion in MoBSE, but also in schools, between the induction (for teachers newly appointed in a school) and the mentoring programs. As in-service teacher training is almost entirely done at school and cluster levels, the TA will review and update the mentoring program, focusing on newly qualified teachers. This action intends to build a bridge between pre-service and in-service teacher training, as there is a current disconnection between the two. As part of this activity, the TA will update and/or develop capacity building modules for mentors and headmasters. The TA will also explore ways to support newly appointed headmasters, in regards to specific competencies related to their role, such as management, administration etc. This might include the development of specific training modules and/or of an induction program for starting headmasters.

The request component on inclusive education, despite not being a CAP activity as such, is still part of the CAP and will be integrated as a cross-cutting issue in the CPD framework and the mentoring program. This intends to respond to a lack of capacity among teachers who benefit only from one capacity module on inclusion. By ensuring that inclusion is embedded into all relevant competencies in the CPD framework, and that the mentoring program is also addressing significant gaps in pre-service training in terms of inclusive education, the TA aims at enhancing teachers’ awareness and skills to better identify and respond to students’ special needs.

# SCOPE OF WORK – CAP ACTION 3

In this context, Expertise France is recruiting a consulting firm to implement this action.

The service covered by this contract corresponds to Action 3 of the Gambia CAP.

## OVERVIEW

| Technical areas of expertise | Action description / Work package | Activities |
| --- | --- | --- |

| - Teachers’ education and professional development STEAM | - Development of a STEM/STEAM policy | - Preliminary study: desk review, benchmark - Development of the STEM/STEAM policy - Development of the STEM/STEAM policy operationalization plan (OP) - Development of sensitization/capacity building modules (based on OP) - Development of an advocacy strategy (donors/ private sector) |
| --- | --- | --- |
|  | - Development of teacher STEAM/ digital competency framework | - Benchmark of best practices/ initiatives - Development of the STEAM/ digital competency framework - Piloting of the competency framework - Development of the framework operationalization plan (OP) - Development of capacity building modules (based on OP) - Training of trainers (based on OP) - Development of a technical memo (learning purpose) |

## OBJECTIVES OF THE ACTION 3

##### GENERAL OBJECTIVE

##### Enhance and promote quality STEAM education from basic to secondary education

##### SPECIFIC OBJECTIVES

- Develop a STEAM education policy that will ensure the development of a strong science, technology, engineering, art and mathematics education commencing at the basic and secondary level

- Develop a teacher STEAM competency framework that will guide teachers’ education and CPD and enhance quality STEAM teaching

- Design realistic national operationalization plans for the STEAM policy and competency framework, using MoBSE existing resources, systems and platforms

- Develop an advocacy strategy targeting donors and the private sector to get financial and material support for the implementation of STEAM education.

- Develop capacity building modules to enhance STEAM policy and competency framework ownership and implementation at all levels of the education system

## IMPLEMENTING NATIONAL PARTNERS

The Ministry of Basic and Secondary Education (MoBSE) who sent the request, is the main implementing partner and will be involved in all the CAP’s components.

More specifically for the STEAM component (activities 3.1. and 3.2.), the lead implementing partner in MoBSE is the Science and Technology Education Directorate (STED). Another key MoBSE department to involve in the co-development of the competency framework is the In-Service Training Unit (INSET). All the relevant departments and directorates of MoBSE for basic and secondary education need to be involved in consultations, both on the STEAM policy and STEAM competency framework (eg. The Human Resources directorate, the Standards and Quality Assurance Directorate, the Curriculum, Research, Evaluation and Development Directorate, the Early Childhood and Inclusive Education Directorate, etc.). The partners for the action should be consulted and actively engaged at different stages of the action to ensure a participatory and inclusive approach.

Other key actors to be involve are the Teachers’ Unions and the University of Education. It will be also essential to ensure that teachers, head teachers, clusters’ monitors and representatives of madrassas and private schools are consulted and involved in the process.

Finally, it is also essential to involve the Local Education Group (LEG) to share information with education partners and ensure that the CAP activities are not duplicating existing efforts, but rather complementing partners’ activities in the Gambia.

## APPROACH AND METHODOLOGY

The general approach and methodology described below are indicative and non-exclusive. The methodology used must be developed in the application file.

##### GENERAL APPROACH

The team of experts provided by the consulting firm will work closely with the representatives of the MoBSE. A participatory approach is essential to ensure that what is proposed is in line with their needs. MoBSE representatives will guide the process, identify and involve relevant stakeholders, and take responsibility for the validation processes.

The team of experts will also need to liaise with the European Union Delegation in Banjul for sharing information and better anchoring technical assistance in existing and future initiatives.

##### METHODOLOGY

The implementation of Action 3 of the CAP Gambia requires the team of experts recruited to:

- Familiarize themselves with the main policy documents of the Gambia education system (Education Sector Strategic Plan 2016-2030, Education Sector Policy 2016-2030, The Gambia 2023-2027 Partnership Compact…)

- Participate in a scoping meeting with the focal points of the MoBSE and the Facility. Following this meeting, the lead expert will propose a brief note describing the work to be carried out, including the methodology and an updated timetable, considering logistical and security constraints. This note will describe in detail the strategy implemented to carry out the various activities.

- Liaise regularly with MoBSE representatives and the core technical group established for the co-development of the STEAM policy and the STEAM teacher competency framework. The core technical group includes participants (technicians and representatives) identified by MoBSE within different centralized and decentralized education directions and services.

- Ensure buy-in and ownership of the process and deliverables by the core technical group and other education stakeholders, through a consultative approach and interim validations.

- Collect data on the methodology and deliverables produced: feedback from experts, participant evaluations, and feedback from the core technical group.

##### COORDINATION

Throughout the mission, the lead expert (who will represent the team of experts, see section 3.6) is expected to hold technical meetings with the technical lead in Education (TLE) responsible for monitoring the implementation of the Facility's Gambia CAP and the Education Officer (EO). The frequency of these meetings will be defined at the start of the mission.

## DELIVERABLES

Deliverables are validated by the MoBSE and the RTIA Facility.

The main deliverables for action 3 are:

3.1. Development of a STEM/STEAM policy

Deliverable 1: report on best practices

This report is based on a benchmark of STEM/STEAM policies in Africa and globally; it will highlight best practices and include recommendations for the development of MoBSE STEAM policy.

Deliverable 2: technical note and PP presentation to the core group (methodology and format)

This presentation aims for the core group to validate the methodology (process) for the development of the STEAM policy, as well as the proposed policy format.

Deliverable 3: STEAM policy

This is the key deliverable – it might need several drafts. The official validation of the STEAM policy is the responsibility of the core group.

Deliverable 4: Operationalization plan

Once the STEAM policy validated, the operationalization plan co-developed with the core group will include roles and responsibilities in the implementation, a communication strategy, a timeframe, a monitoring plan, tools for an annual review and financial/ material resources needed.

Deliverable 5: Sensitization/ capacity building modules

Based on the operationalization plan, these modules might target different education stakeholders, with different objectives: information/ sensitization or capacity building.

Deliverable 6: Technical memo documenting the STEAM policy development process

This memo is an internal document for learning purposes for the Facility and MoBSE.

Deliverable 7: Advocacy strategy/ notes targeting donors and private sector

Based on the resources identified in the OP, the TA will develop advocacy strategies and products with the main purpose of collecting material and financial support (i.e. equipment, materials, extra funding…)

3.2. Development of teacher STEAM/digital competency framework

Deliverable 1: Report on best practices

This report is based on a benchmark of teacher STEAM/digital competency framework in Africa and globally, it will highlight best practices and include recommendations for the development of MoBSE framework.

Deliverable 2: Technical note and PP presentation to the core group (methodology and format)

This presentation aims for the core group to validate the methodology (process) for the development of the teacher's STEAM/digital competency framework, as well as the proposed framework format.

Deliverable 3: Teacher STEAM/digital competency framework

This is the version validated by the core group. Some components will be piloted before finalization of the framework.

Deliverable 4: Pilot/ consultations concept note

The core group will identify few components of the framework to be tested, for collecting the feedback of teachers, monitors and headmasters in particular. This concept note will summarize the scope of these pilot/ consultations (locations, timeframe, number of participants, etc.).

Deliverable 5: Report and PP presentation to the core group of the pilot/ consultations results

The report and presentation summarize findings and propose recommendations for adjusting the framework (if relevant).

Deliverable 6: Final version of the teacher STEAM/digital competency framework

This is the key deliverable: the final version of the teacher STEAM/digital competency framework, following (potential) adjustments based on the pilot/consultations results. The core group is in charge of official validation.

Deliverable 7: Operationalization plan

Once the teacher STEAM/digital competency framework validated, the operationalization plan co-developed with the core group will include roles and responsibilities in the implementation, a communication strategy, a timeframe, a monitoring plan, capacity building needs etc.

Deliverable 8: Sensitization/ capacity building modules

Based on the operationalization plan, these modules might target teachers, master trainers, and cluster monitors with different objectives: information/ sensitization or capacity building.

Deliverable 9: ToT report

Based on the OP and the capacity building needs identified, the TA might facilitate a ToT (up to 3 days, with an estimated number of 20 to 30 participants). The report will highlight the process, feedback of participants, and recommendations for improvement.

Deliverable 10: technical memo documenting the teacher STEAM/digital competency framework development process

This memo is an internal document for learning purpose for the Facility and MoBSE.

## ROLES AND RESPONSIBILITIES

###### The MoBSE is responsible for:

    - Providing all the documentation required for the desk review and the preparation of the field work if any

    - Facilitating the organization of meetings with relevant stakeholders (in-person and remotely)

    - Commenting on and approving deliverables

    - Sharing deliverables with key stakeholders

    - Ensuring that deliverables are taken on board by the national education authorities

    - Facilitating the validation process by the national authorities when necessary.

###### The RTIA Facility is responsible for:

    - Contracting and facilitating the integration of the team of experts by providing all available documents and resources

    - Supporting and monitoring the team of experts’ work from start to finish

    - Acting as the team of experts’ main resource person

    - Ensuring quality control of deliverables in collaboration with the MoBSE focal points

    - Acknowledging final validation of deliverables by all parties

    - Evaluating the team of experts’ overall performance under this mandate.

###### The team of experts represented by the lead expert, are responsible for:

    - Reviewing and commenting on these Terms of Reference (ToR)

    - Ensuring that all deliverables comply with the ToR and the guidelines formulated during the mission scoping meeting, in accordance with the agreed timetable

    - Implementing all stages of the validated methodology

    - Compiling and submitting the final report in a timely manner

    - Ensuring that stakeholders are consulted throughout the mission

    - Organizing /co-organizing consultations with technical and financial partners and national stakeholders working in the education sector

    - Behaving with the highest levels of personal integrity and committing to the required standards of good conduct

    - Submitting data relating to contractual services, RTIA monitoring and evaluation and quality assurance requirements, by collecting attendance sheets, participating in the consultants’ satisfaction survey, and sharing information from the participants’ feedback survey with the RTIA.

    - Immediately reporting to the Facility any difficulties that could hinder the progress and achievement of the mission's objectives.

## LOGISTICS

The contractor shall be responsible for organizing the workshops and training-of-trainers activities required under these Terms of Reference.

A maximum ceiling of EUR 6,100 excluding VAT is allocated to eligible workshop-related costs.

. Such arrangements shall be organized and financed by the Contractor.

Travel

The international expert (s) shall undertake in-country missions for a maximum of thirty (30) working days during the implementation period. This may require travel to Banjul, The Gambia, for up to four (4) missions over the duration of the assignment. All travel-related costs, including international airfare, accommodation, local transportation, and daily subsistence allowances (DSA/per diem), shall be included in the Financial Offer. Per diem rates shall be based on the applicable European Union (EU) rates in force at the time of travel.

Training of Trainers (ToT) Workshop

The assignment shall include one Training of Trainers (ToT) workshop of up to three (3) days for a maximum of thirty (30) participants in support of Deliverable 9 under Action 3.2. The Contractor shall be responsible for all organizational and logistical arrangements related to the workshop.

The Financial Offer shall include a detailed breakdown of all workshop-related costs, including venue (if applicable), catering, training materials, participants' daily allowances, and travel costs for up to ten (10) participants travelling from locations outside Banjul. All such costs shall be fully integrated into the Financial Offer.

Security

Subject to the provisions of the Contract, the Contractor shall be solely responsible for the safety and security of the personnel, subcontractors, equipment, and property mobilized for the performance of the assignment. The Contractor shall ensure that all personnel comply at all times with its internal safety and security procedures and instructions. Expertise France shall bear no liability for any incident, loss, damage, or security breach affecting the Contractor's personnel, subcontractors, or equipment during the performance of the Contract.

## ESTIMATED NUMBER OF DAYS AND TIMETABLE

The assignment shall be implemented by a team of international and national experts. The implementation of the activities will include both remote work and in-country missions. The international expert is expected to contribute a total of sixty (65) working days over the duration of the assignment, including time spent on in-country missions.

The proposed timeline for the implementation of the activities is presented in the table below. However, this timeline is indicative and shall be reviewed, refined, and finalized during the inception phase, and formally approved as part of the Inception Report.

| Activities/Deliverables | Estimated Delivery date |
| --- | --- |
| 3.1. Development of a STEM/STEAM policy |  |
| - Preliminary study report on best practices: desk review, benchmark | 30 September 2026 |
| - Technical Note & PP presentation | 10 October 2026 |
| - Development of the STEM/STEAM policy | 30 December 2026 |
| - Development of the STEM/STEAM policy operationalization plan (OP) | 15 March 2027 |
| - Development of sensitization/ capacity building modules (based on OP) | 30 April 2027 |
| - Technical memo documenting the policy development process | 30 April 2027 |
| - Development of an advocacy strategy (donors/ private sector) | 30 April 2027 |
| 3.2. Development of teacher STEAM/digital competency framework |  |
| - Report on benchmark of best practices/ initiatives | 30 September 2026 |
| - Technical note and PP presentation | 10 October 2027 |
| - Development of the STEAM/ digital competency framework | 26 February 2027 |
| - Piloting of the competency framework-concept note | 30 April 2027 |
| - Report and PP presentation to the core group | 30 April 2027 |
| - Development of the framework operationalization plan | 15 March 2027 |
| - Development of capacity building modules (based on OP) | 30 May 2027 |
| - Training of trainers (based on OP)- Report | 25 August 2027 |
| - Technical memo | 31 August 2027 |

# EXPERTS’ PROFILES

Expertise France is recruiting a consulting firm that will provide a technical assistance team composed of several experts, to carry out the activities detailed above.

The team should include international and national experts. The international experts should be willing to travel to the Gambia. A gender-balanced team is an added value.

The proposed experts may not be members of the civil service, unless they are regularly placed on leave or seconded at the time of their assignment. In this case, proof from their original administration must be included with the application. The proposed experts may not have participated in the development of the CAP and of these Terms of reference.

Composition of the technical assistance team

The consulting firm shall propose a team comprising both international and national experts. The firm is free to determine the number of experts required to deliver the assignment, provided that:

- the total input of all international experts combined is 65 expert-days; and

- the total input of all national experts combined is 30 expert-days.

These allocations are fixed for the purpose of the technical and financial proposals. They apply to each category as a whole and not to each individual expert. For example, the 65 international expert-days may be allocated among one or several international experts, and the 30 national expert-days may be allocated among one or several national experts.

Tenderers shall provide a clear breakdown showing the number of days allocated to each proposed expert by activity and deliverable. The total number of expert-days proposed must remain 65 international expert-days and 30 national expert-days.

One of the international experts shall be designated as the Team Leader and shall assume overall responsibility for the coordination, quality and timely delivery of the assignment..

### DESIRED PROFILES

Lead expert(s) (International Expert) 65 days :

###### Academic qualification:

- Advanced degree in education policy, or related field

###### General work experience:

- Minimum of 10 years of experience in education policy, and/or in teachers’ governance – in particular for the design of education policies and teachers’ competency frameworks

###### Specific work experience:

- Strong experience in/ knowledge in STEAM education. Proven knowledge and experience of education policies and systems in Western Africa

###### Language Proficiency:

- Excellent proficiency in English (both written and spoken);

###### Interpersonal and soft skills and experience

- Ability to work in a team and communicate effectively with various stakeholders

- Experience in technical and political dialogue, with an aptitude for navigating complex institutional contexts

###### Additional assets

- Previous experience working in the Gambia

- Familiarity with the education context and policies of the Gambia

National Expert (s) 30 days:

- In-depth knowledge of education policies and context in the Gambia

- In-depth knowledge of STEAM education challenges in the Gambia (including gender issues)

- In-depth knowledge in STEAM education standards and frameworks

- Experience in STEAM teachers’ education and professional development

- Experience in developing teachers’ competency frameworks

- Expertise in gender in education (gender responsive pedagogy; orientation of girls and boys etc.)

- In depth knowledge of gender issues in STEAM education

- Experience in approaches and methodology for STEAM education

- Experience in developing contents for and facilitating training of trainers

- Expertise in coordination, facilitation and mediation

The consulting firm is free to propose as many experts as it wishes. Preferably, the consulting firm will propose experts who are proficient in English, with a mix of international and national experts for the different areas of expertise. The international expert(s) will be mainly tasked with the first component activities of action (3.1) while the national expert will be mainly responsible for action 3.2.

# APPLICATION SUBMISSION

Interested consulting firms are requested to submit a technical offer and a financial proposal in response to these Terms of Reference. All the procedures for submitting tenders are set out in the document “Tender rules”.