# Terms of reference 
and technical Specifications

- General information

| # Assignment name | Delivery of a series of media training sessions in the Forestry-Climate Change-Biodiversity (EU-FCCB) space in Papua New Guinea (PNG) |
| --- | --- |
| # Beneficiary | Main beneficiaries: Key PNG media institutions and agencies, FCCB government and non-government institutions, school youth, and women Other and indirect beneficiaries: EU-FCCB partners, and general public |
| # Country | Papua New Guinea |
| # Total estimated number of days | # 50 days over a 12-month period from the contract award # To be performed by 02 or 03 experts, including 01 or 02 missions to Papua New Guinea |

- Context and justification of the need

Expertise France, a subsidiary of the French Development Agency (Agence Française de Développement, AFD) Group, is the French government’s international technical cooperation agency. Its role is to design and manage donor-funded international cooperation projects that aim to sustainably strengthen public policies in developing and emerging countries in fields such as governance, security, health, education, and environment. The European Union (EU), the French Ministries, and AFD constitute Expertise France’s main donors.

In 2024, Expertise France was active in 147 countries worldwide, with 384 projects under implementation and revenue of 447 million euros. The agency has a workforce of 870 personnel in its headquarters in Paris and about 1,450 personnel internationally. More information about Expertise France is available on the website: https://www.expertisefrance.fr/

In Papua New Guinea, Expertise France is implementing the national component of the European Union-funded Forestry-Climate Change-Biodiversity (EU-FCCB) Programme. The EU-FCCB Programme is an international cooperation programme funded by the EU whose general objective (GO) is: “To support a development model that reconciles forestry, climate change, and biodiversity with sustainable, inclusive, and gender-responsive green growth and jobs at the national and pilot subnational/community levels”. Its three specific objectives (SOs) are:

- SO1: Effective implementation of evidence-based FCCB policies, governance, and institutional frameworks.

- SO2: Improved FCCB awareness, knowledge, capacities, and mobilisation.

- SO3: Increased inclusive and gender-responsive green growth.

The EU-FCCB Programme consists of three components, one of which is a significant component implemented by Expertise France: “support at the national/institutional level with spill-over effects at the local/community level” – the national component.

The National Component includes interventions across all three specific objectives of the EU-FCCB Programme, including support for a number of PNG-based research, education, and awareness institutions, as well as for PNG-based communities, civil society organisations, and private sector organisations engaged in conservation, sustainable livelihoods, and sustainable value chain development. More information about the EU-FCCB Programme and the national component implemented by Expertise France is available at the website: https://fccbpng.eu/

Effective communication and professional media engagement are vital to ensuring that policy developments, conservation initiatives, and community impacts are conveyed accurately and responsibly. To improve the quality of environmental communication and journalism, the Programme aims to strengthen the capacity of local (junior) journalists, government communication officers/spokespersons, and media students in key areas of modern media production and storytelling.

This initiative aims to enhance participants' capacity to generate precise, engaging, and ethically sound content on forests, biodiversity, climate change, and sustainable development. The concept draws upon established training methodologies, including news reporting, podcast production, and visual storytelling, which integrate technical competencies with practical field experience, with the overall goal to:

“To enhance the professional capabilities of journalists, government spokespersons, and media students in effectively communicating issues related to forests, climate change, and biodiversity conservation through high-quality journalism and multimedia storytelling.”

- Objectives

For this assignment, the Programme is seeking a media institution to:

- Improve participants’ skills in news reporting and professional writing.

- Build capacity in audio storytelling and podcast production for digital communication.

- Develop practical skills in visual storytelling and short documentary production.

- Strengthen ethical journalism and responsible reporting on environmental-related issues.

- Promote collaboration between media professionals and government communication officers.

- Description of the assignment

- Activities

The selected media institution will be responsible for designing and delivering a comprehensive media training programme, based on a submission of a proposed plan, which includes key activities as follows:

- Inception and Planning

- Finalise training implementation plan and schedule

- Coordinate logistics with the EU-FCCB national component team

- Select trainers and participants

- Prepare training materials and learning tools

- Needs Assessment

- Conduct assessments before and after training to evaluate participants’ existing knowledge and skills, and assess improvements.

- Curriculum Development

- Develop training modules and materials, including an understanding of Artificial Intelligence (AI) ethics and usage in reporting, covering:

- News reporting and writing

- Audio podcast production

- Visual storytelling/video production

- Training Delivery

Conduct three practical training modules:

4.1. News Reporting and Writing

  - Understanding news values and storytelling

  - Interview techniques and sourcing

  - Professional news writing

  - Ethics and responsible reporting

  - Practical field assignments and editing

4.2. Audio Podcast Production

- Podcast concept development

- Scriptwriting for audio

- Recording techniques

- Audio editing

- Podcast distribution strategies

4.3. Visual Storytelling / Video Production

- Story development and scripting

- Camera and audio techniques

- Documentary production

- Video editing and post-production

- Field shooting and storytelling

- Mentorship and Field Production

Support participants in producing capstone media projects, such as:

- News stories

- Podcast episodes

- Short documentary videos

- Monitoring and Evaluation

- Conduct pre-training and post-training assessments

- Evaluate participant outputs against professional standards:

- Accuracy

- Clarity

- Technical quality

- Ethical integrity

- Reporting

Submit a final training report including:

- Training methodology

- Participant evaluation results

- Documentation of outputs

- Recommendations for future training

- Other relevant information and data

- Training methodology

The training should adopt an interactive and practice-oriented approach, combining:

- 60% experiential learning, fieldwork, practical assignments, production exercises.

- 20% peer learning, group critique sessions, and collaborative exercises.

- 20% theoretical input: Lectures on journalism principles and communication strategies, including an understanding of Artificial Intelligence (AI) ethics and usage in reporting.

- Anticipated deliverables

The training institution will deliver:

- Detailed training curriculum and materials

- Pre-training knowledge assessment report

- Implementation of three training modules

- Participant capstone projects

- Post-training knowledge assessment report

- Digital toolkit or “media playbook” and relevant templates for participants

- One virtual refresher session after the completion of the media training programme

- Other documents supporting the training plan

- Final assignment report

- Coordination

The Service Provider shall designate a single focal point for the implementation of the assignment.

For Expertise France, the sole contact person for all contractual and operational matters related to this assignment will be:

Ms. Iroise Guenneugues

Project Management Officer – EU-FCCB National Component

Email: iroise.guenneugues@expertisefrance.fr

The Service Provider will also work in close collaboration with the Programme’s Communication and Knowledge Advisor.

A kick-off meeting shall be held no later than seven (7) calendar days after notification of the contract award.

The Service Provider shall maintain close collaboration with the Expertise France team throughout the assignment, from the preparation phase through to its completion. Regular communication shall be maintained to provide progress updates, discuss key findings, and address any challenges or issues encountered during implementation.

- Place, duration and terms of performance

  - Implementation period: the assignment is expected to be completed over approximately 12 months, starting from the time the contract is signed, and will include preparation, training delivery, mentorship, and reporting.

  - Start date: contract signature date

  - End date: 12 months later

  - Effective duration: 50 expert days

  - Schedule/programme: the training/media institution shall include in its proposal a schedule covering all required activities and deliverables

  - Contract modality:

- The contract would be a purchase order-based framework contract based on a unit price for days of expertise to be provided by the Consulting Firm. Expertise France would issue purchase order (POs) for days of expertise by the Consulting Firm according to the emergence of its needs on the basis of an approved workplan. Therefore, the number of days requested could be different from the indicative durations indicated above.

- The financial offer shall include a lump-sum provision covering all travel-related expenses associated with missions to Port Moresby. This includes air travel, accommodation, and daily subsistence allowances (per diem).

- Required expertise and profile

  - Number of experts: to be defined by the training institution, preferably at least two to three experts

  - Profile of the designated institution responsible for contract execution

Interested institutions will be evaluated based on the following criteria:

  - Institutional Experience

- Minimum seven years of experience in journalism, media training, and/or communication capacity development

- Demonstrated experience in multimedia training (print, audio, video)

  - Technical Expertise

Strong expertise in:

- Journalism and media training

- Podcast and digital media production

- Video storytelling and documentary production

- Media ethics and professional standards

  - Experience in Development Communication

- Experience working with government institutions, development partners, media institutions, universities, or/and NGOs

- Familiarity with environmental, climate, and/or biodiversity conservation communication is an advantage

  - Training Methodology

- Ability to deliver participatory and practical training

- Experience mentoring participants in field production and storytelling

  - Trainer Qualifications

Proposed trainers should demonstrate:

- Professional journalism or media production experience

- Training and facilitation experience

- Portfolio of published media content

  - Organisational Capacity

- Ability to manage logistics and training coordination

- Availability of training facilities and equipment

- Administrative and financial management capacity

  - Value for Finance Budget

- Competitive financial proposal

- Efficient use of resources and training time

- Monitoring-evaluation

Performance indicators

| Deliverables | Immediate effects | Intermediate effects | Performance indicators | Means of Verification |
| --- | --- | --- | --- | --- |
| # Detailed training curriculum and materials | Participants have access to structured, context specific learning resources | Standardised communication and media practices adopted across participating institutions | Training curriculum and materials developed and approved Number of training modules and learning resources produced | Approved curriculum Training materials and presentations Consultant reports |
| # Pre-training knowledge assessment report | Baseline knowledge, skills, and capacity gaps identified | Training content tailored to participants’ needs and institutional priorities | Pre-training assessment conducted Percentage of participants completing assessment | Assessment report Survey results and participant database |
| # Implementation of three training modules | Participants gain practical knowledge and skills in communication, media engagement, and content production | Improved quality and effectiveness of communication and visibility activities | Number of training modules delivered Number of participants trained Participant attendance rate | Training report Attendant records Training evaluation |
| # Participant capstone projects | Participants apply acquired skills to practical communication challenges | Increased production of quality communication products and media outputs within institutions | Number and percentage of participants completing capstone projects Quality rating of capstone projects | Complete projects Project evaluation report Participants presentations |
| # Post-training knowledge assessment report | Improved knowledge and competencies demonstrated by participants | Enhanced institutional communication capacity and performance | Percentage increase in participant knowledge scores between pre- and post-assessments Percentage of participants demonstrating improved competency levels | Post training assessment report Assessment results database |
| # Digital toolkit or “media playbook” and relevant templates for participants | Participants have access to practical tools and guidance for communication activities | Consistent application of communication standards and good practices across organisations | Digital toolkit developed and disseminated Number of participants receiving toolkit Percentage of participants reporting toolkit use | Toolkit Distribution records Follow-up survey results |
| # One virtual refresher session after the completion of the media training programme | Participants reinforce learning and address implementation challenges | Sustained application of skills and continued professional development | One refresher session conducted Number of participants attending refresher session Participant satisfaction level | Refresher session report Attendance record Feedback survey report |
| # Other documents supporting the training plan | Training implementation is adequately documented and coordinated | Improved institutional capacity to replicate or scale training initiatives | Number of supporting documents produced Training implementation milestones achieved | Training plan documents Progress report |
| # Final assignment report | Lessons learned, achievements, and recommendations documented | Evidence available to inform future capacity-building programmes and communication strategies | Final report completed and submitted on time Recommendations endorsed | Final assignment report Stakeholder feedback report |

- Practical information

Interested institutions should submit:

- Technical proposal describing methodology and training approach

- Detailed workplan and timeline, including one to two missions to Papua New Guinea

- Profiles of trainers and experts

- Institutional experience and portfolio

- Financial proposal

--/