|  | PROCUREMENT CONTRACT |
| --- | --- |
|  | ☒Service – ☐Supplies |
|  | Number: |
|  | Object of the contract: Provision of Mid-Term Evaluation services for the EU4Innovation East project - 23EDI0C190 |
|  | MAXIMUM AMOUNT OF THE CONTRACT: state here the maximum amount of all services/supplies that may be delivered under the contract |
| Notification date:. This contract is subject to the French Public Procurement Code in its latest version in force as enacted by Order No. 2018-1074 issued on 26 November 2018 and its Implementation Decree No. 2018-1075 issued on 3 December 2018 constituting the regulatory aspects of the Public Procurement Code (“CCP”). It is awarded by means of: adapted procedure in application of Articles L. 2123-1 and R. 2123-1 to R. 2123-7 of CCP. |

TABLE OF CONTENTS

special conditions – commitment procedure	1

ARTICLE 1:	Object of the contract	2

ARTICLE 2:	General characteristics of the Contract	3

Form of the Contract	3

Term of the Contract	3

Commencement and deadline of service provision	3

ARTICLE 3:	Financial provisions	3

Amount of the Contract	3

Form of prices	4

Advance	4

Payment procedure	4

Payment terms and late payment interest	5

Presentation of payment demands	5

Bank transfer	6

Value added tax (VAT)	6

Taxes and duties	6

ARTICLE 4:	inspection and acceptance activities	6

Inspection activities	6

Acceptance of services	6

ARTICLE 5:	Specific terms of execution	6

Deliverables table	6

Place of execution	7

Language of the Contract	7

Commitments of the Contractor	7

Confidentiality	8

Provision of documents	8

Insurance	8

Contact person and communication	8

Understaking against deforestation	9

ARTICLE 6:	Re-examination clause	9

ARTICLE 7:	Similar services	10

ARTICLE 8:	penalties	10

Penalties for periodic documentary deliverables	10

Penalties applicable to submission of final deliverables	10

ARTICLE 9:	intellectual property	10

Definitions	10

Ownership of results	10

Exploitation of results	10

Licensing of pre-existing rights	11

Guarantees	11

Image rights	11

ARTICLE 10:	Termination of the contract	11

General terms of performance	11

Termination of the Contract due to the non-availability of a designated expert	12

Procedure	12

ARTICLE 11:	safety and security measures and responsabilities	12

ARTICLE 12:	ethics	12

ARTICLE 13:	Administration of personal data	12

ARTICLE 14:	Dispute resolution - applicable law	13

ARTICLE 15:	Derogation from the CCAG	13

ARTICLE 16:	AUDIT	14

ARTICLE 17:	Final provisions	14

Annex I – Terms of referenses	16

Annex II – Technical And financial offer	26

# special conditions – commitment procedure

Between:

EXPERTISE FRANCE SAS 40, boulevard de Port Royal - 75005 PARIS, France A simplified joint-stock company with share capital of €828,933 registered under the following numbers: - SIRET no.: 808 734 792 00035 - Intra-community VAT number: FR36 808734792 Represented by Mr Jérémie PELLET, Managing Director, of the first part,

and:

Contractor Name: (Hereafter the “Contractor”) - Registered office address: - Registration number at the trade and companies’ registry: - Intra-community VAT no. (as applicable): Represented by: of the second part,

(Hereafter referred to collectively as the “Parties“)

Whereas:

This Service Contract is part of the cooperation project hereinafter referred to as the “MAIN CONTRACT”, whose code is 23EDI0C190 signed on 26 July 2024 by Expertise France and EU Commission, concerning “EU4Innovation East” – Support to Digital innovation in the Eastern Partnership region for the benefit of Ukraine, Moldova, Georgia, Armenia and Azerbaijan implemented by Expertise France.

In the light of the foregoing, the following is agreed:

- Object of the contract

The object of this contract (hereafter the “Contract) is “Provision of evaluation services for the EU4Innovation East project”.

Contractual documents

The Contract is composed of the contractual documents set out below in decreasing order of priority:

- This document and its annexes:

- Annex I attached: Specifications/ToR;

- Annex II attached: Technical/Financial offer

- Annex III attached: Sworn statement on exclusion criteria, the absence of conflict of interest

- The Code of Conduct of EXPERTISE FRANCE (available at https://www.expertisefrance.fr/documents/20182/426622/Expertise+France+%E2%80%93+Code+of+conduct/82cf6060-4768-4b25-8817-ccba1d86e568);

- CCAG - General administrative clauses applicable to public procurement for day-to-day supplies and services approved under the Order of 30/03/2021, subject to the exceptions set out in the Contract.

These documents constitute the entirety of the agreement between the Parties with regard to the Contract. They supersede all verbal and written communications, procedures, agreements, commitments, guarantees and settlements referring to its object and facts that may have been made by or on behalf of a Party to the other Party before the notification date. These documents are acknowledged by the Parties to represent the sole and complete expression of the terms of their agreement.

Without prejudice to the general rules applicable to administrative contracts, any modification to the Contract or the waiver of any right resulting from the Contract must be covered by an amendment signed by a duly authorized representative of each Party.

- General characteristics of the Contract

## Form of the Contract

The Contract is a public contract for services at fixed and total prices.

The services shall be carried out according to the sequencing and in the order set out in the timeframe below; the validation (notification of an acceptance decision) of each stage conditions the start of execution of the next stage.

## Term of the Contract

The term of the Contract is 5 months from its Notification date to the Contractor by Expertise France.

The Contract shall expire after all services/supplies have been delivered by the Contractor and all rights and obligations of the Parties resulting from the Contract have been extinguished. If all or some of the services/supplies remain outstanding by the specified period, the Contractor must immediately take all necessary steps to complete delivery without being able to claim any remuneration in this regard.

## Commencement and deadline of service provision

The timeframe for execution of the services is specified in the attached Annex I of the CONTRACT and set out as follows:

| Evaluation Phases and Deliverables | Implementation period | Deadline for the deliverable |
| --- | --- | --- |
| D1 – Inception Report (desk review, preliminary interviews with project team, evaluation matrix, methodology, data collection plan, workplan) | Month 1 from T0 | Within ten (10) working days after one (1) month from T0 |
| D2 – Primary Data Collection and field missions report (conduct interviews, carry out surveys, transmit datasets to the project, interim report) | Month 2 from T0 | Within fourteen (14) working days after two (2) months from T0 |
| D3 – Draft Evaluation Report (data analysis, findings and preliminary recommendations) +Knowledge Product | Month 3 from T0 | Within twenty (20) working days after three (3) months from T0 |
| D4 – Validation Workshop report / Presentation of Findings | Month 4 from T0 | Within three (3) working days after the validation of the draft report |
| D5 – Final Evaluation Report with integrated feedback | Month 4 from T0 | Within three (3) working days after four (4) months from T0 |

| Deliverables | Main content | # pages max. |
| --- | --- | --- |
| Deliverable #1 – Inception report | - Preliminary Document Review — a summary of key findings from the desk review of project documents, highlighting issues and questions to explore during the evaluation - Preliminary interviews with project team - Evaluation Matrix —a refined evaluation framework with a selection, prioritization, reformulation of evaluative questions, ensuring full coverage of the evaluation's objectives and the OECD/DAC criteria (relevance, coherence, effectiveness, efficiency, and orientation towards impact) - Methodology — a detailed description of the evaluation methodology, including the mix of quantitative and qualitative methods, the rationale for their selection, the proposed sampling approach, and a transparent identification and discussion of the anticipated limitations of the evaluation - Data Collection Plan — the overall data collection strategy, the final tools to be used during the evaluation (interview guides, focus group discussion guides, survey questionnaires, and observation checklists, developed in line with the evaluation matrix and cross-cutting principles), and the proposed list of people and organizations to interview - Work Plan — a finalized work plan presenting all tasks, a clear description of each evaluation team member's roles, including the lead evaluator milestones, deliverables, and timelines from inception to final report, including planned data collection missions across Armenia, Moldova, and Ukraine | 15 pages + annexes |
| Deliverable #2 - Primary Data Collection and field missions | - Raw Primary Data — all quantitative and qualitative primary data collected during the evaluation, submitted to the project in raw, unprocessed format - Cleaned and Processed Data — all quantitative and qualitative primary data cleaned, organized, and processed, submitted to the project in a structured format - Field Visit Notes — written records of observations, key points, and insights from each field visit and data collection mission - Interim report (in the lighter format of a slideshow) - is submitted at the end of the data collection phase to summarize the findings gathered using each of the data collection tools deployed by the evaluation team. The document will serve as the basis for an interim meeting between the evaluation team and the evaluation steering group aiming at sharing a common understanding of the collected data; jointly sketching the main lines of the cross-analysis; identifying gaps in data collection that may require additional remote follow-up. |  |
| Deliverable #3 - Draft Evaluation Report (V1) +Knowledge Product | - Draft evaluation report shall include: - Executive Summary — a concise two-page summary of the evaluation's conclusions and recommendations, written for a non-technical audience - Methodology Overview — a transparent account of the evaluation methodology as implemented - Answers to the Evaluation Questions - Good Practices and Lessons Learned — including the Knowledge Product - Recommendations | 40 pages + annexes |
| Deliverable # 4 Three Validation workshops to Stakeholders (online) in Armenia, Moldova and Ukraine | During the workshops, EF will challenge the preliminary conclusions—ensuring they are sufficiently supported by evidence and identifying any analytical gaps. The evaluators' wording will be refined to reach a collectively agreed formulation of the final conclusions, after which the recommendations will be co-developed. The PowerPoint Presentation shall include: - Preliminary conclusions - Good Practices and Lessons Learned — including the Knowledge Product - Summary of the Work — an overview of the evaluation work carried out - Summary of Interviews — a consolidated account of the interviews conducted - Data Reliability and Scope Analysis — an assessment of the reliability and scope of the data collected - Recommendations |  |
| Deliverable # 5 Final Evaluation Report (V2) | - Finalized Report — all sections from the Draft Report (V1), revised and finalized based on comments from stakeholders, the EU, and Expertise France - Updated PowerPoint Presentation - Comments and Revisions Matrix — documenting all comments received, how each was addressed and integrated, and a clear justification where a comment was not incorporated |  |

If all or some of the services/supplies remain outstanding within the specified deadline, the CONTRACTOR must immediately take all necessary steps to complete delivery without being able to claim any remuneration in this regard.

- Financial provisions

## Amount of the Contract

The amount of the CONTRACT is:XXXX € exc. VAT.

This amount equates to the total and fixed price of the Contract, which Expertise France undertakes to pay, after validation, all the services due under the Contract have been accepted without reservation. As pricing is fixed, it includes all costs relating to the corresponding service provision.

The fixed amount  corresponds to the total amount Expertise France undertakes to pay, after validation, all services due under the Contract have been accepted without reservation as spcecified in the Annex 1 and Annex 2. As pricing is fixed, it includes all costs relating to the corresponding service provision and/or delivery of supplies.

## Form of prices

Prices are firm and non-modifiable.

## Advance

## No advance will be made.

## Payment procedure

- Interim payment

Interim payments are set out in this contract and shall be made in accordance with the following terms and conditions.

| Amount of instalment | Payment deadline |
| --- | --- |
| A payment equal to 20% of the total amount of the contract | After submission and approval by Expertise France of the corresponding deliverables: - D1 – Inception Report - invoice |
| A payment equal to 80% of the balance from the total of the contract | After submission and approval by Expertise France of the corresponding deliverables: - D2 – Primary Data Collection and field missions report -D3 – Draft Evaluation Report -D4 – Validation Workshop report -D5 – Final Evaluation Report - invoice |

## Payment terms and late payment interest

Payment is always made out in the name of the issuer of the invoice or of the expense reimbursement request.

Overall payment terms for monies due under the Contract are thirty (30) days maximum from the date of receipt of the complete invoice, including all supporting documentation, or the date of service/supply acceptance if this date is later. Any missing document will prevent payment.

If these payment terms are not respected, Expertise France will pay late payment interest to the Contractor pursuant to Article R. 2192-10 et seq. of the CCP on the fight against late payment in public procurement contracts. The rate applied shall be the interest rate of the European Central Bank for its main and most recent refinancing operations, as applicable on the first day of the semester of the calendar year during which late payment interest started to accrue, plus eight percentage points.

The amount of the fixed indemnity to cover collection costs is set at forty (40) euros and will be systematically paid in addition to late payment interest. Interest below €40 shall not be mandated.

## Presentation of payment demands

In addition to the legal notices (intracommunity VAT no.), invoices relating to the Contract must contain the following information:

- Company name, address and registered office of the Contractor;

- Registration number of the Contractor (SIRET or equivalent);

- Bank account details;

- The code of the department acting as specifying department (stated in the article entitled Contact person and communication);

- Reference number of the Contract;

- The reference and title of the cooperation project concerned (if applicable);

- Clear and accurate description of the equipment/supplies sold and/or services performed;

- If the Contractor’s bank details are not stated on invoices, it must provide a statement or certificate of bank or post office account details, with the third-party form duly completed in all cases.

Invoices are to be forwarded via the Chorus Pro system, and must state the department code provided above corresponding to the department of Expertise France on behalf of which the Contract has been placed.

If the Contractor is not obliged to forward invoices via Chorus, it may submit its invoices to the contact person stated in the article entitled Contact person and communication.

Invoices for advances must be accompanied by the corresponding supporting documentation validated by Expertise France.

Invoices for balances (partial definitive payments) must be accompanied by a copy of the acceptance decision for the corresponding services and/or supplies.

Any missing document will prevent payment.

## Bank transfer

Payment for invoiced services/supplies will be made to the bank account identified in the third-party sheet.

Payment is always made out in the name of the issuer of the invoice or of the expense reimbursement request.

## Value added tax (VAT)

The Contractor must state the VAT rate applicable to the transaction or, as applicable, its VAT exemption by stating on the invoice the relevant provisions of the French General Tax Code or those of Directive 2006/112/EC of 28 November 2006.

Any Contractor benefitting from exemption must state “VAT exempt” in accordance with the rules that apply to it.

## Taxes and duties

The Contractor shall be directly responsible for all taxes and duties that may be levied against it under the Contract, both in the country of its registered office and in those of project implementation.

- inspection and acceptance activities

## Inspection activities

Inspection activities will be carried out for services and supplies as set out in Chapter 5 of the CCAG-FCS. By way of derogation from Article 23 of the CCAG-FCS, inspection activities will be carried out by:

- The Country coordinator, Ionela Titirez

- the Deputy Project Director, Charles Mathiaux

## Acceptance of services

By way of derogation from Article 25 of the CCAG-FCS, acceptance activities will be carried out by:

- the Country coordinator, Ionela Titirez

- the Deputy Project Director, Charles Mathiaux

Any lack of response from Expertise France shall not equate to tacit acceptance of services or supplies.

- Specific terms of execution

## Deliverables table

All timelines indicated below are calculated from the notification date of the contract (T0). The deadlines correspond to the latest submission dates of the deliverables

| Activity | Place | Period (indicative) | Duration (man/days) |
| --- | --- | --- | --- |
| Deliverable 1 Inception report | Online | Month 1 from T0 | 10 |
| Deliverable 2 Primary Data Collection and field missions report | Online | Month 2 from T0 | 14 (including 10 days for field missions) |
| Deliverable 3 Draft Evaluation Report (V1) +Knowledge Product | Online/Offline | Month 3 from T0 | 20 |
| Deliverable 4 Validation workshops (3x) | Online | Month 4 from T0 | 3 |
| Deliverable 5 Final Evaluation Report (V2) | Online | Month 4 from T0 | 3 |
|  |  |  | TOTAL: 50 (man/days) |

## Place of execution
The services shall be performed primarily online. While certain analtical work, meetings, and preparatory activities may be carried out remotely, the Contractor shall ensure a strong local presence throughout the assignment to enable effective engagement with stakeholders, beneficiaries, and institutional partners.

The costs associated with these missions, including travel, accommodation, subsistence and any related expenses, are deemed to be included in the Contract price. No additional reimbursement shall be made by the Contracting Authority.

## Language of the Contract

This document is written in English, which shall be the reference language for any dispute that may arise regarding the meaning or interpretation of the Contract, to the exclusion of any other language.

## Commitments of the Contractor

The Contractor is subject to a performance obligation and therefore undertakes to:

- comply with the Specifications;

- immediately notify Expertise France in writing of any communication or instruction relating to the services/supplies that it may receive from the Client (beneficiary country or public entity) or from a third party, and not to comply with any such communication or instruction until having discussed the matter with Expertise France and after receiving the latter’s written authorization;

- notify any difficulty it may encounter with the performance of its obligations under the Contract;

- comply with all applicable laws and regulations of the country of delivery of the services/supplies and adopt an attitude and act vis-à-vis third parties in the interests of Expertise France, such that Expertise France cannot be reproached in this regard by the Client, or by any person the latter may have designated;

- protect the interests of Expertise France vis-à-vis the Client;

- act as a loyal advisor vis-à-vis Expertise France;

- present itself vis-à-vis the Client, partners and local authorities as a Contractor engaged by Expertise France;

- apply the undertakings of Expertise France as expressed in its Code of Ethics, provided in Annex 5 of the Contract.

In the context of Contract execution, the Contractor undertakes to:

- perform the services/supplies in a diligent, effective and economic manner, in accordance with generally accepted techniques and practices;

- employ appropriate modern techniques and safe and affective processes.

## Confidentiality

The Contractor shall treat as private and maintain the confidentiality of all documents and information received or which it becomes aware of in the context of the Project. It shall maintain the secrecy thereof and not use them for any purpose other than execution of the Contract.

In this regard, the Contractor undertakes:

- To protect and maintain the confidentiality of information considered or presented as such;

- To handle confidential information, it receives with the same degree of care and protection as it applies to its own confidential information;

- only to reveal confidential information to its personnel and third parties involved in performance of the Contract after having received prior written and express approval from Expertise France;

- to take all necessary steps such that its personnel and third parties involved in execution of the Contract, who become aware of confidential information, undertake to treat such information with the same level of confidentiality as set out in this clause;

- As and when required, to reiterate the confidential nature of such information to its personnel and third parties involved in the execution of the Contract, as soon as said confidential information is communicated to the aforementioned persons;

- to reiterate the confidential nature of confidential information prior to any meeting during which confidential information is communicated.

Apart from where necessary for the purposes of service delivery, the Contractor may not disclose any element of the Contract without prior written consent from the other party.

## Provision of documents

Expertise France shall ensure that the Contractor receives in good time all the documents (as set out below) required for delivery of the services/supplies:

- ToR

- Technical and financial offer of the Main Contract

- Specifications of the MAIN CONTRACT

## Insurance

The Contractor shall take out, and maintain at its own expense, third-party and professional liability insurance policies covering the physical injury and material and consequential damage that may arise from delivery of the services/supplies.

The Contractor shall also take out, and maintain at its own expense, insurance policies covering its working accident and occupational illness liability with regard to its agents assigned to delivery of the services/supplies.

The Contractor must be able to produce on request by Expertise France all certificates demonstrating its possession of the aforementioned policies.

## Contact person and communication

All communication and notifications between the Parties under the Contract shall take place in written form, either through the exchange of e-mails or via registered letter with acknowledgement of receipt, where the latter form is prohibited in certain cases under the Contract, and shall be deemed to have been validly served from its receipt by the addressee.

All correspondence shall be forwarded, all carriage costs paid, to the following addresses:

| For Expertise France: | Expertise France Deputy Project Director, Charles Mathiaux Department of Economy and inclusive development 40, boulevard de Port Royal F-75005 PARIS |
| --- | --- |
| For the Contractor: | To be completed by the Contractor |

Each Party may modify its address at any time subject to notifying the other Party thereof in writing.

## Undertaking against deforestation

Within the framework of the policy to combat imported deforestation and in the hypothesis of the use of raw materials or processed products, the Contractor undertakes to evaluate precisely the quantities really necessary and to study alternatives to the products at risk listed below:

- Meat;

- Eggs;

- Dairy products;

- Ready-made meals, margarine, spreads;

- Leather shoes;

- Automotive upholstery;

- Household and cleaning products;

- Agrofuels;

- Lumber;

- Solid wood or particle;

- Fuels;

- Paper;

- Cardboard;

- Textiles;

- Coffee, chocolate;

- Exotic fruits;

- Electronics.

For more information, the guide Engaging in Zero Deforestation Public Procurement is available at the following email address: https://www.ecologie.gouv.fr/sites/default/files/Guide_politique_achat_public_zero_deforestation.pdf

- Re-examination clause

Under Article R.2194-1 et seq. of the Public Procurement Code, Expertise France may amend the provisions of the Contract subject to the following conditions:

- Revision of technical elements (clarification of deliverables, producer technical definitions, equipment technical documents, updated instructions, etc.)].

Such modifications shall be notified to the Contractor: by simple exchange of correspondence via the secure platform PLACE, or via any means defined by Expertise France guaranteeing full traceability of exchanges.

- Similar services

Under Article R.2122-7 of the French Public Procurement Code, the Contractor may be awarded a contract for similar services to those of the initial contract without advertising or competitive bidding.

- penalties

The amount of penalties will be applied within the calculation of the balance due under the relevant item or purchase order.

## Penalties for periodic documentary deliverables

By way of derogation from Article 14 of the CCAG, penalties are set at the fixed rate of €50 net per day of delay in the delivery of the periodic deliverables specified in Article 6 “Deliverables table” of the Contract.

## Penalties applicable to submission of final deliverables

By way of derogation from Article 14 of the CCAG, penalties are set at the fixed rate of €100 net per day of delay in the delivery of the final deliverables specified in Article 6 “Deliverables table” of the Contract.

- intellectual property

## Definitions

The Assignment provided for by this article requires definition of the following terms:

- “Result” means any intended outcome of the performance of the Contract which is delivered and definitively accepted by Expertise France;

- “Creator” means any natural person who contributed to the production of the result;

- “Pre-existing right” means any intellectual property right, including pre-existing technologies owned by Expertise France, the Contractor or any third party with a prior interest in the order to be executed under the Contract.

## Ownership of results

The ownership of results, and the title to related intellectual and industrial property rights, including the solutions and technical information they contain, are entirely and irrevocably transferred to Expertise France under the Contract. This Assignment only covers the economic rights of creators under the conditions set out in Article 8.3 of the Contract. The moral rights of creators are excluded. Such moral rights cover the disclosure, paternity and respect for the integrity of the results treated as a work within the meaning of the French Intellectual Property Code.

The aforementioned elements shall be deemed to be effectively transferred to Expertise France after acceptance of the results delivered to it by the Contractor.

The payment of the price to the Contractor is deemed to include any fees payable to the Contractor in relation to the acquisition of rights by Expertise France, notably all forms of exploitation of the results. The acquisition of such covers all territories worldwide.

## Exploitation of results

By acquiring title to the results developed by the Contractor, Expertise France becomes the holder of all economic copyright relating to such rights. In this regard, yet without the list being exhaustive, Expertise France may exploit the results for the following purposes:

- internal exploitation:

  - disclosure to its personnel;

  - communication disclosure to persons and entities working for Expertise France or cooperating with it, including contractors, subcontractors (whether legal or natural persons), EU institutions, agencies and bodies and member states' institutions;

  - installing, uploading, processing, arranging, compiling, combining, retrieving, copying, reproducing in whole or in part and in unlimited number of copies.

- distribution to the public:

  - in paper, electronic or digital format;

  - on the internet as a downloadable/non-downloadable file;

  - via display, radio or television broadcasting or any other transmission technique;

  - otherwise in any form and by any method.

- modifications:

  - modification of content, form or technique;

  - addition of new elements of content and form;

  - adaptation using new media;

  - translation into any language;

  - digitization and computer processing.

## Licensing of pre-existing rights

Expertise France shall not acquire ownership of pre-existing rights. The Contractor shall license the pre-existing rights on a royalty-free, non-exclusive and irrevocable basis to Expertise France, which may use the pre-existing rights as set out in Article 8.3. Such licenses shall become effective from the moment the results are delivered by the Contractor and accepted by Expertise France. On delivery of the results, the Contractor may, as required, provide Expertise France with a list of pre-existing rights and third parties' rights, including those of its personnel, of creators and of other right holders. The licensing of pre-existing rights to Expertise France under the Contract covers all territories worldwide and is valid for the whole duration of intellectual property rights protection.

## Guarantees

When delivering the results, the Contractor shall warrant that they are free of rights or claims from creators and third parties, including in relation to pre-existing rights, for any use envisaged by Expertise France.

On request from Expertise France, the Contractor shall provide evidence of ownership or rights to use all the listed pre-existing rights and rights of third parties, except for the rights owned by Expertise France.

## Image rights

If natural, recognizable persons appear in a result or their voice is recorded, on request from Expertise France the Contractor shall submit a declaration in which such persons (or of the persons exercising parental authority in case of minors) give their permission for the described use of their image or voice. This does not apply to persons whose permission is not required in line with the law of the country where photographs were taken, films shot or audio records made.

- Termination of the contract

## General terms of performance

The Contract is subject to the termination clauses as defined in Articles 29 to 36 of the CCAG.

By way of derogation from Article 40 of the CCAG PI, termination for reasons of general interest is not applicable to this contract. However, the parties agree on the possibility of terminating the contract by mutual consent.

In the event of early termination, the Contractor shall immediately return to Expertise France all documents it may have received for the purposes of execution of the Contract.

## Termination of the Contract due to the non-availability of a designated expert

In the event of the non-availability of a designated expert, the Contractor shall notify Expertise France thereof within 3 days and, within 14 days at the latest, propose the CV of a replacement expert of at least the same level or expertise. If these replacement conditions are not respected, Expertise France may terminate the Contract due to fault on the part of the Contractor.

Regardless of the circumstances, should an expert remain unavailable for a cumulative duration of 2 weeks without a satisfactory replacement having been found, Expertise France may automatically terminate the Contract.

Termination for the non-availability of a designated expert shall not establish any entitlement to any form of compensation for the Contractor.

## Procedure

Any termination decision shall be notified by Expertise France to the Contractor by registered letter with acknowledgement of receipt. It shall state the effective date of termination.

- safety and security measures and responsabilities

The Contractor is the only one who is responsible for the safety of the people and property that he mobilizes for the execution of the present Contract and in this respect, takes all necessary measures. He undertakes to ensure that all of his employees and subcontractors comply with the safety instructions that he issues.

In the event of an incident and/or direct or indirect attack on the safety of people directly or indirectly mobilised by the contractor or its equipment, Expertise France cannot be held responsible in any way whatsoever.

- ethics

The Contractor also undertakes to take note of the  Expertise France Code of Conduct and to comply strictly with it (the Expertise France code of conduct is available on the agency’s website: www.expertisefrance.fr).

Any breach to comply with the code of conduct may result in the termination of the Contract and incur the liability of the Contractor.

- Administration of personal data

Under Article 13 or Regulation (EU) no. 2016/679 of the European Parliament and of the Council of 27 April 2016 on the protection of natural persons with regard to the processing of personal data and on the free movement of such data (GDPR), the Contractor is notified that personal data (notably name, first name and e-mail address) collected under this contract may be processed.

The legal basis under which such processing is performed are set out in c) and e) of Article 6.1 of the GDPR, namely:

- The processing is necessary in order to comply with a legal obligation by which Expertise France is bound;

- The processing is necessary for performance of a public-interest assignment or which falls within the scope of the public authority entrusted to Expertise France.

The purposes of the processing are as follows:

- Management and monitoring of this Contract

- Management and monitoring of reports forwarded to donors and other supervisory authorities.

Recipients or category of recipients of the personal data are exclusively authorized personnel of Expertise France, ministries and state operators and donors responsible for awarding and executing this contract, including any service providers assisting them with their activities.

Retention period: the data will be held throughout the execution of the contract, including the DUA (duration of administrative usefulness) applicable to the contract.

Under Articles 15 to 21 of the GDPR, persons whose personal data is collected enjoy a right of access, rectification and deletion with regard to such data. They also enjoy the right to restrict and refuse processing on legitimate grounds. The information and other rights of data subjects may be exercised by contacting the Data Protection Officer of Expertise France (informatique.libertes@expertisefrance.fr).

Persons whose personal data is collected under this procedure may submit a complaint to CNIL.)]

The Contract may require the processing of personal data. The parties undertake to comply with regulations on the processing of personal data in accordance with amended law no. 78-17 of 6 January 1978 relating to data processing, files and liberties and regulation (EU) 2016/679, known as the General Data Protection Regulation (GDPR).

The Contractor notably undertakes to:

- Process personal data solely for the purposes of the Contract, as defined in annex hereto covering the collection of personal data (GDPR data processor);

- Ensure that persons authorized to process personal data undertake to maintain its confidentiality or are bound by an appropriate legal obligation of confidentiality;

- Implement appropriate technical and organizational measures to guarantee a level of security commensurate with the risks resulting from the Contract, notably with regard to data encryption, confidentiality and integrity;

- Notify Expertise France, via any means, of any personal data breach within 24 hours of becoming aware of any such event;

- Assist Expertise France in its obligation to respond to requests it may receive from data subjects;

- Delete all personal data or return it to Expertise France on conclusion of the services covered by the Contract, as specified by the latter, unless EU law or that of the member state requires such data to be retained;

- Make available to Expertise France all information it may require to demonstrate compliance with the obligations set out in this article and to enable audits to be conducted by the latter or by any other person of its choice.

Where the Contractor uses a data processor to process personal data during execution of the Contract, it must obtain prior written authorization from Expertise France. Similarly, the Contractor shall notify Expertise France of any planned change concerning the addition or replacement of processors, thereby enabling Expertise France to issue any objections it may have in this regard.

The same obligations concerning data protection as those set out in the Contract are mandatory for processors, notably regarding the provision of adequate guarantees for the implementation of appropriate technical and organizational measures ensuring the protection of personal data. Should any processor fail to meet its obligations, the Contractor shall remain fully responsible vis-à-vis Expertise France for the fulfillment of the processor’s obligations.

In the event of non-compliance with the aforementioned provisions, the Contractor is reminded that its liability may be invoked. In the event of any breach of professional secrecy or non-compliance with the aforementioned provisions, Expertise France may immediately terminate the Contract without compensation for the Contractor.

- Dispute resolution - applicable law

Any dispute between the Parties relating to the existence, validity, interpretation, execution, and termination of the Contract (or any of its clauses) that the Parties cannot resolve amicably within 30 days of the notification of the dispute by the requesting Party to the other Party, shall be submitted to the competent court.

The applicable law for this Contract is French law, to the exclusion of any other law.

- Derogation from the CCAG

The following articles of this document derogate from the CCAG-FCS:

- article 5 derogates from article 28 and 15 of the CCAG;

- article 9 derogates from article 14 of the CCAG

- AUDIT

The Contractor may be submitted to an audit concerning compliance with the regulations and contractual obligations applicable to the performance of the present Contract. This audit may be carried out by Expertise France or by a third party appointed by Expertise France and may not be refused by the Contractor. If the audit is carried out by a third party, the appointed third party must not be a direct competitor of the Contractor. Scheduled audits may be carried out periodically or spontaneously at the request of Expertise France or a third party. In all cases, the contractor will be informed at least 5 working days in advance.

The Contractor therefore undertakes to:

- Allow Expertise France or the appointed entity, and facilitate their access to the information required to carry out the audits, including interviews with the people involved and on-site visits;

- Submit documents relating to the performance of the present Contract as well as any documents required by the auditors;

- Demonstrate transparency and respond to auditors’ requests;

- Implement any corrective measures that may be necessary.

Expertise France will notify the Contractor of the identity of the audit structure selected in the case of an external firm, the purpose of the assignment, the planned duration of the assignment and the names of the experts assigned.

The Contractor also undertakes to allow Expertise France, or any other third party mandated by Expertise France, to carry out an investigation in the case of an allegation of a prohibited practice relating to the present Contract, under the conditions set out above.

The conclusions of the audit report will be sent to each of the Parties by any means deemed appropriate by Expertise France.

The conclusions may prescribe the implementation of actions and a deadline for completion.

Any refusal by the Contractor to comply with the audit exercises and/or their conclusions gives as of right to Expertise France the possibility to terminate the present contract without compensation.

- Final provisions

## Declaration

The Contractor, its affiliates, suppliers, service providers, consultants and subcontractors (including directors, employees and agents of such entities) hereby declares:

- that no natural or legal person on whose behalf the Contractor is acting is subject to the prohibitions set out in Articles L. 2141-1 to L. 2141-6 and L. 2141-7 to L. 2141-11 of the French Public Procurement Code or any equivalent prohibition issued in another country;

- that the commitments made by the Contractor within the scope of the Contract do not create a situation of conflict of interest that may affect the execution of the Contract;

- that the Contractor have not committed any act that may influence the process of Project implementation to the detriment of the Beneficiary, and notably that no Understanding has been, or will be, entered into;

- that the negotiation, award and execution of the Contract has not given rise to, nor will do so in the future, any act of corruption as defined in the United Nations Convention Against Corruption dated 31 October 2003;

- accepts that the Contract will be awarded in accordance with standard practices and in electronic format.

Furthermore,

The Contractor, its affiliates, suppliers, service providers, consultants and subcontractors (including directors, employees and agents of such entities) certify that:

- they do not acquire and don't supply/will not acquire or supply equipment and do not intervene/will not intervene in sectors under embargo by the United Nations, the European Union or France. For information, the list can be found at: https://www.sanctionsmap.eu ;

- they are not included in the lists of financial sanctions adopted by the United Nations, the European Union, France and/or the United States, notably in the fight against the financing of terrorism and against attacks on national peace and security. For information, the lists can be consulted at the references below:

- for the United Nations, the United Nations Security Council sanctions lists: https://www.un.org/securitycouncil/content/un-sc-consolidated-list;

- for the European Union, the lists can be consulted at the following address: https://www.sanctionsmap.eu;

- for France, see: https://gels-avoirs.dgtresor.gouv.fr/List;

- for the United States, see: https://home.treasury.gov/policy-issues/financial-sanctions/sanctions-programs-and-country-information;

- they are not subject to a World Bank exclusion order and are not on the list published by the World Bank. For information, the list can be consulted at the following address:

https://www.worldbank.org/en/projects-operations/procurement/debarred-firms

In the hypothesis of such a decision of exclusion, we can join to the present declaration on honor the additional information which would allow to consider that this decision of exclusion is not relevant within the framework of the market).

Finally, the Contractor, its affiliates, suppliers, contractors, consultants and subcontractors (including directors, employees and agents of such entities) acknowledge and accept that the above-mentioned situations may lead to the automatic termination of the contract.

They undertake to inform Expertise France without delay of any change in our situation during the execution of the contract with regard to the present declaration.

FOR THE CONTRACTOR:

In ...……....., on...…….....20....

Preceded by the handwritten words “Read and approved":

Signature:

Name: 
First name:

Role:

FOR EXPERTISE FRANCE:

This offer is accepted as an undertaking.

In Paris, on...…….....2026

Signature:

Name: 
First name:

Role:

Done in one original copy retained by Expertise France.

# Annex I – Terms of referenses

TERMS OF REFERENCE AND TECHNICAL SPECIFICATIONS

Research Firm to Undertake a Mid-Term Evaluation of the Project

- General information

| # Assignment name | Provision of Mid-Term evaluation services for the EU4Innovation East project |
| --- | --- |
| # Beneficiary | Expertise France – EU4Innovation East project |
| # Country | Armenia, Azerbaijan, Georgia, the Republic of Moldova and Ukraine |
| # Duration | 5 months |

- Context and justification of the need

EU4Innovation East is a regional project enhancing the competitiveness of the startup ecosystems in five Eastern Partnership (EaP) countries: Armenia, Azerbaijan, Georgia, the Republic of Moldova and Ukraine. At its core is a comprehensive strategy to foster high-performance incubators, expand funding and market opportunities, strengthen community ties and amplify the visibility of EaP startups. Through strategic co-financing, capacity building, regulatory support, and a commitment to gender equality, EU4Innovation East promotes an inclusive and sustainable innovation landscape. By amplifying regional achievements and deepening cross-border connections, the project lays the groundwork for impactful growth.

The EU4Innovation East project is funded by the European Union, co-funded by the French government and implemented by Expertise France.

| Title: | EU4Innovation East – Support to Digital innovation in the Eastern Partnership region |
| --- | --- |
| Geographic scope: | Armenia, Azerbaijan, Georgia, the Republic of Moldova and Ukraine |
| Duration: | 54 months, i.e. 4.5 years (04/2024 - 10/2028) |
| Financed by: | • EU Commission: 21.000.000,00€ • France: 2.120.000,00€, earmarked for Ukraine |
| Implementing Agency: | Expertise France (EF) |
| Overall objective: | Contribute to strengthen the competitiveness and maturity of the private sector in innovation in EaP countries through valuable collaborations with European partners |
| Pillars’ description: | Pillar 1 – Supporting early-stage funding Pillar 2 - Backing high added-value segments and high-performance incubation Pillar 3 - Strengthening community ties Pillar 4 – Promoting EaP startups and advancing the development of EU partnerships Pillar 5 - WiFi4MD: Public Digital Infrastructure for Inclusive Innovation Ecosystems in Moldova |

Justification of the need - EU4Innovation East is a regional project aiming to strengthen the competitiveness and maturity of the EaP startup ecosystem. An independent mid-term evaluation is therefore essential to generate evidence that will inform and strengthen the project's implementation going forward. In accordance with the Monitoring, Evaluation, Accountability and Learning (MEAL) plan and Description of Action (DoA), Expertise France MEAL procedure, the project is required to carry out an independent mid-term evaluation.

This evaluation is a milestone to ensure the project's accountability to the funder (European Union) and the Ministry for Europe and Foreign Affairs of France, Ministry of Economics, Finance and Industrial and Digital Sovereignty of France, the implementing agency (Expertise France), and the project beneficiaries.

The primary users of this mid-term evaluation are the European Union, as the principal funder of EU4Innovation East, which will use the findings to assess the project's accountability, value for money, and progress towards delivering the expected results and impact, and to inform future funding decisions and regional programming priorities. Expertise France, as the primary implementing agency, will use the evaluation findings to assess overall project performance, inform adaptive management decisions, and strengthen implementation strategies for the remainder of the project period. The project management team will similarly draw on the findings and recommendations to refine operational strategies, address implementation bottlenecks, and enhance the quality and effectiveness of project activities for the remaining project period. Finally, partners engaged in the project will use the evaluation to strengthen coordination, align strategies, and enhance their contribution to the project's objectives.

Scope of the evaluation- the midterm evaluation covers all activities since the start of the project in April 2024 in Armenia, Azerbaijan, Georgia, Moldova and Ukraine. The evaluation will assess the relevance, coherence, effectiveness, efficiency, and potential impact of the project across its four core pillars: support to early-stage funding creation; backing of added-value segments and high-performance incubation; support to community initiatives and legal alignment; and international promotion of Eastern Partnership (EaP) startups and the development of EU partnerships. End beneficiaries are government institutional partners, startup support organizations and startups and young entrepreneurs.

The project aims to achieve the following results:

| Component | Specific objectives |
| --- | --- |
| Pillar 1 – Supporting early-stage funding | Specific Objective 1: Startups in the East Neighborhood have greater access to local funding in the pre-seed stage (fundraising, vouchers, etc.), including startups founded or co-founded by women |
| Pillar 2 - Backing high added-value segments and high-performance incubation |  |
| Pillar 3 - Strengthening community ties | Specific Objective 2: The EaP ecosystems are structured and strengthened, creating a business environment more conducive to innovation development |
| Pillar 4 – Promoting EaP startups and advancing the development of EU partnerships | Specific Objective 3: The EaP ecosystems are connected with European investors, generating foreign investments for startups |
| Cofi FR Specific support from France for the reconstruction of Ukraine | Specific Objective 4: Ukrainian startup ecosystem improves its support to local startups |
| Pillar 5 - WiFi4MD: Public Digital Infrastructure for Inclusive Innovation Ecosystems in Moldova | Specific Objective 5: Improved access to free, reliable public internet services in Moldovan cities, contributing to digital inclusion and territorial cohesion |

The evaluation should take into account several cross-cutting principles: Gender in accordance with the Expertise France Gender Strategy and project’s Gender Strategy and by positioning gender as a cross-cutting area throughout the evaluation. Integrating a consolidated gender approach and measures across all stages of the evaluation process: methodological approach (sampling, evaluation questions), data collection (always disaggregated by sex and age as far as possible), analysis of data (always disaggregated by sex and age as far as possible, integration of gender dynamics in contextual analyses), recommendations taking into account gender-related experiences, etc.  In the context of Ukraine, the evaluation will additionally capture information on vulnerable groups, including veterans and war-affected populations. The evaluation will adopt a participatory approach, actively engaging key stakeholders- through interviews, focus group discussions, and validation workshops at key stages of the evaluation process. Ethics: the evaluation must comply with the principles and commitments of the Expertise France Ethics Charter. The evaluation will assess the project's contribution to promotion of environmental sustainability with particular attention to the project's support to startups in GreenTech vertical.

3.	Objectives

3.1. General objective

The overall objective of this evaluation is to improve current and future project interventions. In order to achieve this, a mid-term report will be drawn up with the following specific objectives:

3.2. Specific objectives

- Produce a comprehensive and independent analysis of the performance of the project, with particular attention to its intermediate results, in comparison to the objectives initially set; and its trajectory towards achieving its intended impact

- Learning. Identify lessons learned and best practices to inform adaptive management for the remainder of the project, and to support the scale-up and replication of successful approaches in other Expertise France interventions. In doing so, the evaluation shall produce a knowledge product capturing EU4Innovation East's contribution to advancing startup ecosystems across Eastern Partnership (EaP) countries, demonstrating value for money for the European Union.

- Provide recommendations for improving implementation- including adjustments to indicators, targets, and the Theory of Change- understanding that the project team and stakeholders will use the findings to enhance decision-making and refine strategies

3.3 Evaluation criteria and questions

The evaluation will use the criteria set out by the Organization for Economic Co-operation and Development (OECD) Development Assistance Committee (DAC) in its publication Better Criteria for Better Evaluation – Definitions and Principles for Use. They should be reviewed by the evaluator during the inception phase of the evaluation, in order to propose a final version in the inception report.

| Evaluation criteria | General evaluation questions | Examples of specific evaluation questions |
| --- | --- | --- |
| Relevance and coherence | To what extent does the project address the needs and constraints of the targeted actors? To what extent is the project internally coherent? To what extent is the project coherent with other initiatives in the sector/region? | - To what extent does the project address the innovation and startup ecosystem challenges identified in the Country Diagnostics? - To what extent does the project remain relevant to the current priorities and agendas of ecosystem players — including government agencies, innovation bodies, startup support organizations, and private sector actors — across the five target countries? |
| Effectiveness | Is the intervention achieving its objectives? | - Are startups gaining better access to local funding in pre-seed and seed stage? - Are the EaP ecosystems starting to be more structured and strengthened? - Is there evidence of an improved connection between EaP ecosystems and European funders? Are startups attracting foreign investments? - Is there evidence Ukrainian startup ecosystem improving its support to local startups? |
| Efficiency | Are resources being used in an optimal way? | - How is budget allocated to reach outputs? - To what extent have project inputs — including grant tranches, technical expertise, man/days, services— been converted into outputs? - What is the EU leverage ratio — to what extent has EU funding catalyzed additional sponsorships and / or co-financing contracts, and what results have these generated? |
| Orientation towards impact | What difference the intervention is expected to make and how? | - What are the areas of causal impact? - What are the top-level effects of the project on government actors, private sector, startup support organizations, youth, academia and startups? - What are the lessons learned and good practices of the project at the midpoint? - What are the long-term changes that the project is expected to produce if it stays on this trajectory? |
| Cross-cutting | -Gender equality -Green Innovation -Communication and visibility | - To what extent are gender and green innovation considered in project activities, particularly in the selection of startups for support? - To what extent the project ensures compliance with EU visibility and communication requirements across its outputs, events, and communications materials - How effectively the project communicates its results and EU funding contribution to relevant stakeholders |

4. Description of the assignment

Governance and the collaboration process- consultants are expected to work in close collaboration with EF (including with the Project Manager and the MEAL Manager) and to collaborate with the ad hoc Evaluation Committee set up for this mid-term evaluation.

4.1. Evaluation methodology

The evaluator shall design and implement a mixed-methods methodology integrating both qualitative and quantitative approaches, with data triangulation applied throughout to ensure the validity, reliability, and credibility of findings. While the evaluator retains flexibility in the design of the methodology, the following approaches are required and shall be explicitly incorporated in the methodology:

i. Contribution Analysis The evaluation shall apply a contribution analysis approach to build a credible, evidence-based contribution pathway on mid-term. The analysis will trace the causal chain from project activities to outputs and to early outcomes, test the validity of the Theory of Change assumptions, and identify enabling and constraining factors. Findings will directly inform recommendations and strengthening the project's pathways to impact for the remainder of the project period.

ii. Qualitative Approach — Key Informant Interviews The evaluation shall conduct in-depth Key Informant Interviews (KIIs) with a representative and purposively selected range of stakeholders, including the project management team, Expertise France, European Union representatives, government agencies, national innovation bodies, partner organizations, startup support organisations, and direct project beneficiaries across the three target countries. KIIs shall be complemented by focus group discussions where appropriate, and all data shall be disaggregated by sex, age, and country.

iii. Qualitative — Success Case Method (SCM) The evaluation shall identify and document a number of success cases across the project's supported startups and startup support organizations in Armenia, Moldova, and Ukraine, examining the conditions and project interventions that enabled them. This will be done in the form of Survey or Focus Group Discussions.

iv. Quantitative Approach — Quasi-Experimental Design The evaluation shall design and apply an impact measurement framework for the Pillar 1 funding mechanism, using a quasi-experimental design to assess its effectiveness and causal contribution to startup development. The framework shall compare characteristics and outcomes between startups selected for funding and those that applied but were not selected, controlling for selection bias where possible. Sample testing shall be drawn from Pillar 1 funding mechanism applications across the three target countries.

v. Knowledge Product for Learning The evaluation shall produce a knowledge product capturing EU4Innovation East's contribution to advancing startup ecosystems across Eastern Partnership (EaP) countries. The knowledge product shall synthesize key findings, good practices, and lessons learned in an accessible and visually engaging format, suitable for dissemination to a broad audience including development practitioners, policymakers, donors, and the wider innovation community. The knowledge product shall demonstrate the project's value for money for the European Union and its potential for scale-up and replication in other Expertise France interventions.

4.2. Planned activities

The evaluation process will be implemented through the following phases in 2026:

| Evaluation Phases | Implementation period |
| --- | --- |
| - Inception phase - Inception Report (evaluation matrix, methodology, work plan, desk review, preliminary interviews with project team, data collection plan) | Month 1 from T0 |
| - Primary data collection phase- field missions (conduct interviews, carry out surveys, transmit datasets to the project, interim report) | Month 2 from T0 |
| - Data analysis and reporting phase- draft Evaluation Report (data analysis, findings and preliminary recommendations) +Knowledge Product | Month 3 from T0 |
| - Final reporting phase -validation Workshop / Presentation of Findings | Month 4 from T0 |
| - Final reporting phase -final Evaluation Report with integrated feedback | Month 4 from T0 |

1. Inception phase

The inception phase will include:

  - An online kick-off meeting with the Project Management Unit (PMU) and the evaluator. The purpose of the meeting is to come to a clear and shared understanding of the evaluation. The identified limitations will be discussed, and mitigation measures will be set out. Finally, the evaluation plan and process will be presented and approved. Initial interviews will be conducted if deemed necessary by PMU.

  - A desk research report, for which EU4IE will share the following data:

  - Description of Action (DoA)

  - Annual progress reports

  - Country diagnostics and action plans

  - Project monitoring data (Planning, monitoring and reporting tool)

  - Learning data

  - MEAL Strategy

  - Knowledge Management (KM) Strategy

  - Other relevant document (regulatory reviews, studies, etc.)

Based on the information collected and initial interviews conducted (first exchange with the team), an inception report will be drafted and submitted to Expertise France for validation.

2. Primary data collection phase (face-to-face in the implementing countries and online):

- The lead evaluator shall conduct in-country missions to Armenia, Moldova, and Ukraine to meet stakeholders in person, and carry out key informant interviews. Each in-country mission shall be carried out with a country-based subject matter expert-national evaluator, to ensure contextual depth and local knowledge.

- The qualitative and quantitative collection methods designed by the evaluator to be used with all project beneficiaries

- Interim report and an interim meeting between the evaluation team and the evaluation steering group

3. Analysis and reporting phase

The analysis and reporting phase will include:

- Data analysis by triangulating primary, secondary, quantitative and qualitative data. Analysis should be disaggregated by sex, and if possible, by age, vulnerability status, vertical of startup;

- The analytical framework used;

- The evaluator to write the draft report before participating in the validation workshop. Draft report to be submitted to Expertise France for review, and quality assessment in accordance with an evaluation grid. Particular attention will be paid to the objectivity, balance and detail of any assertions made and their evidence base, as well how operational and tangible the recommendations are. The evaluation grid will be discussed with the evaluator to decide if any improvements are necessary. Produce knowledge product.

- Evaluation to conduct three validation workshops (one per country) online

4. Final reporting phase

Evaluator to incorporate feedback and produce the final report taking into account information from the validation workshops.

4.3. Anticipated deliverables and descriptions

| Evaluation Phases and Deliverables | Implementation period | Deadline for the deliverable |
| --- | --- | --- |
| D1 – Inception Report (desk review, preliminary interviews with project team, evaluation matrix, methodology, data collection plan, workplan) | Month 1 from T0 | Within ten (10) working days after one (1) month from T0 |
| D2 – Primary Data Collection and field missions report (conduct interviews, carry out surveys, transmit datasets to the project, interim report) | Month 2 from T0 | Within fourteen (14) working days after two (2) months from T0 |
| D3 – Draft Evaluation Report (data analysis, findings and preliminary recommendations) +Knowledge Product | Month 3 from T0 | Within twenty (20) working days after three (3) months from T0 |
| D4 – Validation Workshop report / Presentation of Findings | Month 4 from T0 | Within three (3) working days after the validation of the draft report |
| D5 – Final Evaluation Report with integrated feedback | Month 4 from T0 | Within three (3) working days after four (4) months from T0 |

| Deliverables | Main content | # pages max. |
| --- | --- | --- |
| Deliverable #1 – Inception report | - Preliminary Document Review — a summary of key findings from the desk review of project documents, highlighting issues and questions to explore during the evaluation - Preliminary interviews with project team - Evaluation Matrix —a refined evaluation framework with a selection, prioritization, reformulation of evaluative questions, ensuring full coverage of the evaluation's objectives and the OECD/DAC criteria (relevance, coherence, effectiveness, efficiency, and orientation towards impact) - Methodology — a detailed description of the evaluation methodology, including the mix of quantitative and qualitative methods, the rationale for their selection, the proposed sampling approach, and a transparent identification and discussion of the anticipated limitations of the evaluation - Data Collection Plan — the overall data collection strategy, the final tools to be used during the evaluation (interview guides, focus group discussion guides, survey questionnaires, and observation checklists, developed in line with the evaluation matrix and cross-cutting principles), and the proposed list of people and organizations to interview - Work Plan — a finalized work plan presenting all tasks, a clear description of each evaluation team member's roles, including the lead evaluator milestones, deliverables, and timelines from inception to final report, including planned data collection missions across Armenia, Moldova, and Ukraine | 15 pages + annexes |
| Deliverable #2 - Primary Data Collection and field missions | - Raw Primary Data — all quantitative and qualitative primary data collected during the evaluation, submitted to the project in raw, unprocessed format - Cleaned and Processed Data — all quantitative and qualitative primary data cleaned, organized, and processed, submitted to the project in a structured format - Field Visit Notes — written records of observations, key points, and insights from each field visit and data collection mission - Interim report (in the lighter format of a slideshow) - is submitted at the end of the data collection phase to summarize the findings gathered using each of the data collection tools deployed by the evaluation team. The document will serve as the basis for an interim meeting between the evaluation team and the evaluation steering group aiming at sharing a common understanding of the collected data; jointly sketching the main lines of the cross-analysis; identifying gaps in data collection that may require additional remote follow-up. |  |
| Deliverable #3 - Draft Evaluation Report (V1) +Knowledge Product | - Draft evaluation report shall include: - Executive Summary — a concise two-page summary of the evaluation's conclusions and recommendations, written for a non-technical audience - Methodology Overview — a transparent account of the evaluation methodology as implemented - Answers to the Evaluation Questions - Good Practices and Lessons Learned — including the Knowledge Product - Recommendations | 40 pages + annexes |
| Deliverable # 4 Three Validation workshops to Stakeholders (online) in Armenia, Moldova and Ukraine | During the workshops, EF will challenge the preliminary conclusions—ensuring they are sufficiently supported by evidence and identifying any analytical gaps. The evaluators' wording will be refined to reach a collectively agreed formulation of the final conclusions, after which the recommendations will be co-developed. The PowerPoint Presentation shall include: - Preliminary conclusions - Good Practices and Lessons Learned — including the Knowledge Product - Summary of the Work — an overview of the evaluation work carried out - Summary of Interviews — a consolidated account of the interviews conducted - Data Reliability and Scope Analysis — an assessment of the reliability and scope of the data collected - Recommendations |  |
| Deliverable # 5 Final Evaluation Report (V2) | - Finalized Report — all sections from the Draft Report (V1), revised and finalized based on comments from stakeholders, the EU, and Expertise France - Updated PowerPoint Presentation - Comments and Revisions Matrix — documenting all comments received, how each was addressed and integrated, and a clear justification where a comment was not incorporated |  |

4.4. Coordination

EU4IE MEAL manager will be the service provider’s contact person for Expertise France.

5.Place, duration and terms of performance

- Start and end dates: The duration of the assignment is 4 months from the contract notification date (T0).

- Schedule/program:

The evaluation process will take place from September to December 2026, in line with the indicative schedule below.

| Activity | Place | Period (indicative) | Duration (man/days) |
| --- | --- | --- | --- |
| Deliverable 1 Inception report | Online | Month 1 from T0 | 10 |
| Deliverable 2 Primary Data Collection and field missions report | Online | Month 2 from T0 | 14 (including 10 days for field missions) |
| Deliverable 3 Draft Evaluation Report (V1) +Knowledge Product | Online/Offline | Month 3 from T0 | 20 |
| Deliverable 4 Validation workshops (3x) | Online | Month 4 from T0 | 3 |
| Deliverable 5 Final Evaluation Report (V2) | Online | Month 4 from T0 | 3 |
|  |  |  | TOTAL: 50 (man/days) |

- Qualifications and experience

The contracted firm should have a proven history in successfully providing similar services, as following:

6.1 Organizational Capacity

- Be a legally registered research, consulting, or evaluation firm with a demonstrated experience conducting evaluations, evidenced by a portfolio of completed evaluation assignments;

- Demonstrate financial and operational capacity to manage and deliver a regional, multi-country evaluation assignment;

- Have experience working with European Union-funded projects and familiarity with EU reporting and OECD/DAC evaluation standards.

6.2 Technical Expertise

- Demonstrated experience in conducting evaluations of development projects, preferably in the areas of innovation, entrepreneurship, or private sector development

- Experience in learning — demonstrated experience designing and facilitating learning processes within evaluations (e.g. lessons learned, knowledge products, learning workshops)

- Strong knowledge of Theory of Change, results-based management frameworks, and evaluation methodologies including both qualitative and quantitative approaches

- Familiarity with startup ecosystems, innovation policy, and private sector development in Eastern Partnership (EaP) countries, as well as relevant EU policies and programmes related to innovation, will be a distinct advantage

6.3 Geographic Experience

- Proven experience conducting multi-country evaluations

- Demonstrated ability to manage multi-country data collection, including remote and in-person methods

6.4 Team Composition

The firm must propose a qualified evaluation team comprising at minimum:

Team Leader/Lead Evaluator — Advanced degree (Masters or PhD) in evaluation, social sciences, development studies, economics, or a related field, with a minimum of 10 years of relevant experience in project evaluation.

National Subject Matter Experts for each country — Minimum of 5 years of experience in data collection, SMEs/startups’ analytics. In-depth knowledge of the Eastern Partnership region, its innovation landscape, and startup ecosystems with a knowledge of languages spoken in the region (Armenian, Romanian and Ukrainian)

6.5 Independence and Impartiality

The research firm and its proposed team members must be independent and have no prior or existing relationship with EU4Innovation East project.

# Annex II – Technical And financial offer

Prohibited practices as defined by the Agence Française de Développement group are defined below: https://www.afd.fr/en/ressources/afd-groups-policy-prevent-and-combat-prohibited-practices-2020

The questionnaire should be elaborated by the evaluator

Based on the assessment of the security situation