TERMS OF REFERENCE AND TECHNICAL SPECIFICATIONS

EU4Innovation East – Technical Assistance for ecosystem strategy and data monitoring in Moldova

- General information

| # Assignment name | Support the development and implementation of a coordinated strategy and establishment of ecosystem-wide data monitoring system |
| --- | --- |
| # Beneficiary | Expertise France – EU4Innovation East project |
| # Country | Republic of Moldova |
| # Assignment Duration | 4 Months |

- Context and justification of the need

The EU4Innovation East is a regional project aiming at enhancing the competitiveness of the startup ecosystem within 5 countries of the Eastern Partnership (EaP): Armenia, Azerbaijan, Georgia, the Republic of Moldova and Ukraine. EU4Innovation East focuses on strengthening the performance of the local ecosystems to provide support to startups, improving access to funding and markets, and delivering targeted support to Ukraine’s tech ecosystem. The initiative combines co-financing, skills training, regulatory guidance, and gender-inclusive measures to promote long-term, sustainable innovation across the region.

The EU4Innovation East project is funded by the European Union, co-funded by the French government and implemented by Expertise France.

| Title: | Initiative “EU4Innovation East” – Support to Digital Innovation in the Eastern Partnership region |
| --- | --- |
| Geographic scope: | Multi-country Eastern Partner: Armenia, Azerbaijan, Georgia, Republic of Moldova and Ukraine |
| Duration: | • Duration: 54 months, i.e. 4.5 years (04/2024 - 10/2028) |
| Financed by: | • EU Commission: 20.000.000,00€ • France: 2.120.000,00€, earmarked for Ukraine |
| Implementing Agency: | Expertise France (EF) |
| Overall objective: | Strengthen the competitiveness and maturity of the EaP startup ecosystem |
| Specific Objectives: | SO1: Enhance early-stage funding access for EaP startups, especially those led or co-founded by women, by creating a new funding mechanism and improving incubation programs, including technology transfer initiatives. SO2: Foster innovation development in EaP ecosystems by structuring and improving the business environment. SO3: Amplify the visibility of EaP startups and strengthen connections with European investors, fostering both funding acquisition, market access, and increased local interest in the entrepreneurial journey. |
| Pillars description: | Pillar 1 - Early-stage funding Pillar 2 - Backing high added-value segments and high-performance incubation Pillar 3 - Strengthening Community ties Pillar 4 - International Spotlight for EaP Startups Integrating European emblematic events |

Local context

Moldova’s entrepreneurial and innovation ecosystem has expanded in recent years, reflecting growing interest among founders and a gradual shift toward knowledge-based economic activity. Public authorities, development partners, and private-sector actors have introduced various support measures—innovation grants, incubation and acceleration initiatives, and regulatory improvements aimed at encouraging startup creation. According to Startup Moldova’s annual report, startup investment reached USD 7.9 million in 2024—twice the 2023 level—and is projected to double again in 2025.

Despite this progress, the ecosystem remains fragmented, insufficiently coordinated and functioning at suboptimal efficiency. Numerous actors—including startup support organisations, universities, innovation centres, donor-funded programmes, private associations, and public agencies—operate without a shared vision and strategic framework. Their efforts, while valuable individually, do not collectively form a coherent or mutually reinforcing system. As a result, support services vary in quality, overlaps and gaps persist, and the ecosystem struggles to provide consistent pathways for founders as they grow and scale their ventures.

One of the structural challenges is the absence of a unified national vision or roadmap for startup ecosystem development. Without a coordinated strategy, interventions tend to be short-term, project-driven, and focused on isolated components rather than systemic needs. Startup support organisations lack a common reference framework for service design and performance standards. At the same time, donor programmes increasingly target innovation and entrepreneurship, yet operate with limited alignment, which reduces opportunities for complementarity, long-term sustainability, and scaling of what works.

Another constraint is the limited availability of reliable, structured, and publicly accessible data on startup activity, support services, investment flows, and ecosystem performance. Existing datasets are scattered across institutions, vary in quality, and lack standardisation or alignment with European indicators. This constrains data-driven policymaking, donor coordination, and the ability to track ecosystem evolution over time. Startup Moldova has begun to curate foundational datasets; however, these remain underutilised and require methodological strengthening and enhanced visibility.

This assignment seeks to address these gaps by supporting the development and implementation of a coordinated strategy for ecosystem development and an ecosystem-wide data monitoring framework.

The selected team will engage stakeholders through a participatory co-design process to gather insights, validate priorities, and ensure broad ownership; however, the consultants themselves remain fully responsible for drafting the complete Startup Ecosystem Development Strategy, ensuring it reflects shared priorities, ensures interoperability, and aligns with international best practices.

Also, by analysing existing datasets—particularly those curated by Startup Moldova—the team will generate a baseline report and develop dashboards that visualize ecosystem current status, trends, gaps, and opportunities. These dashboards will be integrated into the Startup Moldova website to enhance local and international visibility and accessibility of the ecosystem data. Among other areas, the consultants will assess the long-term viability of showcasing ecosystem data on an international dashboard and will propose funding options to support such an initiative.

Beyond technical outputs, the assignment aims to foster a culture of collaboration and transparent, well-structured data management across the ecosystem. It will establish mechanisms for continuous data collection and reporting, strengthen institutional capacity to use data for decision-making, and facilitate donor coordination around shared metrics and strategic priorities. Ultimately, these efforts will help build a more transparent, resilient, and internationally credible innovation ecosystem in Moldova.

- Objectives of the assignment

This Terms of Reference (ToR) outlines a consulting assignment aimed at strengthening strategic coordination and establishing robust data governance across Moldova’s startup and innovation ecosystem.

3.1. General objective

The general objective of this assignment is to strengthen Moldova’s startup and innovation ecosystem by developing a comprehensive Startup Ecosystem Development Strategy, underpinned by a strategic framework that aligns stakeholders around shared priorities, and by establishing an ecosystem-wide data monitoring system. Together, these components will provide a unified roadmap for ecosystem development, improve the availability and transparency of data, and enable more coherent, effective, and well-coordinated policies and donor interventions.

3.2. Specific objectives

(A) Develop a Startup Ecosystem Development Strategy

- Co-design a unified strategic framework that articulates a shared vision for ecosystem development and establishes priority areas for intervention.

- Engage public institutions, startup support organisations (SSOs), private actors, and donors to ensure that the strategy captures common priorities and supports coordinated action.

- Analyse the current structure and performance of the ecosystem, identifying systemic gaps, overlaps, and opportunities for improvement.

- Develop a roadmap of actionable steps to strengthen support services, improve coordination, and align ecosystem development with European and international best practices.

- Assess long-term options for showcasing ecosystem data internationally, including feasibility, sustainability, and potential funding mechanisms.

(B) Create an Ecosystem-Wide Data Monitoring Framework

- Conduct an AS-IS assessment of existing datasets, data owners, indicators, and methodologies—particularly those curated by Startup Moldova.

- Generate a reference data report capturing current ecosystem performance and identifying gaps in data quality, coverage, and standardisation.

- Develop interactive dashboards that visualise ecosystem trends, gaps, and opportunities; integrate these dashboards into the Startup Moldova website.

- Design a long-term data governance model that defines processes, roles, quality assurance mechanisms, and update cycles.

- Align the proposed framework with EU and international methodologies (e.g., European Innovation Scoreboard, Startup Nations Standard, DESI).

- Facilitate donor coordination around shared metrics and harmonised reporting standards.

- Description of the assignment

The assignment will support the development of a coordinated strategy and the establishment of a sustainable, ecosystem-wide data monitoring system for Moldova’s tech and startup landscape. It includes stakeholder consultations, strategy drafting, analysis of existing datasets (notably from Startup Moldova), and the creation of dashboards and visual tools. The work is supposed to enhance coordination among ecosystem actors and donors, improve data governance, and enable evidence-based decision-making.

While the resulting Startup Ecosystem Development Strategy will be developed in close consultation with government institutions and aligned with national priorities for economic competitiveness, it is conceived as a sector-driven, bottom-up document rather than an official policy instrument. Its purpose is to provide a coordinated vision, guide stakeholder action, and support donor alignment, without requiring formal governmental adoption.

  - Description of Services

The assignment aims to support the coordinated development of Moldova’s startup and innovation ecosystem by producing two core, interlinked deliverables:
(1) Startup Ecosystem Development Strategy, and
(2) an ecosystem-wide Data Monitoring Framework supported by baseline analysis and integrated dashboards.

The selected organisation will propose an appropriate methodological approach and work plan to achieve the objectives of the assignment. While the consultant is expected to outline clear stages of work, the sequencing and structure of these stages may differ from the illustration below and should reflect best practices in strategic ecosystem development, participatory design, and data governance.

The work will include, but not be limited to, the following areas of service:

1. Update Ecosystem Diagnostic and Strategic Foundations

- Conduct an assessment of Moldova’s startup and innovation ecosystem, examining actors, services, governance, regulatory frameworks, talent pipelines, funding mechanisms, infrastructure, and other elements.

- Build on the ecosystem mapping conducted by the EU4Innovation East project at the end of 2024 (to be provided), updating and refining it as needed. The consultant may propose an alternative structure or analytical model if it provides clearer insights or improved alignment with international standards.

- Engage a broad range of stakeholders—including startup support organisations, public institutions, founders, investors, academia, and development partners—to identify shared priorities, systemic bottlenecks, and opportunities for coordinated actions.

- Develop a strategic framework or conceptual structure to guide the formulation of the Startup Ecosystem Development Strategy.

2. Drafting of the Startup Ecosystem Development Strategy

- Elaborate a strategic document that articulates a shared vision for ecosystem development, identifies priority areas for intervention, and proposes a coordinated approach across public and private stakeholders.

- Define recommended actions, governance arrangements, institutional roles, and areas where donor support could be aligned or consolidated.

- Provide a practical roadmap for implementation, including short-, medium-, and long-term measures, sequencing considerations, and potential risks or enabling factors.

- Assess the long-term feasibility of presenting Moldova’s ecosystem data on an international-facing dashboard or platform, and outline potential sustainability and funding options.

3. Development of the Ecosystem-Wide Data Monitoring Framework

- Conduct an AS-IS assessment of ecosystem data availability, data owners, methodologies, and quality—including datasets curated by Startup Moldova.

- Produce a baseline data report that consolidates available indicators and visualises ecosystem trends, gaps, and opportunities.

- Design a Data Monitoring Framework aligned with EU and international methodologies (e.g., European Innovation Scoreboard, Startup Nations Standard, DESI).

- Propose a data governance model detailing roles, responsibilities, processes for data collection and updates, and quality assurance mechanisms.

- Develop data dashboards visualising key indicators and prepare them for integration into the Startup Moldova website, enhancing visibility and accessibility for national and international stakeholders.

- Dashboards should be modular and allow for different user profiles (e.g., startups, investors, donors, policymakers).

- Consultants are encouraged to incorporate gender-disaggregated and sustainability-related indicators where feasible.

4. Validation, Capacity Strengthening, and Stakeholder Alignment

- Facilitate workshops and consultation sessions to validate the Strategy, Data Framework, and dashboards.

- Build the capacity of Startup Moldova and other relevant institutions to maintain, update, and communicate ecosystem data over time.

- Support coordination with development partners to foster alignment around shared metrics, data standards, and strategic priorities.

- Provide final consolidated documentation summarising methodologies, findings, validated recommendations, and proposed next steps for implementation.

- Provide recommendations on mechanisms and incentives to motivate data subjects—particularly startup founders/managers—to share relevant information, increasing participation and ensuring long-term sustainability of the data system.

  - Anticipated deliverables

Indicative Length and Format of Deliverables
To ensure clarity, usability, and efficiency, the contracting authority encourages concise and action-oriented deliverables. Unless otherwise agreed, reports should generally not exceed 10–20 pages (excluding annexes), with key findings presented visually where appropriate. The consultant is welcome to propose either Narrative or Presentation formats where suitable, provided the content remains clear, complete, and aligned with the requirements of each deliverable. All written outputs shall be submitted in English and delivered in both PDF and editable formats. Dashboards must be provided in a web-ready digital format compatible with the Startup Moldova platform.

| Deliverable | Description | Indicative Timeline |
| --- | --- | --- |
| 1. Inception Report | Refined work plan and methodology, stakeholder engagement plan, confirmation of analytical structure for strategy and data framework. | Week 1–2 |
| 2. Updated Ecosystem Mapping & Diagnostic Report | Updated ecosystem mapping and diagnostic covering actors, services, governance, policy, funding, infrastructure, and talent. | Week 2–4 |
| 3. AS-IS Data Assessment & Baseline Report | Review of existing datasets (from Startup Moldova), data gaps, data quality assessment, and consolidated baseline indicators with initial visualisations. | Week 4–6 |
| 4. Draft Startup Ecosystem Development Strategy | Vision, priority areas, coordination mechanisms, implementation roadmap; aligned with government competitiveness priorities but not an official policy document. | Week 6–8 |
| 5. Draft Ecosystem Data Monitoring Framework | Indicator set aligned with EU/international methodologies; data governance model; update cycles; quality assurance; recommendations on motivating startups to share data with Startup Moldova. | Week 8–10 |
| 6. Prototype Dashboards | Visualisation of ecosystem indicators; prepared for integration into the Startup Moldova website. | Week 10–12 |
| 7. Final Ecosystem Package (merged final output) | Validation summary; Final Strategy; Final Data Monitoring Framework; Final Dashboards; Final Integrated Report with findings and recommendations. | Week 12–16 |

Note: The assignment is expected to require approximately 60–80 man-days. This estimate is provided to guide bidders in calibrating the scope and intensity of their proposed methodology.

  - Coordination

The selected consultants will work in close coordination with EU4Innovation East and collaborate with Startup Moldova, Dreamups, XY, YEP! MITP and other ecosystem organisations. They will make sure to include the Ministry of Economic Development and Digitalisation, relevant donor-funded projects and organisations representatives in the consultation process.

Bidders are encouraged to collaborate with local partners or consultants to support field activities, stakeholder mobilisation, and contextual insights; however, such collaboration is not mandatory. All arrangements remain at the discretion of the bidder.

- Place, duration and terms of performance

The assignment shall be implemented in Chișinău, the Republic of Moldova. While some of the activities could be conducted remotely, the provider selected for this assignment is expected to ensure a strong local presence to facilitate direct engagement with stakeholders, beneficiaries, and institutional partners.

The duration of the assignment is approximately 16 weeks from the date of contract signature. The implementation will follow a phased approach aligned with the indicative timeline from section 4.2 Anticipated deliverables.

- Qualifications and experience

The assignment may be undertaken by a team of experts, a consortium, or an organization. The ideal candidates will demonstrate:

- Proven experience delivering assignments of comparable scope and complexity, including sectoral analysis, multi-stakeholder consultation processes, strategy formulation, and the design of data governance or monitoring systems.

- Demonstrated analytical capabilities and proficiency with data visualisation tools (e.g., Power BI or equivalent).

- Familiarity with Moldova’s startup and innovation ecosystem or with similar emerging ecosystem contexts.

- Experience working in donor-funded projects and multi-stakeholder environments, including coordination with public institutions, private actors, and development partners.

- Ability to deliver clear, concise, and audience-appropriate outputs in English, in both narrative and presentation formats.

- Application documents

The application documents as well as all correspondence and documents relating to this assignment must be written in English.

Candidates must submit the following documents:

- A proof of legal registration (certificate of registration).

- The attached application form - Expression of Interest Form, including the annexes: Sworn Statement on Exclusion Criteria, the Absence of Conflict of Interest and the Third-Party Identification Sheet.

- The attached GDPR compliance verification form, used to verify that the bidder has implemented appropriate technical and organisational measures such that data processing complies with relevant data protection laws and regulations (GDPR and French data protection legislation), thereby guaranteeing the rights of data subjects;

- The draft contract, including the candidate's financial offer, duly completed, dated and signed;

- A technical offer comprising:

- A description of the applicant organization or consortium, including its relevant credentials, track record, and previous experience that demonstrate its suitability for the assignment.

- Curriculum vitae (CVs) of the expert(s) proposed for the implementation of the activities, highlighting their qualifications, thematic expertise, experience in angel investment and prior relevant engagements.

- A detailed financial offer, including:

  - A breakdown of costs presented as a unit price schedule.

  - The schedule should indicate the price per man-day, provide an estimate of the total number of days required to complete the assignment, cover all services and deliverables under the contract, and be consistent with the expected level of effort (approximately 60–80 man-days).

  - The financial offer must also include all associated costs, such as travel, accommodation, venue rental, catering, materials, and any other expenses necessary for the successful implementation of the assignment.

The documents requested above are mandatory. If missing, the tender submitted will not be compliant and will therefore be rejected.

Electronic submission via the French government procurement platform at https://www.marches-publics.gouv.fr is mandatory. Any submission via other means will be rejected.

Deadline for submission: August 28 2026, at 23:59:00 (PARIS TIME)

The period of validity of the offers submitted is fixed at 90 calendar days from the deadline for submission of tenders.

- Evaluation and selection

Expertise France will first check the eligibility of the applications and their ability to provide the service. Subsequently, it will evaluate the offers according to the following criteria:

Criterion 1: Technical offer

Each technically conforming offer will be evaluated based on the following criteria, with a total of 70 points. The Technical Score (TS) will be calculated by summing the points awarded for each sub-criterion.

Technical Offer Evaluation Breakdown

The technical value of each application will be assessed against the following sub-criteria, for a total of 70 points:

| Sub-criteria for assessing the technical quality | Maximum number of points |
| --- | --- |
| Understanding of the Assignment and Context (Clarity in understanding Moldova’s ecosystem challenges, purpose of the strategy, and data monitoring needs) | 20 |
| Quality and Relevance of the Proposed Methodology (Approach for strategy development, data mapping, analysis, dashboard creation, stakeholder engagement, and feasibility within the timeframe) | 20 |
| Expertise and Competence of the Proposed Team (Experience in strategy development, startup ecosystem, data governance, dashboard development, and similar assignments.) | 15 |
| Organisational Experience and Capacity (Relevant past work, institutional capacity to deliver, ability to manage multi-stakeholder assignments.) | 10 |
| Quality and Feasibility of the Work Plan (Coherence, realism, and alignment of the proposed timeline and deliverables.) | 5 |
| TOTAL | 70 |

Minimum Technical Score to Qualify

Only bids scoring 50 points or more in the technical evaluation will proceed to financial assessment.

Criterion 2: Price of the services

The Financial Score (FS), with a maximum of 30 points, will be calculated to allow a comparative assessment of the financial offers submitted by all candidates with conforming bids. The lowest-priced bid will receive the full 30 points, while other bids will be scored proportionally using the following formula:

FS = Lowest Price / Bid Price × 30

Total score will be calculated as a sum of Technical and Financial scores.

- Negotiations

Following the initial analysis of bids by the Evaluation Committee, the contracting authority may enter into negotiations with all or selected bidders, ensuring equal treatment throughout. The contracting authority, however, reserves the right to award the contract without engaging in negotiations.

- Additional information

In order to access the tender consultation space, bidders must connect to the French government procurement platform at:  https://www.marches-publics.gouv.fr