|  | PROCUREMENT CONTRACT |
| --- | --- |
|  | ☒Service – ☐Supplies |
|  | Number: |
|  | Object of the contract: Support the development and implementation of a coordinated strategy and establishment of ecosystem-wide data monitoring system - 23EDI0C190 |
|  | MAXIMUM AMOUNT OF THE CONTRACT: state here the maximum amount of all services/supplies that may be delivered under the contract |
| Notification date:. This contract is subject to the French Public Procurement Code in its latest version in force as enacted by Order No. 2018-1074 issued on 26 November 2018 and its Implementation Decree No. 2018-1075 issued on 3 December 2018 constituting the regulatory aspects of the Public Procurement Code (“CCP”). It is awarded by means of: adapted procedure in application of Articles L. 2123-1 and R. 2123-1 to R. 2123-7 of CCP. |

TABLE OF CONTENTS

special conditions – commitment procedure	1

ARTICLE 1:	Object of the contract	2

ARTICLE 2:	General characteristics of the Contract	3

Form of the Contract	3

Term of the Contract	3

Commencement and deadline of service provision	3

ARTICLE 3:	Financial provisions	3

Amount of the Contract	3

Form of prices	4

Advance	4

Payment procedure	4

Payment terms and late payment interest	5

Presentation of payment demands	5

Bank transfer	6

Value added tax (VAT)	6

Taxes and duties	6

ARTICLE 4:	inspection and acceptance activities	6

Inspection activities	6

Acceptance of services	6

ARTICLE 5:	Specific terms of execution	6

Deliverables table	6

Place of execution	7

Language of the Contract	7

Commitments of the Contractor	7

Confidentiality	8

Provision of documents	8

Insurance	8

Contact person and communication	8

Understaking against deforestation	9

ARTICLE 6:	Re-examination clause	9

ARTICLE 7:	Similar services	10

ARTICLE 8:	penalties	10

Penalties for periodic documentary deliverables	10

Penalties applicable to submission of final deliverables	10

ARTICLE 9:	intellectual property	10

Definitions	10

Ownership of results	10

Exploitation of results	10

Licensing of pre-existing rights	11

Guarantees	11

Image rights	11

ARTICLE 10:	Termination of the contract	11

General terms of performance	11

Termination of the Contract due to the non-availability of a designated expert	12

Procedure	12

ARTICLE 11:	safety and security measures and responsabilities	12

ARTICLE 12:	ethics	12

ARTICLE 13:	Administration of personal data	12

ARTICLE 14:	Dispute resolution - applicable law	13

ARTICLE 15:	Derogation from the CCAG	13

ARTICLE 16:	AUDIT	14

ARTICLE 17:	Final provisions	14

Annex I – Terms of referenses	16

Annex II – Technical And financial offer	26

# special conditions – commitment procedure

Between:

EXPERTISE FRANCE SAS 40, boulevard de Port Royal - 75005 PARIS, France A simplified joint-stock company with share capital of €828,933 registered under the following numbers: - SIRET no.: 808 734 792 00035 - Intra-community VAT number: FR36 808734792 Represented by Mr Jérémie PELLET, Managing Director, of the first part,

and:

Contractor Name: (Hereafter the “Contractor”) - Registered office address: - Registration number at the trade and companies’ registry: - Intra-community VAT no. (as applicable): Represented by: of the second part,

(Hereafter referred to collectively as the “Parties“)

Whereas:

This Service Contract is part of the cooperation project hereinafter referred to as the “MAIN CONTRACT”, whose code is 23EDI0C190 signed on 26 July 2024 by Expertise France and EU Commission, concerning “EU4Innovation East” – Support to Digital innovation in the Eastern Partnership region for the benefit of Ukraine, Moldova, Georgia, Armenia and Azerbaijan implemented by Expertise France.

In the light of the foregoing, the following is agreed:

- Object of the contract

The object of this contract (hereafter the “Contract) is “Support the development and implementation of a coordinated strategy and establishment of ecosystem-wide data monitoring system”.

Contractual documents

The Contract is composed of the contractual documents set out below in decreasing order of priority:

- This document and its annexes:

- Annex I attached: Specifications/ToR;

- Annex II attached: Technical/Financial offer

- Annex III attached: Sworn statement on exclusion criteria, the absence of conflict of interest

- The Code of Conduct of EXPERTISE FRANCE (available at https://www.expertisefrance.fr/documents/20182/426622/Expertise+France+%E2%80%93+Code+of+conduct/82cf6060-4768-4b25-8817-ccba1d86e568);

- CCAG - General administrative clauses applicable to public procurement for day-to-day supplies and services approved under the Order of 30/03/2021, subject to the exceptions set out in the Contract.

These documents constitute the entirety of the agreement between the Parties with regard to the Contract. They supersede all verbal and written communications, procedures, agreements, commitments, guarantees and settlements referring to its object and facts that may have been made by or on behalf of a Party to the other Party before the notification date. These documents are acknowledged by the Parties to represent the sole and complete expression of the terms of their agreement.

Without prejudice to the general rules applicable to administrative contracts, any modification to the Contract or the waiver of any right resulting from the Contract must be covered by an amendment signed by a duly authorized representative of each Party.

- General characteristics of the Contract

## Form of the Contract

The Contract is a public contract for services at fixed and total prices.

The services shall be carried out according to the sequencing and in the order set out in the timeframe below; the validation (notification of an acceptance decision) of each stage conditions the start of execution of the next stage.

## Term of the Contract

The term of the Contract is 6 months from its Notification date to the Contractor by Expertise France.

The Contract shall expire after all services/supplies have been delivered by the Contractor and all rights and obligations of the Parties resulting from the Contract have been extinguished. If all or some of the services/supplies remain outstanding by the specified period, the Contractor must immediately take all necessary steps to complete delivery without being able to claim any remuneration in this regard.

## Commencement and deadline of service provision

The timeframe for execution of the services is specified in the attached Annex I of the CONTRACT and set out as follows:

| Deliverable | Description | Timeline |
| --- | --- | --- |
| Inception Report | Includes methodology, work plan, and stakeholder map | Week 2 -5 from T0 |
| Draft Strategy | A coordinated ecosystem strategy and framework for ecosystem-wide data monitoring | Week 5-6 from T0 |
| Data Analysis Report annexed startups dataset | Key findings, trends, and gaps based on existing datasets, including gender and green startup representation | Week 7-8 from T0 |
| Dashboards & Visuals | Interactive tools tailored to different stakeholder groups | Week 9-10 from T0 |
| Stakeholders’ validation workshop (online) | Validate the report findings, defined stakeholders’ roadmap, workshop report | Week 10-11 from T0 |
| Final Report & Recommendations | Consolidated outputs and roadmap for sustainability | Week 12-15 from T0 |

If all or some of the services/supplies remain outstanding within the specified deadline, the CONTRACTOR must immediately take all necessary steps to complete delivery without being able to claim any remuneration in this regard.

- Financial provisions

## Amount of the Contract

The amount of the CONTRACT is:XXXX € exc. VAT.

This amount equates to the total and fixed price of the Contract, which Expertise France undertakes to pay, after validation, all the services due under the Contract have been accepted without reservation. As pricing is fixed, it includes all costs relating to the corresponding service provision.

The fixed amount  corresponds to the total amount Expertise France undertakes to pay, after validation, all services due under the Contract have been accepted without reservation as spcecified in the Annex 1 and Annex 2. As pricing is fixed, it includes all costs relating to the corresponding service provision and/or delivery of supplies.

## Form of prices

Prices are firm and non-modifiable.

## Advance

## No advance will be made.

## Payment procedure

- Interim payment

Interim payments are set out in this contract and shall be made in accordance with the following terms and conditions.

| Amount of instalment | Payment deadline |
| --- | --- |
| A payment equal to 30% of the total amount of the contract | After submission and approval by Expertise France of the corresponding deliverables: - Inception Report - Draft Strategy - invoice |
| A payment equal to 30% of the total amount of the contract | After submission and approval by Expertise France of the corresponding deliverables: - Data Analysis Report annexed startups dataset - invoice |
| A payment equal to 30% of the total amount of the contract | After submission and approval by Expertise France of the corresponding deliverables: - Dashboards & Visuals - Stakeholders’ validation workshop (online) - invoice |
| A payment equal to 10% of the balance from the total of the contract | After submission and approval by Expertise France of the corresponding deliverables - Final Report & Recommendations - Final invoice |

## Payment terms and late payment interest

Payment is always made out in the name of the issuer of the invoice or of the expense reimbursement request.

Overall payment terms for monies due under the Contract are thirty (30) days maximum from the date of receipt of the complete invoice, including all supporting documentation, or the date of service/supply acceptance if this date is later. Any missing document will prevent payment.

If these payment terms are not respected, Expertise France will pay late payment interest to the Contractor pursuant to Article R. 2192-10 et seq. of the CCP on the fight against late payment in public procurement contracts. The rate applied shall be the interest rate of the European Central Bank for its main and most recent refinancing operations, as applicable on the first day of the semester of the calendar year during which late payment interest started to accrue, plus eight percentage points.

The amount of the fixed indemnity to cover collection costs is set at forty (40) euros and will be systematically paid in addition to late payment interest. Interest below €40 shall not be mandated.

## Presentation of payment demands

In addition to the legal notices (intracommunity VAT no.), invoices relating to the Contract must contain the following information:

- Company name, address and registered office of the Contractor;

- Registration number of the Contractor (SIRET or equivalent);

- Bank account details;

- The code of the department acting as specifying department (stated in the article entitled Contact person and communication);

- Reference number of the Contract;

- The reference and title of the cooperation project concerned (if applicable);

- Clear and accurate description of the equipment/supplies sold and/or services performed;

- If the Contractor’s bank details are not stated on invoices, it must provide a statement or certificate of bank or post office account details, with the third-party form duly completed in all cases.

Invoices are to be forwarded via the Chorus Pro system, and must state the department code provided above corresponding to the department of Expertise France on behalf of which the Contract has been placed.

If the Contractor is not obliged to forward invoices via Chorus, it may submit its invoices to the contact person stated in the article entitled Contact person and communication.

Invoices for advances must be accompanied by the corresponding supporting documentation validated by Expertise France.

Invoices for balances (partial definitive payments) must be accompanied by a copy of the acceptance decision for the corresponding services and/or supplies.

Any missing document will prevent payment.

## Bank transfer

Payment for invoiced services/supplies will be made to the bank account identified in the third-party sheet.

Payment is always made out in the name of the issuer of the invoice or of the expense reimbursement request.

## Value added tax (VAT)

The Contractor must state the VAT rate applicable to the transaction or, as applicable, its VAT exemption by stating on the invoice the relevant provisions of the French General Tax Code or those of Directive 2006/112/EC of 28 November 2006.

Any Contractor benefitting from exemption must state “VAT exempt” in accordance with the rules that apply to it.

## Taxes and duties

The Contractor shall be directly responsible for all taxes and duties that may be levied against it under the Contract, both in the country of its registered office and in those of project implementation.

- inspection and acceptance activities

## Inspection activities

Inspection activities will be carried out for services and supplies as set out in Chapter 5 of the CCAG-FCS. By way of derogation from Article 23 of the CCAG-FCS, inspection activities will be carried out by:

- The Country coordinator, Ionela Titirez

- the Deputy Project Director, Charles Mathiaux

## Acceptance of services

By way of derogation from Article 25 of the CCAG-FCS, acceptance activities will be carried out by:

- the Country coordinator, Ionela Titirez - ionela.titirez@expertisefrance.fr

- the Deputy Project Director, Charles Mathiaux - charles.mathiaux@expertisefrance.fr

Any lack of response from Expertise France shall not equate to tacit acceptance of services or supplies.

- Specific terms of execution

## Deliverables table

All timelines indicated below are calculated from the notification date of the contract (T0). The deadlines correspond to the latest submission dates of the deliverables

| Deliverable | Description | Timeline |
| --- | --- | --- |
| Inception Report | Includes methodology, work plan, and stakeholder map | Week 2 -5 from T0 |
| Draft Strategy | A coordinated ecosystem strategy and framework for ecosystem-wide data monitoring | Week 5-6 from T0 |
| Data Analysis Report annexed startups dataset | Key findings, trends, and gaps based on existing datasets, including gender and green startup representation | Week 7-8 from T0 |
| Dashboards & Visuals | Interactive tools tailored to different stakeholder groups | Week 9-10 from T0 |
| Stakeholders’ validation workshop (online) | Validate the report findings, defined stakeholders’ roadmap, workshop report | Week 10-11 from T0 |
| Final Report & Recommendations | Consolidated outputs and roadmap for sustainability | Week 12-15 from T0 |

## Place of execution

## The services shall be performed primarily in Chișinău, Republic of Moldova. While certain analytical work, meetings, and preparatory activities may be carried out remotely, the Contractor shall ensure a strong local presence throughout the assignment to enable effective engagement with stakeholders, beneficiaries, and institutional partners.

The costs associated with these missions, including travel, accommodation, subsistence and any related expenses, are deemed to be included in the Contract price. No additional reimbursement shall be made by the Contracting Authority.

## Language of the Contract

This document is written in English, which shall be the reference language for any dispute that may arise regarding the meaning or interpretation of the Contract, to the exclusion of any other language.

## Commitments of the Contractor

The Contractor is subject to a performance obligation and therefore undertakes to:

- comply with the Specifications;

- immediately notify Expertise France in writing of any communication or instruction relating to the services/supplies that it may receive from the Client (beneficiary country or public entity) or from a third party, and not to comply with any such communication or instruction until having discussed the matter with Expertise France and after receiving the latter’s written authorization;

- notify any difficulty it may encounter with the performance of its obligations under the Contract;

- comply with all applicable laws and regulations of the country of delivery of the services/supplies and adopt an attitude and act vis-à-vis third parties in the interests of Expertise France, such that Expertise France cannot be reproached in this regard by the Client, or by any person the latter may have designated;

- protect the interests of Expertise France vis-à-vis the Client;

- act as a loyal advisor vis-à-vis Expertise France;

- present itself vis-à-vis the Client, partners and local authorities as a Contractor engaged by Expertise France;

- apply the undertakings of Expertise France as expressed in its Code of Ethics, provided in Annex 5 of the Contract.

In the context of Contract execution, the Contractor undertakes to:

- perform the services/supplies in a diligent, effective and economic manner, in accordance with generally accepted techniques and practices;

- employ appropriate modern techniques and safe and affective processes.

## Confidentiality

The Contractor shall treat as private and maintain the confidentiality of all documents and information received or which it becomes aware of in the context of the Project. It shall maintain the secrecy thereof and not use them for any purpose other than execution of the Contract.

In this regard, the Contractor undertakes:

- To protect and maintain the confidentiality of information considered or presented as such;

- To handle confidential information, it receives with the same degree of care and protection as it applies to its own confidential information;

- only to reveal confidential information to its personnel and third parties involved in performance of the Contract after having received prior written and express approval from Expertise France;

- to take all necessary steps such that its personnel and third parties involved in execution of the Contract, who become aware of confidential information, undertake to treat such information with the same level of confidentiality as set out in this clause;

- As and when required, to reiterate the confidential nature of such information to its personnel and third parties involved in the execution of the Contract, as soon as said confidential information is communicated to the aforementioned persons;

- to reiterate the confidential nature of confidential information prior to any meeting during which confidential information is communicated.

Apart from where necessary for the purposes of service delivery, the Contractor may not disclose any element of the Contract without prior written consent from the other party.

## Provision of documents

Expertise France shall ensure that the Contractor receives in good time all the documents (as set out below) required for delivery of the services/supplies:

- ToR

- Technical and financial offer of the Main Contract

- Specifications of the MAIN CONTRACT

## Insurance

The Contractor shall take out, and maintain at its own expense, third-party and professional liability insurance policies covering the physical injury and material and consequential damage that may arise from delivery of the services/supplies.

The Contractor shall also take out, and maintain at its own expense, insurance policies covering its working accident and occupational illness liability with regard to its agents assigned to delivery of the services/supplies.

The Contractor must be able to produce on request by Expertise France all certificates demonstrating its possession of the aforementioned policies.

## Contact person and communication

All communication and notifications between the Parties under the Contract shall take place in written form, either through the exchange of e-mails or via registered letter with acknowledgement of receipt, where the latter form is prohibited in certain cases under the Contract, and shall be deemed to have been validly served from its receipt by the addressee.

All correspondence shall be forwarded, all carriage costs paid, to the following addresses:

| For Expertise France: | Expertise France Deputy Project Director, Charles Mathiaux Department of Economy and inclusive development 40, boulevard de Port Royal F-75005 PARIS charles.mathiaux@expertisefrance.fr |
| --- | --- |
| For the Contractor: | To be completed by the Contractor |

Each Party may modify its address at any time subject to notifying the other Party thereof in writing.

## Undertaking against deforestation

Within the framework of the policy to combat imported deforestation and in the hypothesis of the use of raw materials or processed products, the Contractor undertakes to evaluate precisely the quantities really necessary and to study alternatives to the products at risk listed below:

- Meat;

- Eggs;

- Dairy products;

- Ready-made meals, margarine, spreads;

- Leather shoes;

- Automotive upholstery;

- Household and cleaning products;

- Agrofuels;

- Lumber;

- Solid wood or particle;

- Fuels;

- Paper;

- Cardboard;

- Textiles;

- Coffee, chocolate;

- Exotic fruits;

- Electronics.

For more information, the guide Engaging in Zero Deforestation Public Procurement is available at the following email address: https://www.ecologie.gouv.fr/sites/default/files/Guide_politique_achat_public_zero_deforestation.pdf

- Re-examination clause

Under Article R.2194-1 et seq. of the Public Procurement Code, Expertise France may amend the provisions of the Contract subject to the following conditions:

- Revision of technical elements (clarification of deliverables, producer technical definitions, equipment technical documents, updated instructions, etc.)].

Such modifications shall be notified to the Contractor: by simple exchange of correspondence via the secure platform PLACE, or via any means defined by Expertise France guaranteeing full traceability of exchanges.

- Similar services

Under Article R.2122-7 of the French Public Procurement Code, the Contractor may be awarded a contract for similar services to those of the initial contract without advertising or competitive bidding.

- penalties

The amount of penalties will be applied within the calculation of the balance due under the relevant item or purchase order.

## Penalties for periodic documentary deliverables

By way of derogation from Article 14 of the CCAG, penalties are set at the fixed rate of €50 net per day of delay in the delivery of the periodic deliverables specified in Article 6 “Deliverables table” of the Contract.

## Penalties applicable to submission of final deliverables

By way of derogation from Article 14 of the CCAG, penalties are set at the fixed rate of €100 net per day of delay in the delivery of the final deliverables specified in Article 6 “Deliverables table” of the Contract.

- intellectual property

## Definitions

The Assignment provided for by this article requires definition of the following terms:

- “Result” means any intended outcome of the performance of the Contract which is delivered and definitively accepted by Expertise France;

- “Creator” means any natural person who contributed to the production of the result;

- “Pre-existing right” means any intellectual property right, including pre-existing technologies owned by Expertise France, the Contractor or any third party with a prior interest in the order to be executed under the Contract.

## Ownership of results

The ownership of results, and the title to related intellectual and industrial property rights, including the solutions and technical information they contain, are entirely and irrevocably transferred to Expertise France under the Contract. This Assignment only covers the economic rights of creators under the conditions set out in Article 8.3 of the Contract. The moral rights of creators are excluded. Such moral rights cover the disclosure, paternity and respect for the integrity of the results treated as a work within the meaning of the French Intellectual Property Code.

The aforementioned elements shall be deemed to be effectively transferred to Expertise France after acceptance of the results delivered to it by the Contractor.

The payment of the price to the Contractor is deemed to include any fees payable to the Contractor in relation to the acquisition of rights by Expertise France, notably all forms of exploitation of the results. The acquisition of such covers all territories worldwide.

## Exploitation of results

By acquiring title to the results developed by the Contractor, Expertise France becomes the holder of all economic copyright relating to such rights. In this regard, yet without the list being exhaustive, Expertise France may exploit the results for the following purposes:

- internal exploitation:

  - disclosure to its personnel;

  - communication disclosure to persons and entities working for Expertise France or cooperating with it, including contractors, subcontractors (whether legal or natural persons), EU institutions, agencies and bodies and member states' institutions;

  - installing, uploading, processing, arranging, compiling, combining, retrieving, copying, reproducing in whole or in part and in unlimited number of copies.

- distribution to the public:

  - in paper, electronic or digital format;

  - on the internet as a downloadable/non-downloadable file;

  - via display, radio or television broadcasting or any other transmission technique;

  - otherwise in any form and by any method.

- modifications:

  - modification of content, form or technique;

  - addition of new elements of content and form;

  - adaptation using new media;

  - translation into any language;

  - digitization and computer processing.

## Licensing of pre-existing rights

Expertise France shall not acquire ownership of pre-existing rights. The Contractor shall license the pre-existing rights on a royalty-free, non-exclusive and irrevocable basis to Expertise France, which may use the pre-existing rights as set out in Article 8.3. Such licenses shall become effective from the moment the results are delivered by the Contractor and accepted by Expertise France. On delivery of the results, the Contractor may, as required, provide Expertise France with a list of pre-existing rights and third parties' rights, including those of its personnel, of creators and of other right holders. The licensing of pre-existing rights to Expertise France under the Contract covers all territories worldwide and is valid for the whole duration of intellectual property rights protection.

## Guarantees

When delivering the results, the Contractor shall warrant that they are free of rights or claims from creators and third parties, including in relation to pre-existing rights, for any use envisaged by Expertise France.

On request from Expertise France, the Contractor shall provide evidence of ownership or rights to use all the listed pre-existing rights and rights of third parties, except for the rights owned by Expertise France.

## Image rights

If natural, recognizable persons appear in a result or their voice is recorded, on request from Expertise France the Contractor shall submit a declaration in which such persons (or of the persons exercising parental authority in case of minors) give their permission for the described use of their image or voice. This does not apply to persons whose permission is not required in line with the law of the country where photographs were taken, films shot or audio records made.

- Termination of the contract

## General terms of performance

The Contract is subject to the termination clauses as defined in Articles 29 to 36 of the CCAG.

By way of derogation from Article 40 of the CCAG PI, termination for reasons of general interest is not applicable to this contract. However, the parties agree on the possibility of terminating the contract by mutual consent.

In the event of early termination, the Contractor shall immediately return to Expertise France all documents it may have received for the purposes of execution of the Contract.

## Termination of the Contract due to the non-availability of a designated expert

In the event of the non-availability of a designated expert, the Contractor shall notify Expertise France thereof within 3 days and, within 14 days at the latest, propose the CV of a replacement expert of at least the same level or expertise. If these replacement conditions are not respected, Expertise France may terminate the Contract due to fault on the part of the Contractor.

Regardless of the circumstances, should an expert remain unavailable for a cumulative duration of 2 weeks without a satisfactory replacement having been found, Expertise France may automatically terminate the Contract.

Termination for the non-availability of a designated expert shall not establish any entitlement to any form of compensation for the Contractor.

## Procedure

Any termination decision shall be notified by Expertise France to the Contractor by registered letter with acknowledgement of receipt. It shall state the effective date of termination.

- safety and security measures and responsabilities

The Contractor is the only one who is responsible for the safety of the people and property that he mobilizes for the execution of the present Contract and in this respect, takes all necessary measures. He undertakes to ensure that all of his employees and subcontractors comply with the safety instructions that he issues.

In the event of an incident and/or direct or indirect attack on the safety of people directly or indirectly mobilised by the contractor or its equipment, Expertise France cannot be held responsible in any way whatsoever.

- ethics

The Contractor also undertakes to take note of the  Expertise France Code of Conduct and to comply strictly with it (the Expertise France code of conduct is available on the agency’s website: www.expertisefrance.fr).

Any breach to comply with the code of conduct may result in the termination of the Contract and incur the liability of the Contractor.

- Administration of personal data

Under Article 13 or Regulation (EU) no. 2016/679 of the European Parliament and of the Council of 27 April 2016 on the protection of natural persons with regard to the processing of personal data and on the free movement of such data (GDPR), the Contractor is notified that personal data (notably name, first name and e-mail address) collected under this contract may be processed.

The legal basis under which such processing is performed are set out in c) and e) of Article 6.1 of the GDPR, namely:

- The processing is necessary in order to comply with a legal obligation by which Expertise France is bound;

- The processing is necessary for performance of a public-interest assignment or which falls within the scope of the public authority entrusted to Expertise France.

The purposes of the processing are as follows:

- Management and monitoring of this Contract

- Management and monitoring of reports forwarded to donors and other supervisory authorities.

Recipients or category of recipients of the personal data are exclusively authorized personnel of Expertise France, ministries and state operators and donors responsible for awarding and executing this contract, including any service providers assisting them with their activities.

Retention period: the data will be held throughout the execution of the contract, including the DUA (duration of administrative usefulness) applicable to the contract.

Under Articles 15 to 21 of the GDPR, persons whose personal data is collected enjoy a right of access, rectification and deletion with regard to such data. They also enjoy the right to restrict and refuse processing on legitimate grounds. The information and other rights of data subjects may be exercised by contacting the Data Protection Officer of Expertise France (informatique.libertes@expertisefrance.fr).

Persons whose personal data is collected under this procedure may submit a complaint to CNIL.)]

The Contract may require the processing of personal data. The parties undertake to comply with regulations on the processing of personal data in accordance with amended law no. 78-17 of 6 January 1978 relating to data processing, files and liberties and regulation (EU) 2016/679, known as the General Data Protection Regulation (GDPR).

The Contractor notably undertakes to:

- Process personal data solely for the purposes of the Contract, as defined in annex hereto covering the collection of personal data (GDPR data processor);

- Ensure that persons authorized to process personal data undertake to maintain its confidentiality or are bound by an appropriate legal obligation of confidentiality;

- Implement appropriate technical and organizational measures to guarantee a level of security commensurate with the risks resulting from the Contract, notably with regard to data encryption, confidentiality and integrity;

- Notify Expertise France, via any means, of any personal data breach within 24 hours of becoming aware of any such event;

- Assist Expertise France in its obligation to respond to requests it may receive from data subjects;

- Delete all personal data or return it to Expertise France on conclusion of the services covered by the Contract, as specified by the latter, unless EU law or that of the member state requires such data to be retained;

- Make available to Expertise France all information it may require to demonstrate compliance with the obligations set out in this article and to enable audits to be conducted by the latter or by any other person of its choice.

Where the Contractor uses a data processor to process personal data during execution of the Contract, it must obtain prior written authorization from Expertise France. Similarly, the Contractor shall notify Expertise France of any planned change concerning the addition or replacement of processors, thereby enabling Expertise France to issue any objections it may have in this regard.

The same obligations concerning data protection as those set out in the Contract are mandatory for processors, notably regarding the provision of adequate guarantees for the implementation of appropriate technical and organizational measures ensuring the protection of personal data. Should any processor fail to meet its obligations, the Contractor shall remain fully responsible vis-à-vis Expertise France for the fulfillment of the processor’s obligations.

In the event of non-compliance with the aforementioned provisions, the Contractor is reminded that its liability may be invoked. In the event of any breach of professional secrecy or non-compliance with the aforementioned provisions, Expertise France may immediately terminate the Contract without compensation for the Contractor.

- Dispute resolution - applicable law

Any dispute between the Parties relating to the existence, validity, interpretation, execution, and termination of the Contract (or any of its clauses) that the Parties cannot resolve amicably within 30 days of the notification of the dispute by the requesting Party to the other Party, shall be submitted to the competent court.

The applicable law for this Contract is French law, to the exclusion of any other law.

- Derogation from the CCAG

The following articles of this document derogate from the CCAG-FCS:

- article 5 derogates from article 28 and 15 of the CCAG;

- article 9 derogates from article 14 of the CCAG

- AUDIT

The Contractor may be submitted to an audit concerning compliance with the regulations and contractual obligations applicable to the performance of the present Contract. This audit may be carried out by Expertise France or by a third party appointed by Expertise France and may not be refused by the Contractor. If the audit is carried out by a third party, the appointed third party must not be a direct competitor of the Contractor. Scheduled audits may be carried out periodically or spontaneously at the request of Expertise France or a third party. In all cases, the contractor will be informed at least 5 working days in advance.

The Contractor therefore undertakes to:

- Allow Expertise France or the appointed entity, and facilitate their access to the information required to carry out the audits, including interviews with the people involved and on-site visits;

- Submit documents relating to the performance of the present Contract as well as any documents required by the auditors;

- Demonstrate transparency and respond to auditors’ requests;

- Implement any corrective measures that may be necessary.

Expertise France will notify the Contractor of the identity of the audit structure selected in the case of an external firm, the purpose of the assignment, the planned duration of the assignment and the names of the experts assigned.

The Contractor also undertakes to allow Expertise France, or any other third party mandated by Expertise France, to carry out an investigation in the case of an allegation of a prohibited practice relating to the present Contract, under the conditions set out above.

The conclusions of the audit report will be sent to each of the Parties by any means deemed appropriate by Expertise France.

The conclusions may prescribe the implementation of actions and a deadline for completion.

Any refusal by the Contractor to comply with the audit exercises and/or their conclusions gives as of right to Expertise France the possibility to terminate the present contract without compensation.

- Final provisions

## Declaration

The Contractor, its affiliates, suppliers, service providers, consultants and subcontractors (including directors, employees and agents of such entities) hereby declares:

- that no natural or legal person on whose behalf the Contractor is acting is subject to the prohibitions set out in Articles L. 2141-1 to L. 2141-6 and L. 2141-7 to L. 2141-11 of the French Public Procurement Code or any equivalent prohibition issued in another country;

- that the commitments made by the Contractor within the scope of the Contract do not create a situation of conflict of interest that may affect the execution of the Contract;

- that the Contractor have not committed any act that may influence the process of Project implementation to the detriment of the Beneficiary, and notably that no Understanding has been, or will be, entered into;

- that the negotiation, award and execution of the Contract has not given rise to, nor will do so in the future, any act of corruption as defined in the United Nations Convention Against Corruption dated 31 October 2003;

- accepts that the Contract will be awarded in accordance with standard practices and in electronic format.

Furthermore,

The Contractor, its affiliates, suppliers, service providers, consultants and subcontractors (including directors, employees and agents of such entities) certify that:

- they do not acquire and don't supply/will not acquire or supply equipment and do not intervene/will not intervene in sectors under embargo by the United Nations, the European Union or France. For information, the list can be found at: https://www.sanctionsmap.eu ;

- they are not included in the lists of financial sanctions adopted by the United Nations, the European Union, France and/or the United States, notably in the fight against the financing of terrorism and against attacks on national peace and security. For information, the lists can be consulted at the references below:

- for the United Nations, the United Nations Security Council sanctions lists: https://www.un.org/securitycouncil/content/un-sc-consolidated-list;

- for the European Union, the lists can be consulted at the following address: https://www.sanctionsmap.eu;

- for France, see: https://gels-avoirs.dgtresor.gouv.fr/List;

- for the United States, see: https://home.treasury.gov/policy-issues/financial-sanctions/sanctions-programs-and-country-information;

- they are not subject to a World Bank exclusion order and are not on the list published by the World Bank. For information, the list can be consulted at the following address:

https://www.worldbank.org/en/projects-operations/procurement/debarred-firms

In the hypothesis of such a decision of exclusion, we can join to the present declaration on honor the additional information which would allow to consider that this decision of exclusion is not relevant within the framework of the market).

Finally, the Contractor, its affiliates, suppliers, contractors, consultants and subcontractors (including directors, employees and agents of such entities) acknowledge and accept that the above-mentioned situations may lead to the automatic termination of the contract.

They undertake to inform Expertise France without delay of any change in our situation during the execution of the contract with regard to the present declaration.

FOR THE CONTRACTOR:

In ...……....., on...…….....20....

Preceded by the handwritten words “Read and approved":

Signature:

Name: 
First name:

Role:

FOR EXPERTISE FRANCE:

This offer is accepted as an undertaking.

In Paris, on...…….....2026

Signature:

Name: Gulhem 
First name: Clara

Role: Responsable du pôle Entreprenariat et Innovation

Done in one original copy retained by Expertise France.

# Annex I – Terms of referenses

TERMS OF REFERENCE AND TECHNICAL SPECIFICATIONS

EU4Innovation East – Technical Assistance for ecosystem strategy and data monitoring in Moldova

- General information

| # Assignment name | Support the development and implementation of a coordinated strategy and establishment of ecosystem-wide data monitoring system |
| --- | --- |
| # Beneficiary | Expertise France – EU4Innovation East project |
| # Country | Republic of Moldova |
| # Assignment Duration | 4 Months |

- Context and justification of the need

The EU4Innovation East is a regional project aiming at enhancing the competitiveness of the startup ecosystem within 5 countries of the Eastern Partnership (EaP): Armenia, Azerbaijan, Georgia, the Republic of Moldova and Ukraine. EU4Innovation East focuses on strengthening the performance of the local ecosystems to provide support to startups, improving access to funding and markets, and delivering targeted support to Ukraine’s tech ecosystem. The initiative combines co-financing, skills training, regulatory guidance, and gender-inclusive measures to promote long-term, sustainable innovation across the region.

The EU4Innovation East project is funded by the European Union, co-funded by the French government and implemented by Expertise France.

| Title: | Initiative “EU4Innovation East” – Support to Digital Innovation in the Eastern Partnership region |
| --- | --- |
| Geographic scope: | Multi-country Eastern Partner: Armenia, Azerbaijan, Georgia, Republic of Moldova and Ukraine |
| Duration: | • Duration: 54 months, i.e. 4.5 years (04/2024 - 10/2028) |
| Financed by: | • EU Commission: 20.000.000,00€ • France: 2.120.000,00€, earmarked for Ukraine |
| Implementing Agency: | Expertise France (EF) |
| Overall objective: | Strengthen the competitiveness and maturity of the EaP startup ecosystem |
| Specific Objectives: | SO1: Enhance early-stage funding access for EaP startups, especially those led or co-founded by women, by creating a new funding mechanism and improving incubation programs, including technology transfer initiatives. SO2: Foster innovation development in EaP ecosystems by structuring and improving the business environment. SO3: Amplify the visibility of EaP startups and strengthen connections with European investors, fostering both funding acquisition, market access, and increased local interest in the entrepreneurial journey. |
| Pillars description: | Pillar 1 - Early-stage funding Pillar 2 - Backing high added-value segments and high-performance incubation Pillar 3 - Strengthening Community ties Pillar 4 - International Spotlight for EaP Startups Integrating European emblematic events |

Local context

Moldova’s entrepreneurial and innovation ecosystem has expanded in recent years, reflecting growing interest among founders and a gradual shift toward knowledge-based economic activity. Public authorities, development partners, and private-sector actors have introduced various support measures—innovation grants, incubation and acceleration initiatives, and regulatory improvements aimed at encouraging startup creation. According to Startup Moldova’s annual report, startup investment reached USD 7.9 million in 2024—twice the 2023 level—and is projected to double again in 2025.

Despite this progress, the ecosystem remains fragmented, insufficiently coordinated and functioning at suboptimal efficiency. Numerous actors—including startup support organisations, universities, innovation centres, donor-funded programmes, private associations, and public agencies—operate without a shared vision and strategic framework. Their efforts, while valuable individually, do not collectively form a coherent or mutually reinforcing system. As a result, support services vary in quality, overlaps and gaps persist, and the ecosystem struggles to provide consistent pathways for founders as they grow and scale their ventures.

One of the structural challenges is the absence of a unified national vision or roadmap for startup ecosystem development. Without a coordinated strategy, interventions tend to be short-term, project-driven, and focused on isolated components rather than systemic needs. Startup support organisations lack a common reference framework for service design and performance standards. At the same time, donor programmes increasingly target innovation and entrepreneurship, yet operate with limited alignment, which reduces opportunities for complementarity, long-term sustainability, and scaling of what works.

Another constraint is the limited availability of reliable, structured, and publicly accessible data on startup activity, support services, investment flows, and ecosystem performance. Existing datasets are scattered across institutions, vary in quality, and lack standardisation or alignment with European indicators. This constrains data-driven policymaking, donor coordination, and the ability to track ecosystem evolution over time. Startup Moldova has begun to curate foundational datasets; however, these remain underutilised and require methodological strengthening and enhanced visibility.

This assignment seeks to address these gaps by supporting the development and implementation of a coordinated strategy for ecosystem development and an ecosystem-wide data monitoring framework.

The selected team will engage stakeholders through a participatory co-design process to gather insights, validate priorities, and ensure broad ownership; however, the consultants themselves remain fully responsible for drafting the complete Startup Ecosystem Development Strategy, ensuring it reflects shared priorities, ensures interoperability, and aligns with international best practices.

Also, by analysing existing datasets—particularly those curated by Startup Moldova—the team will generate a baseline report and develop dashboards that visualize ecosystem current status, trends, gaps, and opportunities. These dashboards will be integrated into the Startup Moldova website to enhance local and international visibility and accessibility of the ecosystem data. Among other areas, the consultants will assess the long-term viability of showcasing ecosystem data on an international dashboard and will propose funding options to support such an initiative.

Beyond technical outputs, the assignment aims to foster a culture of collaboration and transparent, well-structured data management across the ecosystem. It will establish mechanisms for continuous data collection and reporting, strengthen institutional capacity to use data for decision-making, and facilitate donor coordination around shared metrics and strategic priorities. Ultimately, these efforts will help build a more transparent, resilient, and internationally credible innovation ecosystem in Moldova.

- Objectives of the assignment

This Terms of Reference (ToR) outlines a consulting assignment aimed at strengthening strategic coordination and establishing robust data governance across Moldova’s startup and innovation ecosystem.

3.1. General objective

The general objective of this assignment is to strengthen Moldova’s startup and innovation ecosystem by developing a comprehensive Startup Ecosystem Development Strategy, underpinned by a strategic framework that aligns stakeholders around shared priorities, and by establishing an ecosystem-wide data monitoring system. Together, these components will provide a unified roadmap for ecosystem development, improve the availability and transparency of data, and enable more coherent, effective, and well-coordinated policies and donor interventions.

3.2. Specific objectives

(A) Develop a Startup Ecosystem Development Strategy

- Co-design a unified strategic framework that articulates a shared vision for ecosystem development and establishes priority areas for intervention.

- Engage public institutions, startup support organisations (SSOs), private actors, and donors to ensure that the strategy captures common priorities and supports coordinated action.

- Analyse the current structure and performance of the ecosystem, identifying systemic gaps, overlaps, and opportunities for improvement.

- Develop a roadmap of actionable steps to strengthen support services, improve coordination, and align ecosystem development with European and international best practices.

- Assess long-term options for showcasing ecosystem data internationally, including feasibility, sustainability, and potential funding mechanisms.

(B) Create an Ecosystem-Wide Data Monitoring Framework

- Conduct an AS-IS assessment of existing datasets, data owners, indicators, and methodologies—particularly those curated by Startup Moldova.

- Generate a reference data report capturing current ecosystem performance and identifying gaps in data quality, coverage, and standardisation.

- Develop interactive dashboards that visualise ecosystem trends, gaps, and opportunities; integrate these dashboards into the Startup Moldova website.

- Design a long-term data governance model that defines processes, roles, quality assurance mechanisms, and update cycles.

- Align the proposed framework with EU and international methodologies (e.g., European Innovation Scoreboard, Startup Nations Standard, DESI).

- Facilitate donor coordination around shared metrics and harmonised reporting standards.

- Description of the assignment

The assignment will support the development of a coordinated strategy and the establishment of a sustainable, ecosystem-wide data monitoring system for Moldova’s tech and startup landscape. It includes stakeholder consultations, strategy drafting, analysis of existing datasets (notably from Startup Moldova), and the creation of dashboards and visual tools. The work is supposed to enhance coordination among ecosystem actors and donors, improve data governance, and enable evidence-based decision-making.

While the resulting Startup Ecosystem Development Strategy will be developed in close consultation with government institutions and aligned with national priorities for economic competitiveness, it is conceived as a sector-driven, bottom-up document rather than an official policy instrument. Its purpose is to provide a coordinated vision, guide stakeholder action, and support donor alignment, without requiring formal governmental adoption.

  - Description of Services

The assignment aims to support the coordinated development of Moldova’s startup and innovation ecosystem by producing two core, interlinked deliverables:
(1) Startup Ecosystem Development Strategy, and
(2) an ecosystem-wide Data Monitoring Framework supported by baseline analysis and integrated dashboards.

The selected organisation will propose an appropriate methodological approach and work plan to achieve the objectives of the assignment. While the consultant is expected to outline clear stages of work, the sequencing and structure of these stages may differ from the illustration below and should reflect best practices in strategic ecosystem development, participatory design, and data governance.

The work will include, but not be limited to, the following areas of service:

1. Update Ecosystem Diagnostic and Strategic Foundations

- Conduct an assessment of Moldova’s startup and innovation ecosystem, examining actors, services, governance, regulatory frameworks, talent pipelines, funding mechanisms, infrastructure, and other elements.

- Build on the ecosystem mapping conducted by the EU4Innovation East project at the end of 2024 (to be provided), updating and refining it as needed. The consultant may propose an alternative structure or analytical model if it provides clearer insights or improved alignment with international standards.

- Engage a broad range of stakeholders—including startup support organisations, public institutions, founders, investors, academia, and development partners—to identify shared priorities, systemic bottlenecks, and opportunities for coordinated actions.

- Develop a strategic framework or conceptual structure to guide the formulation of the Startup Ecosystem Development Strategy.

2. Drafting of the Startup Ecosystem Development Strategy

- Elaborate a strategic document that articulates a shared vision for ecosystem development, identifies priority areas for intervention, and proposes a coordinated approach across public and private stakeholders.

- Define recommended actions, governance arrangements, institutional roles, and areas where donor support could be aligned or consolidated.

- Provide a practical roadmap for implementation, including short-, medium-, and long-term measures, sequencing considerations, and potential risks or enabling factors.

- Assess the long-term feasibility of presenting Moldova’s ecosystem data on an international-facing dashboard or platform, and outline potential sustainability and funding options.

3. Development of the Ecosystem-Wide Data Monitoring Framework

- Conduct an AS-IS assessment of ecosystem data availability, data owners, methodologies, and quality—including datasets curated by Startup Moldova.

- Produce a baseline data report that consolidates available indicators and visualises ecosystem trends, gaps, and opportunities.

- Design a Data Monitoring Framework aligned with EU and international methodologies (e.g., European Innovation Scoreboard, Startup Nations Standard, DESI).

- Propose a data governance model detailing roles, responsibilities, processes for data collection and updates, and quality assurance mechanisms.

- Develop data dashboards visualising key indicators and prepare them for integration into the Startup Moldova website, enhancing visibility and accessibility for national and international stakeholders.

- Dashboards should be modular and allow for different user profiles (e.g., startups, investors, donors, policymakers).

- Consultants are encouraged to incorporate gender-disaggregated and sustainability-related indicators where feasible.

4. Validation, Capacity Strengthening, and Stakeholder Alignment

- Facilitate workshops and consultation sessions to validate the Strategy, Data Framework, and dashboards.

- Build the capacity of Startup Moldova and other relevant institutions to maintain, update, and communicate ecosystem data over time.

- Support coordination with development partners to foster alignment around shared metrics, data standards, and strategic priorities.

- Provide final consolidated documentation summarising methodologies, findings, validated recommendations, and proposed next steps for implementation.

- Provide recommendations on mechanisms and incentives to motivate data subjects—particularly startup founders/managers—to share relevant information, increasing participation and ensuring long-term sustainability of the data system.

  - Anticipated deliverables

Indicative Length and Format of Deliverables
To ensure clarity, usability, and efficiency, the contracting authority encourages concise and action-oriented deliverables. Unless otherwise agreed, reports should generally not exceed 10–20 pages (excluding annexes), with key findings presented visually where appropriate. The consultant is welcome to propose either Narrative or Presentation formats where suitable, provided the content remains clear, complete, and aligned with the requirements of each deliverable. All written outputs shall be submitted in English and delivered in both PDF and editable formats. Dashboards must be provided in a web-ready digital format compatible with the Startup Moldova platform.

| Deliverable | Description | Indicative Timeline |
| --- | --- | --- |
| 1. Inception Report | Refined work plan and methodology, stakeholder engagement plan, confirmation of analytical structure for strategy and data framework. | Week 1–2 |
| 2. Updated Ecosystem Mapping & Diagnostic Report | Updated ecosystem mapping and diagnostic covering actors, services, governance, policy, funding, infrastructure, and talent. | Week 2–4 |
| 3. AS-IS Data Assessment & Baseline Report | Review of existing datasets (from Startup Moldova), data gaps, data quality assessment, and consolidated baseline indicators with initial visualisations. | Week 4–6 |
| 4. Draft Startup Ecosystem Development Strategy | Vision, priority areas, coordination mechanisms, implementation roadmap; aligned with government competitiveness priorities but not an official policy document. | Week 6–8 |
| 5. Draft Ecosystem Data Monitoring Framework | Indicator set aligned with EU/international methodologies; data governance model; update cycles; quality assurance; recommendations on motivating startups to share data with Startup Moldova. | Week 8–10 |
| 6. Prototype Dashboards | Visualisation of ecosystem indicators; prepared for integration into the Startup Moldova website. | Week 10–12 |
| 7. Final Ecosystem Package (merged final output) | Validation summary; Final Strategy; Final Data Monitoring Framework; Final Dashboards; Final Integrated Report with findings and recommendations. | Week 12–16 |

Note: The assignment is expected to require approximately 60–80 man-days. This estimate is provided to guide bidders in calibrating the scope and intensity of their proposed methodology.

  - Coordination

The selected consultants will work in close coordination with EU4Innovation East and collaborate with Startup Moldova, Dreamups, XY, YEP! MITP and other ecosystem organisations. They will make sure to include the Ministry of Economic Development and Digitalisation, relevant donor-funded projects and organisations representatives in the consultation process.

Bidders are encouraged to collaborate with local partners or consultants to support field activities, stakeholder mobilisation, and contextual insights; however, such collaboration is not mandatory. All arrangements remain at the discretion of the bidder.

- Place, duration and terms of performance

The assignment shall be implemented in Chișinău, the Republic of Moldova. While some of the activities could be conducted remotely, the provider selected for this assignment is expected to ensure a strong local presence to facilitate direct engagement with stakeholders, beneficiaries, and institutional partners.

The duration of the assignment is approximately 16 weeks from the date of contract signature. The implementation will follow a phased approach aligned with the indicative timeline from section 4.2 Anticipated deliverables.

- Qualifications and experience

The assignment may be undertaken by a team of experts, a consortium, or an organization. The ideal candidates will demonstrate:

- Proven experience delivering assignments of comparable scope and complexity, including sectoral analysis, multi-stakeholder consultation processes, strategy formulation, and the design of data governance or monitoring systems.

- Demonstrated analytical capabilities and proficiency with data visualisation tools (e.g., Power BI or equivalent).

- Familiarity with Moldova’s startup and innovation ecosystem or with similar emerging ecosystem contexts.

- Experience working in donor-funded projects and multi-stakeholder environments, including coordination with public institutions, private actors, and development partners.

- Ability to deliver clear, concise, and audience-appropriate outputs in English, in both narrative and presentation formats.

- Application documents

The application documents as well as all correspondence and documents relating to this assignment must be written in English.

Candidates must submit the following documents:

- A proof of legal registration (certificate of registration).

- The attached application form - Expression of Interest Form, including the annexes: Sworn Statement on Exclusion Criteria, the Absence of Conflict of Interest and the Third-Party Identification Sheet.

- The attached GDPR compliance verification form, used to verify that the bidder has implemented appropriate technical and organisational measures such that data processing complies with relevant data protection laws and regulations (GDPR and French data protection legislation), thereby guaranteeing the rights of data subjects;

- The draft contract, including the candidate's financial offer, duly completed, dated and signed;

- A technical offer comprising:

- A description of the applicant organization or consortium, including its relevant credentials, track record, and previous experience that demonstrate its suitability for the assignment.

- Curriculum vitae (CVs) of the expert(s) proposed for the implementation of the activities, highlighting their qualifications, thematic expertise, experience in angel investment and prior relevant engagements.

- A detailed financial offer, including:

  - A breakdown of costs presented as a unit price schedule.

  - The schedule should indicate the price per man-day, provide an estimate of the total number of days required to complete the assignment, cover all services and deliverables under the contract, and be consistent with the expected level of effort (approximately 60–80 man-days).

  - The financial offer must also include all associated costs, such as travel, accommodation, venue rental, catering, materials, and any other expenses necessary for the successful implementation of the assignment.

The documents requested above are mandatory. If missing, the tender submitted will not be compliant and will therefore be rejected.

Electronic submission via the French government procurement platform at https://www.marches-publics.gouv.fr is mandatory. Any submission via other means will be rejected.

Deadline for submission: August 28, 2026, COB Paris time.

The period of validity of the offers submitted is fixed at 90 calendar days from the deadline for submission of tenders.

- Evaluation and selection

Expertise France will first check the eligibility of the applications and their ability to provide the service. Subsequently, it will evaluate the offers according to the following criteria:

Criterion 1: Technical offer

Each technically conforming offer will be evaluated based on the following criteria, with a total of 70 points. The Technical Score (TS) will be calculated by summing the points awarded for each sub-criterion.

Technical Offer Evaluation Breakdown

The technical value of each application will be assessed against the following sub-criteria, for a total of 70 points:

| Sub-criteria for assessing the technical quality | Maximum number of points |
| --- | --- |
| Understanding of the Assignment and Context (Clarity in understanding Moldova’s ecosystem challenges, purpose of the strategy, and data monitoring needs) | 20 |
| Quality and Relevance of the Proposed Methodology (Approach for strategy development, data mapping, analysis, dashboard creation, stakeholder engagement, and feasibility within the timeframe) | 20 |
| Expertise and Competence of the Proposed Team (Experience in strategy development, startup ecosystem, data governance, dashboard development, and similar assignments.) | 15 |
| Organisational Experience and Capacity (Relevant past work, institutional capacity to deliver, ability to manage multi-stakeholder assignments.) | 10 |
| Quality and Feasibility of the Work Plan (Coherence, realism, and alignment of the proposed timeline and deliverables.) | 5 |
| TOTAL | 70 |

Minimum Technical Score to Qualify

Only bids scoring 50 points or more in the technical evaluation will proceed to financial assessment.

Criterion 2: Price of the services

The Financial Score (FS), with a maximum of 30 points, will be calculated to allow a comparative assessment of the financial offers submitted by all candidates with conforming bids. The lowest-priced bid will receive the full 30 points, while other bids will be scored proportionally using the following formula:

FS = Lowest Price / Bid Price × 30

Total score will be calculated as a sum of Technical and Financial scores.

- Negotiations

Following the initial analysis of bids by the Evaluation Committee, the contracting authority may enter into negotiations with all or selected bidders, ensuring equal treatment throughout. The contracting authority, however, reserves the right to award the contract without engaging in negotiations.

- Additional information

In order to access the tender consultation space, bidders must connect to the French government procurement platform at:  https://www.marches-publics.gouv.fr

# Annex II – Technical And financial offer

Prohibited practices as defined by the Agence Française de Développement group are defined below: https://www.afd.fr/en/ressources/afd-groups-policy-prevent-and-combat-prohibited-practices-2020